## Data Validation (hidden)
Action (Col E) | Technician (Col L)
Reimage | Berry, Michael
Replace | Hargett, James
Return to Insight | Brooks, Justin
New Deployment | Hendrickson, Bruce
Gamboa, Andrew
Martin, TJ
Campbell, Jarion
Berry, Andrew
Goodson, Don
Hayes, Rodney
Tsedi, Vincent
Banks, Charde
Edmondson, Richard
Dandy, Winston
Raney, Joshua
Case, Shawn
Sanchez, George
Dawson, Mike
Moore, Johney
Freeman, Jamil (Termed)
Lemi, Noel (Termed)
Kennedy, Adam
Alexander, Gary
Chandler, Christopher
McMurry, Barry (Termed)
Alegbeley, Ladi
Cawthon, Joshua
Open 1
Open 2
Open 3
Open 4
Open 5
Open 6
Open 7
Open 8
Open 9
Open 10

## T-Schedule (hidden)
Wave | Facility ID | WIN 10 Upgrade Date | HCHB+75 days HCHB | H-4 HCHB OLH Training | HCHB Go Live Date | Tech Resources | Number of Sites | WIN 10 Upgraded | CI Facility Number | Old CI | Facility ID | Site Name (Intake sites in Bold) (Blue background indicates Corp/Regional Offices) | Street Address | City | State | ZIP | Main Number | Executive Director | Office MGR | Subnet | Shares Network | Total Employees | Estimate Total Employees | Approx. VDI Users | Estimate Total Laptops to Reimage | Actual Total Laptops to Reimage | Estimate Total Laptops to Replace | Total Laptops to Replace | Estimate Total Desktops To Replace | Total Thin Clients to Install | %VDI | System Scan Site Total | Site Survey Total | Job
Alpha | 5049201 | 2019-06-24 | 2019-07-09 | 2019-07-16 | 2019-08-13 | 2 | 2 | Yes | Y-6964 | WS | 5049201 | 5049 HH - SALISBURY | 1834 West Jake Alexander Blvd. STE 503 | Salisbury | NC | 28147 | (704)636-3334 | Donna Willis | Aulen Sellers-Cook | 10.25.92 |  | 53 | 49 | 48 | 5 | 5 | 0 | 0 | 10 | 14 | 28.57% | 15 |  | WIN 10 Upgrade
| 5056201 | 2019-06-24 | 2019-07-09 | 2019-07-16 | 2019-08-13 |  |  | Yes | Y-6964 | WS | 5056201 | 5056 HH - IREDELL CO | 1905 East Broad Street | Statesville | NC | 28625 | (704)872-3606 | Christine Rombough |  | 10.25.94 |  | 73 | 66 | 70 | 1 | 3 | 2 | 5 | 10 | 19 | 28.79% | 13 | 27 | WIN 10 Upgrade
| 2475201 | 2019-06-24 | 2019-07-09 | 2019-07-16 | 2019-08-13 | 1 | 1 | Yes | Y-2191 | EC | 2475201 | 2475 HH - PANAMA CITY | 1013 Beck Avenue | Panama City | FL | 32401 | (850)769-3398 | Gwen Kady | Lindsey Demro | 10.24.204 |  | 70 | 70 | 60 | 10 | 9 | 0 | 0 | 17 | 9 | 12.86% | 27 |  | WIN 10 Upgrade
| 5033201 | 2019-06-24 | 2019-07-09 | 2019-07-16 | 2019-08-13 | 2 | 2 | Yes | Y-1143 | WS | 5033201 | 5033 HH - KINSTON | 2111 North Queen Street STE C | Kinston | NC | 28501 | (252)522-1458 | Ginger Whaley | Wilma Edwards | 10.25.84 |  | 33 | 34 | 29 | 4 | 4 | 0 | 1 | 5 | 9 | 26.47% | 9 |  | WIN 10 Upgrade
| 5031201 | 2019-06-24 | 2019-07-09 | 2019-07-16 | 2019-08-13 |  |  | Yes | Y-1143 | WS | 5031201 | 5031 HH - GOLDSBORO | 1200 Parkway Dr. | Goldsboro | NC | 27534 | (919)731-7254 | Debra Walker |  | 10.25.77 |  | 51 | 39 | 48 | 3 | 4 | 0 | 0 | 6 | 16 | 41.03% | 9 |  | WIN 10 Upgrade
Wave 1 | 5023201 | 2019-07-01 | 2019-07-09 | 2019-07-16 | 2019-08-13 | 1 | 2 | Yes | Y-1143 | WS | 5023201 | 5023 HH - KIMEL PARK | 2000 Frontis Plaza Blvd STE 300 | Winston-Salem | NC | 27103 | (336)659-3300 |  |  | 10.25.34 | 5027 | 44 | 41 | 36 | 7 | 8 | 1 | 2 | 6 | 17 | 41.46% | 14 |  | WIN 10 Upgrade
| 5027201 | 2019-07-01 | 2019-07-09 | 2019-07-16 | 2019-08-13 |  |  | Yes | Y-1143 | WS | 5027201 | 5027 HH - WAKE FOREST JV (fka 2353) Intake? | 2000 Frontis Plaza Blvd STE 303 | Winston-Salem | NC | 27103 | (336)760-1838 | Kristen Craver |  | 10.24.26 | 5023 | 34 | 28 | 29 | 4 | 4 | 1 | 1 | 9 | 14 | 50% | 14 |  | WIN 10 Upgrade
| 5047201 | 2019-07-01 | 2019-07-09 | 2019-07-16 | 2019-08-13 | 1 | 1 | Yes | Y-6964 | WS | 5047201 | 5047 HH - KING | 621 Ingram Drive STE B | King | NC | 27021 | (336)983-2110 | Michelle Roseman |  | 10.25.83 |  | 56 | 52 | 50 | 3 | 5 | 3 | 6 | 10 | 11 | 21.15% | 16 |  | WIN 10 Upgrade
| 2472201 | 2019-07-01 | 2019-07-09 | 2019-07-16 | 2019-08-13 | 1 | 1 | Yes | Y-2191 | EC | 2472201 | 2472 HH - FT WALTON BEACH Intake | 340 Beal Parkway NW STE A | Fort Walton Beach | FL | 32548 | (850)862-3240 | Kerry Colvin | Jill Harvard | 10.24.186 |  | 50 | 46 | 36 | 12 | 38 | 2 | 1 | 8 | 6 | 13.04% | 22 | 45 | WIN 10 Upgrade
| 5034201 | 2019-07-01 | 2019-07-09 | 2019-07-16 | 2019-08-13 | 1 | 2 | Yes | Y-1143 | WS | 5034201 | 5034 HH - MOREHEAD | Cypress Bay Plaza, 5167 US Hwy 70 West STE 100 | Morehead City | NC | 28557 | (252)726-9300 | Debra Vitelle |  | 10.25.87 |  | 25 | 25 | 18 | 3 | 6 | 4 | 1 | 3 | 6 | 24% | 10 | 13 | WIN 10 Upgrade
| 5036201 | 2019-07-01 | 2019-07-09 | 2019-07-16 | 2019-08-13 |  |  | Yes | Y-1143 | WS | 5036201 | 5036 HH - POLLOCKSVILLE | P. O. Box 399, 124 Main Street | Pollocksville | NC | 28573 | (252)224-1012 | Kimberly Carder |  | 10.25.89 |  | 52 | 54 | 47 | 5 | 7 | 0 | 0 | 9 | 7 | 12.96% | 14 | 14 | WIN 10 Upgrade
| 5029201 | 2019-07-01 | 2019-07-09 | 2019-07-16 | 2019-08-13 | 1 | 2 | Yes | Y-1143 | WS | 5029201 | 5029 HH - YOUNGSVILLE | 74 Wheaton Avenue | Youngsville | NC | 27596 | (919)554-2279 | Jessica Richardson |  | 10.25.101 |  | 33 | 28 | 30 | 3 | 3 | 0 | 2 | 6 | 9 | 32.14% | 9 | 14 | WIN 10 Upgrade
| 1294201 | 2019-07-01 | 2019-07-09 | 2019-07-16 | 2019-08-13 |  |  | Yes | Y-1143 |  | 1294201 | 1294 HH - LILLINGTON NC | 87 W Cornelius Harnett Boulevard | Lillington | NC | 27546 | (910)808-4556 | Laura Hardison |  | 10.160.254 |  | 20 | 21 | 20 | 0 | 2 | 0 | 0 | 4 | 4 | 19.05% | 4 | 6 | WIN 10 Upgrade
| 5058201 | 2019-07-01 | 2019-07-09 | 2019-07-16 | 2019-08-13 | 1 | 1 | Yes | Y-6964 | CH | 5058201 | 5058 HH - ASHEVILLE | 9 Olde Eastwood Village Blvd. | Asheville | NC | 28803 | (828)298-1370 | Jennifer Parker |  | 10.25.69 |  | 212 | 203 | 200 | 10 | 10 | 2 | 4 | 18 | 29 | 14.29% | 30 | 43 | WIN 10 Upgrade
| 5032201 | 2019-07-01 | 2019-07-09 | 2019-07-16 | 2019-08-13 | 1 | 2 | Yes | Y-1143 | WS | 5032201 | 5032 HH - GREENVILLE NC | 1970 West Arlington Blvd. STE B-2 | Greenville | NC | 27834 | (252)353-3300 | June Grimsley | Tanya Letchworth | 10.25.79 |  | 75 | 65 | 69 | 6 | 7 | 0 | 1 | 12 | 10 | 15.38% | 18 | 18 | WIN 10 Upgrade
| 5038201 | 2019-07-01 | 2019-07-09 | 2019-07-16 | 2019-08-13 |  |  | Yes | Y-1143 | WS | 5038201 | 5038 HH - WASHINGTON | 1638 Carolina Ave. | Washington | NC | 27889 | (252)946-7145 | Christy Watkins | Erin Wichard | 10.25.95 |  | 99 | 89 | 93 | 6 | 5 | 0 | 0 | 13 | 20 | 22.47% | 19 | 25 | WIN 10 Upgrade
| 5060201 | 2019-07-01 | 2019-07-09 | 2019-07-16 | 2019-08-13 | 1 | 2 | Yes | Y-6964 | CH | 5060201 | 5060 HH - HICKORY | 1771 Tate Blvd. SE STE 104 | Hickory | NC | 28602 | (828)322-6131 | Bobbi Willis |  | 10.25.81 | 5061 | 56 | 53 | 47 | 7 | 1 | 2 | 0 | 25 | 12 | 22.64% | 34 | 13 | WIN 10 Upgrade
| 5061201 | 2019-07-01 | 2019-07-09 | 2019-07-16 | 2019-08-13 |  |  | Yes | Y-6964 | CH | 5061201 | 5061 HH - HICKORY (Healthfield) | 1771 Tate Blvd. SE STE 101 | Hickory | NC | 28602 | (828)328-8090 | Bobbi Willis |  | 10.25.81 | 5060 | 87 | 83 | 87 |  | 14 |  | 0 |  | 23 | 27.71% | 0 | 37 | WIN 10 Upgrade
| 5063201 | 2019-07-08 | 2019-07-09 | 2019-07-16 | 2019-08-13 | 1 | 2 | Yes | Y-6964 | CH | 5063201 | 5063 HH - SHELBY | 1405 N Lafayette Street | Shelby | NC | 28150 | (704)484-3294 | Melissa Lackey | Chasity Goode | 10.25.93 |  | 115 | 113 | 106 | 6 | 10 | 3 | 5 | 19 | 28 | 24.78% | 28 | 43 | WIN 10 Upgrade
| 6989201 | 2019-07-08 | 2019-07-09 | 2019-07-16 | 2019-08-13 |  |  | Yes | Y-6964 |  | 6989201 | 6989 HH - LINCOLN COUNTY | 308 S Academy Street | Lincolnton | NC | 28092 | (704)736-4570 |  |  | 10.234.49 |  | 26 | 28 | 26 | 0 | 2 | 0 | 0 | 5 | 6 | 21.43% | 5 | 8 | WIN 10 Upgrade
Wave 2 | 2439201 | 2019-07-15 | 2019-08-27 | 2019-09-03 | 2019-10-01 | 1 | 1 | Yes | Y-6956 |  | 2439201 | 2439 HH - STROUDSBURG PA + Bethlehem Drop Site | 1250 N. 9th St. STE 105 | Stroudsburg | PA | 18360 | (570)424-7790 | Lisa Goldner | Paula Desmond | 10.25.140 |  | 79 | 71 | 70 | 6 | 7 | 3 | 6 | 15 | 13 | 18.31% | 24 | 26 | WIN 10 Upgrade
| 2399201 | 2019-07-15 | 2019-08-27 | 2019-09-03 | 2019-10-01 | 1 | 1 | Yes | Y-6956 |  | 2399201 | 2399 HH - AKRON | 1531 Boettler Road STE E | Uniontown | OH | 44685 | (330)644-4447 | Cynthia Rodeman |  | 10.160.181 |  | 28 | 26 | 23 | 4 | 4 | 1 | 0 | 4 | 4 | 15.38% | 9 | 8 | WIN 10 Upgrade
| 2473201 | 2019-07-22 | 2019-07-09 | 2019-07-16 | 2019-08-13 | 1 | 1 | Yes | Y-2191 | EC | 2473201 | 2473 HH - CRESTVIEW | 370 W Redstone Ave | Crestview | FL | 32536 | (850)682-9615 | Dionne Stauffer | Marcia Clifton | 10.24.182 |  | 37 | 33 | 26 | 9 | 10 | 2 | 2 | 5 | 12 | 36.36% | 16 | 24 | WIN 10 Upgrade
| 5030201 | 2019-07-22 | 2019-07-09 | 2019-07-16 | 2019-08-13 | 2 | 1 | Yes | Y-1143 | WS | 5030201 | 5030 HH - RALEIGH | 3301 Benson Drive STE 222 | Raleigh | NC | 27609 | (919)881-9492 | Pamela Williams | Carol Allen | 10.25.90 |  | 127 | 92 | 105 | 20 | 22 | 2 | 10 | 16 | 23 | 25% | 38 | 55 | WIN 10 Upgrade
| 5084201 | 2019-07-22 | 2019-08-27 | 2019-09-03 | 2019-10-01 | 2 | 2 | Yes | Y-6964 | VB | 5084201 | 5084 HH - KNOXVILLE | 320 North Cedar Bluff Road STE 380/360 | Knoxville | TN | 37923 | (865)690-7767 | Bethany Runions | Kimberly Hall | 10.21.62 |  | 30 | 29 | 26 | 4 | 7 | 0 | 0 | 3 | 7 | 24.14% | 7 | 14 | WIN 10 Upgrade
| 5083201 | 2019-07-22 | 2019-08-27 | 2019-09-03 | 2019-10-01 |  |  | Yes | Y-6964 | VB | 5083201 | 5083 HH - KINGSPORT | 2004 American Way STE 121 | Kingsport | TN | 37660 | (423)230-1000 | Valerie Flint | Danielle Bowman | 10.25.172 |  | 36 | 37 | 30 | 5 | 5 | 1 | 0 | 4 | 10 | 27.03% | 10 | 15 | WIN 10 Upgrade
| 5085201 | 2019-08-05 | 2019-08-27 | 2019-09-03 | 2019-10-01 | 1 | 2 | Yes | Y-6964 | VB | 5085201 | 5085 HH - CHATTANOOGA | 5751 Cornelison Road Bldg 6400 B STE 100 | Chattanooga | TN | 37411 | (423)892-1122 | Bethany Runions | September Smith | 10.25.170 |  | 16 | 10 | 11 | 5 | 3 | 0 | 1 | 3 | 4 | 40% | 8 | 8 | WIN 10 Upgrade
| 2468201 | 2019-08-05 | 2019-10-08 | 2019-10-15 | 2019-11-12 |  |  | Yes | Y-6952 | GA | 2468201 | 2468 HH - ROME | 504 Riverside Parkway NE STE 500 | Rome | GA | 30161 | (706)235-1841 | Melissa Touchstone, AVP Ops | Jana Hunter | 10.24.235 |  | 71 | 65 | 65 | 5 | 6 | 1 | 2 | 5 | 13 | 20% | 11 | 21 | WIN 10 Upgrade
| 5080201 | 2019-08-05 | 2019-08-27 | 2019-09-03 | 2019-10-01 | 1 | 2 | Yes | Y-6964 | VB | 5080201 | 5080 HH - LEBANON TN | 115 Winwood Dr. STE 101 | Lebanon | TN | 37087 | (615)449-0045 | Tracy Reddick | Rita Maynard | 10.25.173 |  | 38 | 34 | 34 | 3 | 4 | 1 | 1 | 8 | 9 | 26.47% | 12 | 14 | WIN 10 Upgrade
| 5082201 | 2019-08-05 | 2019-08-27 | 2019-09-03 | 2019-10-01 |  |  | Yes | Y-6964 | VB | 5082201 | 5082 HH - SMYRNA | 697 President Place STE 303B | Smyrna | TN | 37167 | (615)220-6183 | Stephanie Todd, CTC |  | 10.25.175 |  | 11 | 9 | 11 | 0 | 0 | 0 | 0 | 0 | 2 | 22.22% | 0 | 2 | WIN 10 Upgrade
| 2655201 | 2019-08-12 | 2019-08-27 | 2019-09-03 | 2019-10-01 | 3 | 1 | Yes |  |  | 2655201 | 2655 HH - SEATTLE | 155 NE 100th Street STE 510 | Seattle | WA | 98125 | (206)729-7773 | Sandra Winmill | Eileen Vargas | 10.24.33 |  | 47 | 42 | 34 | 12 | 9 | 1 | 0 | 18 | 14 | 33.33% | 31 | 23 | WIN 10 Upgrade
| 7026201 | 2019-08-12 | 2019-08-27 | 2019-09-03 | 2019-10-01 | 2 | 2 | Yes |  |  | 7026201 | 7026 HH - EVERETT (fka 2654) | 728 134TH ST SW, Suite 203 | Everett | WA | 98204 | (425)745-4345 | Dori Shane | Jennifer Garcia | 10.25.114 |  | 31 | 30 | 26 | 5 | 7 | 0 | 0 | 7 | 13 | 43.33% | 12 | 20 | WIN 10 Upgrade
| 7027201 | 2019-08-12 | 2019-08-27 | 2019-09-03 | 2019-10-01 |  |  | Yes |  |  | 7027201 | 7027 HH - BELLEVUE WA | 10940 NE 33rd Place STE 103 | Bellevue | WA | 98004 | (425)827-2415 | Annalisa Atienza | Erin King | 10.25.111 |  | 35 | 39 | 28 | 6 | 8 | 1 | 1 | 6 | 12 | 30.77% | 13 | 21 | WIN 10 Upgrade
| 2438201 | 2019-08-12 | 2019-08-27 | 2019-09-03 | 2019-10-01 | 2 | 2 | Yes | Y-6956 | NY | 2438201 | 2438 HH - WESTBURY | 865 Merrick Avenue STE 340 South | Westbury | NY | 11590 | (516)746-8013 | James Egan |  | 10.25.123 |  | 49 | 41 | 43 | 6 | 5 | 0 | 0 | 8 | 10 | 24.39% | 14 | 15 | WIN 10 Upgrade
| 3197201 | 2019-08-12 | 2019-08-27 | 2019-09-03 | 2019-10-01 |  |  | Yes | Y-6956 | NY | 3197201 | 3197 HH - RIVERHEAD NEW | 877 East Main St. | Riverhead | NY | 11901 | (631)727-5353 | Eric Lawrence | Val Sutton-Risi | 10.25.122 |  | 44 | 43 | 40 | 4 | 5 | 0 | 1 | 3 | 12 | 27.91% | 7 | 18 | WIN 10 Upgrade
| 2685201 | 2019-08-12 | 2019-08-27 | 2019-09-03 | 2019-10-01 | 2 | 2 | Yes |  |  | 2685201 | 2685 HH - VANCOUVER | 204 SE Stone Mill Drive STE 260 | Vancouver | WA | 98684 | (360)253-7746 | Tamala Reno | Daniela Jeffries | 10.25.213 |  | 45 | 38 | 40 | 4 | 6 | 1 | 2 | 4 | 11 | 28.95% | 9 | 19 | WIN 10 Upgrade
| 2697201 | 2019-08-12 | 2019-08-27 | 2019-09-03 | 2019-10-01 |  |  | Yes |  |  | 2697201 | 2697 HH - PORTLAND OR HHA | 4500 Kruse Way STE 310 | Lake Oswego | OR | 97035 | (503)620-3407 | Anna Snow |  | 10.25.132 |  | 33 | 31 | 25 | 8 | 6 | 0 | 0 | 8 | 8 | 25.81% | 16 | 14 | WIN 10 Upgrade
| 2395201 | 2019-08-12 | 2019-08-27 | 2019-09-03 | 2019-10-01 | 2 | 2 | Yes | Y-6956 |  | 2395201 | 2395 HH - GRAND RAPIDS | 625 Kenmoor Avenue SE STE 306 | Grand Rapids | MI | 49546 | (616)942-5744 | Jennifer Mamp |  | 10.25.45 |  | 47 | 35 | 38 | 7 | 7 | 2 | 7 | 7 | 7 | 20% | 16 | 21 | WIN 10 Upgrade
| 2394201 | 2019-08-12 | 2019-08-27 | 2019-09-03 | 2019-10-01 |  |  | Yes | Y-6956 |  | 2394201 | 2394 HH - FLINT | 4458 Oakbridge Drive STE B | Flint | MI | 48532 | (810)732-9030 | Tobi Rutherford |  | 10.25.43 |  | 40 | 37 | 34 | 5 | 3 | 1 | 0 | 6 | 7 | 18.92% | 12 | 10 | WIN 10 Upgrade
| 2393201 | 2019-08-12 | 2019-08-27 | 2019-09-03 | 2019-10-01 | 1 | 1 | Yes | Y-6956 |  | 2393201 | 2393 HH - KALAMAZOO | 5148 Lovers Lane STE 210 | Portage | MI | 49002 | (269)381-5620 | Kaycie Churchman |  | 10.25.46 |  | 50 | 50 | 40 | 8 | 6 | 2 | 0 | 6 | 10 | 20% | 16 | 16 | WIN 10 Upgrade
| 2626201 | 2019-08-12 | 2019-08-27 | 2019-09-03 | 2019-10-01 | 2 | 2 | Yes |  |  | 2626201 | 2626 HH - SAN JOSE - HARDEN | 1840 The Alameda | San Jose | CA | 95126 | (408)283-5100 | Hui Fang | Meiying Cao | 10.21.227 |  | 101 | 99 | 97 | 4 | 3 | 0 | 0 | 20 | 19 | 19.19% | 24 | 22 | WIN 10 Upgrade
| 2617201 | 2019-08-12 | 2019-08-27 | 2019-09-03 | 2019-10-01 |  |  | Yes |  |  | 2617201 | 2617 HH - SAN JOSE HHA | 4030 Moorpark Ave. STE 251 | San Jose | CA | 95117 | (408)261-2801 | Anniebeth Nacino | Grace Guidicotti | 10.24.148 |  | 38 | 36 | 30 | 8 | 7 | 0 | 0 | 4 | 6 | 16.67% | 12 | 13 | WIN 10 Upgrade
| 2436201 | 2019-08-19 | 2019-08-27 | 2019-09-03 | 2019-10-01 | 2 | 1 | Yes | Y-6956 | NY | 2436201 | 2436 HH - HAUPPAUGE | 888 Veterans Memorial Highway STE 210 | Hauppauge | NY | 11788 | (631)232-6030 | Elizabeth Anderson |  | 10.25.118 |  | 77 | 74 | 68 | 6 | 7 | 3 | 5 | 16 | 18 | 24.32% | 25 | 30 | WIN 10 Upgrade
| 2623201 | 2019-08-26 | 2019-08-27 | 2019-09-03 | 2019-10-01 | 2 | 2 | Yes |  |  | 2623201 | 2623 HH - OAKLAND | 1301 Marina Village Parkway STE 103 | Alameda | CA | 94501 | (510)835-3268 | Shuchen Chen | Lu Jiang | 10.21.228 |  | 76 | 72 | 74 | 2 | 1 | 0 | 0 | 13 | 17 | 23.61% | 15 | 18 | WIN 10 Upgrade
| 7021201 | 2019-08-26 |  |  | 2019-04-09 |  |  | Yes |  |  | 7021201 | 7021 HH - SANTA ROSA | 5341 Old Redwood Highway, STE 350 | Peteluma | CA | 94954 | (707)545-7114 | Beverly Garcia | Amy Hayes | 10.24.151 |  | 44 | 42 | 40 | 4 | 7 | 0 | 0 | 7 | 10 | 23.81% | 11 | 17 | WIN 10 Upgrade
| 2111201 | 2019-08-26 | 2019-08-27 | 2019-09-03 | 2019-10-01 | 1 | 2 | Yes |  |  | 2111201 | 2111 HH - TACOMA (Equipment Onsite) | 4020 South 56th St. STE 101 | Tacoma | WA | 98409 | (253)475-6862 | Mel Nickel |  | 10.25.212 |  | 60 | 56 | 60 | 0 | 11 | 0 | 3 | 12 | 13 | 23.21% | 12 | 27 | WIN 10 Upgrade
| 2730201 | 2019-08-26 | 2019-08-27 | 2019-09-03 | 2019-10-01 |  |  | Yes |  |  | 2730201 | 2730 HH - PUYALLUP WA (2134 in KD) | 2913 NE 5th Avenue STE 202 | Puyallup | WA | 98372 | (253)435-9953 | Latasha Newkirk |  | 10.25.209 |  | 39 | 37 | 37 | 2 | 0 | 0 | 0 | 4 | 5 | 13.51% | 6 | 5 | WIN 10 Upgrade
| 2534201 | 2019-09-09 | 2019-07-28 |  | 2019-05-14 | 1 | 2 | Yes | Y-6959 | AL | 2534201 | 2534 HH - FORT PAYNE | 716 Gault Avenue N | Fort Payne | AL | 35967 | (256)845-8994 | Amanda Chisenhall |  | 10.24.103 |  | 19 | 18 | 17 | 1 | 2 | 1 | 2 | 3 | 3 | 16.67% | 5 | 7 | WIN 10 Upgrade
| 2533201 | 2019-09-09 | 2019-07-28 |  | 2019-05-14 |  |  | Yes | Y-6959 | AL | 2533201 | 2533 HH - ALBERTVILLE | 700 AL Hwy 75 N | Albertville | AL | 35951 | (256)878-1113 | Tiffany Curvin |  | 10.24.85 |  | 27 | 25 | 24 | 3 | 4 | 0 | 1 | 5 | 7 | 28% | 8 | 12 | WIN 10 Upgrade
| 2536201 | 2019-09-16 | 2019-07-28 |  | 2019-05-14 | 1 | 1 | Yes | Y-6959 | AL | 2536201 | 2536 HH - FLORENCE | 3242 Florence Boulevard | Florence | AL | 35634 | (256)764-9001 | Vicki Tays | Angie Marks | 10.24.100 |  | 41 | 35 | 39 | 2 | 2 | 0 | 0 | 8 | 10 | 28.57% | 10 | 12 | WIN 10 Upgrade
| 2458201 | 2019-09-16 | 2020-01-26 | 2019-10-15 | 2019-11-12 | 1 | 1 | Yes | Y-6959 | AL | 2458201 | 2458 HH - COLUMBUS GA | 1921 Whittlesey Road STE 310 | Columbus | GA | 31904 | (706)649-7990 | Jessica Hill | Nikki Taft | 10.24.226 |  | 43 | 31 | 38 | 5 | 9 | 0 | 1 | 6 | 9 | 29.03% | 11 | 19 | WIN 10 Upgrade
| 2492201 | 2019-09-30 | 2019-07-28 |  | 2019-05-14 | 1 | 1 | Yes |  | MS | 2492201 | 2492 HH - GILBERTOWN AL | 114 North Academy Ave | Butler | AL | 36904 | (251)843-2808 | Kassie McInnis | Suzanne Littlepage | 10.24.105 |  | 27 | 26 | 25 | 2 | 3 | 0 | 1 | 3 | 5 | 19.23% | 5 | 9 | WIN 10 Upgrade
| 2490201 | 2019-11-04 | 2019-07-28 |  | 2019-05-14 | 1 | 1 | Yes |  | MS | 2490201 | 2490 HH - MERIDIAN MS | 2600 Old North Hills Street | Meridian | MS | 39305 | (601)482-5055 | Kimberly Bihn |  | 10.25.61 |  | 46 | 42 | 39 | 7 | 9 | 0 | 1 | 5 | 10 | 23.81% | 12 | 20 | WIN 10 Upgrade
| 2491201 | 2019-11-04 | 2019-07-28 |  | 2019-05-14 | 1 | 1 | Yes |  | MS | 2491201 | 2491 HH - PHILADELPHIA MS | 250 Canal Place | Philadelphia | MS | 39350 | (601)389-2105 | Juan Sparnecht | Darlene Bryan | 10.25.63 |  | 46 | 37 | 44 | 0 | 3 | 2 | 2 | 6 | 10 | 27.03% | 8 | 15 | WIN 10 Upgrade
| 2505201 | 2019-11-04 | 2019-07-28 |  | 2019-05-14 | 1 | 1 | Yes |  | MS | 2505201 | 2505 HH - MADISON | 1082 Gluckstadt Road STE B | Madison | MS | 39110 | (601)605-2829 | Alice Wooten |  | 10.92.10 |  | 14 | 15 | 12 | 2 | 2 | 0 | 0 | 3 | 3 | 20% | 5 | 5 | WIN 10 Upgrade
| 2498201 | 2019-11-04 | 2019-07-28 |  | 2019-05-14 | 1 | 1 | Yes |  | MS | 2498201 | 2498 HH - NEW ALBANY MS | 407 Doctors Dr. | New Albany | MS | 38652 | (662)534-0106 | Kimberly Brown |  | 10.22.10 |  | 26 | 30 | 23 | 2 | 4 | 1 | 1 | 4 | 6 | 20% | 7 | 11 | WIN 10 Upgrade
| 2497201 | 2019-11-04 | 2019-07-28 |  | 2019-05-14 | 1 | 1 | Yes |  | MS | 2497201 | 2497 HH - BOONEVILLE | 200 South Second St. | Booneville | MS | 38829 | (662)720-0066 | Deborah Fleming |  | 10.25.10 |  | 49 | 46 | 47 | 2 | 5 | 0 | 0 | 8 | 10 | 21.74% | 10 | 15 | WIN 10 Upgrade
| 2499201 | 2019-11-04 | 2019-07-28 |  | 2019-05-14 | 1 | 1 | Yes |  | MS | 2499201 | 2499 HH - RIPLEY MS | 902 North Main Street STE D | Ripley | MS | 38663 | (662)837-7005 | Carissa Hopkins |  | 10.23.10 |  | 25 | 27 | 21 | 1 | 4 | 3 | 0 | 2 | 6 | 22.22% | 6 | 10 | WIN 10 Upgrade
| 2493201 | 2019-11-04 | 2019-07-28 |  | 2019-05-14 | 1 | 1 | Yes |  | MS | 2493201 | 2493 HH - TUPELO | 3402 West Main St. | Tupelo | MS | 38801 | (662)844-9725 | Angela Murphy | Sandy Winfrey | 10.21.10 |  | 27 | 25 | 23 | 3 | 5 | 1 | 1 | 5 | 7 | 28% | 9 | 13 | WIN 10 Upgrade
| 2496201 | 2019-11-04 | 2019-07-28 |  | 2019-05-14 | 1 | 1 | Yes |  | MS | 2496201 | 2496 HH - AMORY | 1225 Hwy 278 East | Amory | MS | 38821 | (662)256-5404 | Kelly Mann |  | 10.62.10 |  | 33 | 30 | 31 | 1 | 4 | 1 | 2 | 9 | 7 | 23.33% | 11 | 13 | WIN 10 Upgrade
| 2504201 | 2019-11-04 | 2019-07-28 |  | 2019-05-14 | 1 | 1 | Yes |  | MS | 2504201 | 2504 HH - VICKSBURG | 2080 S. Frontage Rd. STE 101 | Vicksburg | MS | 39180 | (601)638-3808 | Nena Longmire | Jenny Bowers Sanders | 10.91.10 |  | 24 | 28 | 19 | 3 | 3 | 2 | 0 | 3 | 7 | 25% | 8 | 10 | WIN 10 Upgrade
| 2506201 | 2019-11-04 | 2019-07-28 |  | 2019-05-14 | 1 | 1 | Yes |  | MS | 2506201 | 2506 HH - HAZLEHURST | 217 Caldwell Drive | Hazlehurst | MS | 39083 | (601)894-2701 | Wendy Falvey | Renee Smith | 10.32.10 |  | 26 | 19 | 23 | 3 | 3 | 0 | 0 | 6 | 5 | 26.32% | 9 | 8 | WIN 10 Upgrade
| 2508201 | 2019-11-11 | 2019-07-28 |  | 2019-05-14 | 1 | 2 | Yes |  | MS | 2508201 | 2508 HH - MAGEE | 306 2nd Street SE | Magee | MS | 39111 | (601)849-6263 | Vicky Stubbs |  | 10.34.10 |  | 26 | 26 | 21 | 5 | 4 | 0 | 0 | 7 | 8 | 30.77% | 12 | 12 | WIN 10 Upgrade
| 2507201 | 2019-11-11 | 2019-07-28 |  | 2019-05-14 |  |  | Yes |  | MS | 2507201 | 2507 HH - MORTON MS | 5325 Hwy 80 | Morton | MS | 39117 | (601)732-3952 | Jennifer Russell |  | 10.94.10 |  | 27 | 26 | 24 | 3 | 7 | 0 | 0 | 6 | 6 | 23.08% | 9 | 13 | WIN 10 Upgrade
| 2494201 | 2019-11-11 | 2019-07-28 |  | 2019-05-14 | 1 | 1 | Yes |  | MS | 2494201 | 2494 HH - COLUMBUS MS | 189 Park Creek Drive | Columbus | MS | 39705 | (662)327-9669 | Joni Prescott | Cassandra Bogan | 10.61.10 |  | 26 | 26 | 22 | 4 | 6 | 0 | 1 | 8 | 8 | 30.77% | 12 | 15 | WIN 10 Upgrade
| 2487201 | 2019-11-11 | 2019-09-29 |  | 2019-07-16 | 1 | 1 | Yes | Y-2191 | TM | 2487201 | 2487 HH - OCALA | 311 SE 17th Place | Ocala | FL | 34471 | (352)402-0660 | Mary Ryals | Janelle Marshall | 10.24.200 |  | 57 | 53 | 46 | 11 | 6 | 0 | 6 | 7 | 14 | 26.42% | 18 | 26 | WIN 10 Upgrade
| 2488201 | 2019-11-11 | 2019-06-23 |  | 2019-04-09 | 1 | 1 | Yes | Y-2191 | TM | 2488201 | 2488 HH - PALATKA-PUTNAM | 205 Zeagler Dr STE 401 | Palatka | FL | 32177 | (386)328-0202 | Kasey Brown |  | 10.24.203 |  | 22 | 20 | 13 | 9 | 4 | 0 | 1 | 2 | 6 | 30% | 11 | 11 | WIN 10 Upgrade
| 2483201 | 2019-11-11 | 2019-09-29 |  | 2019-07-16 | 1 | 1 | Yes | Y-2191 | TM | 2483201 | 2483 HH - ORANGE PARK | 350 Corporate Way STE 250 | Orange Park | FL | 32073 | (904)731-3515 | Anna Niemiec | Catrilla Stringfield | 10.24.189 |  | 44 | 41 | 33 | 11 |  | 0 |  | 9 |  | 0% | 20 | 0 | WIN 10 Upgrade
| 2479201 | 2019-11-11 | 2019-06-23 |  | 2019-04-09 | 1 | 1 | Yes | Y-2191 | TM | 2479201 | 2479 HH - DAYTONA BEACH | 1717 North Clyde Morris Blvd. STE 140 | Daytona Beach | FL | 32117 | (386)274-1088 | Jamie Cameron |  | 10.24.184 |  | 44 | 39 | 32 | 12 | 9 | 0 | 2 | 6 | 11 | 28.21% | 18 | 22 | WIN 10 Upgrade
| 2480201 | 2019-11-11 | 2019-06-23 |  | 2019-04-09 | 1 | 1 | Yes | Y-2191 | TM | 2480201 | 2480 HH - DELAND | 929 North Spring Garden Ave STE 100 | Deland | FL | 32720 | (386)736-9224 | Janice Price |  | 10.24.185 |  | 49 | 38 | 37 | 11 | 7 | 1 | 0 | 6 | 6 | 15.79% | 18 | 13 | WIN 10 Upgrade
| 2495201 | 2019-11-18 | 2019-07-28 |  | 2019-05-14 | 1 | 2 | Yes |  | MS | 2495201 | 2495 HH - CALHOUN CITY | 200 South Pontotoc Drive, Suite A | Bruce | MS | 38915 | (662)628-6657 | Autumn Chrestman | Donna Wall | 10.63.10 |  | 27 | 27 | 21 | 6 | 5 | 0 | 0 | 7 | 8 | 29.63% | 13 | 13 | WIN 10 Upgrade
| 2502201 | 2019-11-18 | 2019-07-28 |  | 2019-05-14 |  |  | Yes |  | MS | 2502201 | 2502 HH - STARKVILLE MS | 1085 Stark Road STE 306 | Starkville | MS | 39759 | (662)323-6777 | Jennifer Alexander |  | 10.66.10 |  | 28 | 27 | 24 | 4 | 5 | 0 | 2 | 6 | 7 | 25.93% | 10 | 14 | WIN 10 Upgrade
| 2481201 | 2019-11-18 | 2019-09-29 |  | 2019-07-16 | 2 | 1 | Yes | Y-2191 | TM | 2481201 | 2481 HH - GAINESVILLE | 3951 NW 48th Terrace STE 201 | Gainesville | FL | 32606 | (352)376-3221 | Dyan Anderson | Mary Ellis | 10.24.188 |  | 56 | 40 | 39 | 17 | 9 | 0 | 0 | 9 | 10 | 25% | 26 | 19 | WIN 10 Upgrade
| 2489201 | 2019-11-18 | 2019-10-27 |  | 2019-08-13 | 1 | 2 | Yes | Y-2191 | TM | 2489201 | 2489 HH - TALLAHASSEE | 2450 Tim Gamble Place | Tallahassee | FL | 32308 | (850)878-2191 | Andrea Granger | Deborah McKnight | 10.24.212 |  | 69 | 62 | 59 | 10 | 12 | 0 | 0 | 11 | 16 | 25.81% | 21 | 28 | WIN 10 Upgrade
| 2482201 | 2019-11-18 | 2019-09-29 |  | 2019-07-16 |  |  | Yes | Y-2191 | TM | 2482201 | 2482 HH - TRENTON | 413 East Wade Street | Trenton | FL | 32693 | (352)463-7411 | David Neilson |  | 10.24.179 |  | 35 | 31 | 34 | 1 | 2 | 0 | 3 | 6 | 11 | 35.48% | 7 | 16 | WIN 10 Upgrade
| 2484201 | 2019-11-18 | 2019-09-29 |  | 2019-07-16 | 1 | 2 | Yes | Y-2191 | TM | 2484201 | 2484 HH - LIVE OAK | 712 Ohio Avenue South | Live Oak | FL | 32064 | (386)364-4593 | Marsha Jarrell |  | 10.24.195 |  | 23 | 22 | 18 | 5 | 3 | 0 | 0 | 7 | 6 | 27.27% | 12 | 9 | WIN 10 Upgrade
| 2485201 | 2019-11-18 | 2019-09-29 |  | 2019-07-16 |  |  | Yes | Y-2191 | TM | 2485201 | 2485 HH - LAKE CITY | 419 SW State Road 247 STE 109 | Lake City | FL | 32025 | (386)758-3490 | Ashley Walker | Peggy Lewis | 10.24.192 |  | 39 | 34 | 31 | 7 | 4 | 1 | 0 | 9 | 11 | 32.35% | 17 | 15 | WIN 10 Upgrade
| 2477201 | 2019-11-18 | 2019-10-27 |  | 2019-08-13 | 2 | 1 | Yes | Y-2191 | EC | 2477201 | 2477 HH - MARIANNA 2 | 2491 Commercial Park Dr. | Marianna | FL | 32448 | (850)526-1932 | Amy Askew | Joan Helmes | 10.24.197 |  | 76 | 59 | 56 | 17 | 24 | 3 | 4 | 19 | 28 | 47.46% | 39 | 56 | WIN 10 Upgrade
| 2445201 | 2019-11-18 | 2019-09-29 |  | 2019-07-16 | 1 | 1 | Yes | Y-6957 | TM | 2445201 | 2445 HH - ORLANDO SOUTH | 4776 New Broad St. STE 110 | Orlando | FL | 32814 | (407)894-5703 | Paula Wunderlich |  | 10.24.201 |  | 101 | 68 | 87 | 10 | 12 | 4 | 1 | 16 | 22 | 32.35% | 30 | 35 | WIN 10 Upgrade
| 2474201 | 2019-11-18 | 2019-10-27 |  | 2019-08-13 | 1 | 1 | Yes | Y-2191 | EC | 2474201 | 2474 HH - MOBILE | 824 Western America Drive | Mobile | AL | 36609 | (251)316-0917 | Cathy Lomax | Diana Grimes Cole | 10.24.112 |  | 45 | 42 | 32 | 12 | 10 | 1 | 1 | 11 | 11 | 26.19% | 24 | 22 | WIN 10 Upgrade
| 2447201 | 2019-12-02 | 2019-09-29 |  | 2019-07-16 | 1 | 2 | Yes | Y-6957 | TM | 2447201 | 2447 HH - APOPKA (moved to Orlando North) | 527 Wekiva Commons Circle | Apopka | FL | 32712 | (407)865-7671 | Rita Margolis |  | 10.24.177 |  | 17 | 13 | 14 | 3 | 3 | 0 | 0 | 2 | 5 | 38.46% | 5 | 8 | WIN 10 Upgrade
| 2446201 | 2019-12-02 | 2019-09-29 |  | 2019-07-16 |  |  | Yes | Y-6957 | TM | 2446201 | 2446 HH - KISSIMMEE | 3296 North Greenwald Way | Kissimmee | FL | 34741 | (407)935-1235 | Rita Margolis |  | 10.24.190 |  | 21 | 19 | 19 | 0 | 2 | 2 | 0 | 4 | 8 | 42.11% | 6 | 10 | WIN 10 Upgrade
| 2455201 | 2019-12-02 | 2019-09-29 |  | 2019-07-16 | 1 | 2 | Yes | Y-6957 | TM | 2455201 | 2455 HH - BRADENTON EAST | 101 Riverfront Blvd STE 400 | Bradenton | FL | 34205 | (941)749-2990 | Margaret Tsai | Lisa Kennedy | 10.160.177 |  | 51 | 37 | 43 | 8 | 8 | 0 | 3 | 9 | 10 | 27.03% | 17 | 21 | WIN 10 Upgrade
| 2454201 | 2019-12-02 | 2019-09-29 |  | 2019-07-16 |  |  | Yes | Y-6957 | TM | 2454201 | 2454 HH - SARASOTA | 2601 Cattlemen Road STE 102 | Sarasota | FL | 34232 | (941)363-4590 | Sherry Coval | Margine Rivera | 10.234.77 |  | 48 | 38 | 46 | 2 | 9 | 0 | 0 | 6 | 10 | 26.32% | 8 | 19 | WIN 10 Upgrade
| 2441201 | 2019-12-02 | 2019-09-29 |  | 2019-07-16 | 1 | 1 | Yes | Y-6957 | TM | 2441201 | 2441 HH - LAKELAND | 3671 Innovation Drive | Lakeland | FL | 33812 | (863)648-9118 | Jessica Young | Lynne Ross | 10.24.191 |  | 45 | 39 | 39 | 6 | 7 | 0 | 0 | 11 | 10 | 25.64% | 17 | 17 | WIN 10 Upgrade
| 2442201 | 2019-12-16 | 2019-09-29 |  | 2019-07-16 | 1 | 1 | Yes | Y-6957 | TM | 2442201 | 2442 HH - VIERA | 8247 Devereux Drive STE 103 | Melbourne | FL | 32940 | (321)255-9995 | Jo-Ann Harper | Taquashia Morgan | 10.24.198 |  | 53 | 38 | 49 | 3 | 2 | 1 | 2 | 7 | 10 | 26.32% | 11 | 14 | WIN 10 Upgrade
| 2444201 | 2019-12-16 | 2019-09-29 |  | 2019-07-16 | 1 | 1 | Yes | Y-6957 | TM | 2444201 | 2444 HH - PALM BAY | 2080 W Eau Gallie Blvd STE B | Melbourne | FL | 32935 | (321)725-4799 | Jo-Ann Harper | Donna Carter | 10.24.199 |  | 44 | 31 | 38 | 5 | 1 | 1 | 4 | 6 | 10 | 32.26% | 12 | 15 | WIN 10 Upgrade
| 2452201 | 2019-12-16 | 2019-06-23 |  | 2019-04-09 | 2 | 2 | Yes | Y-6957 | TM | 2452201 | 2452 HH - TAMPA DALE MABRY | 4511 North Himes Ave STE 240 | Tampa | FL | 33614 | (813)961-8446 | Brenda Gerst | Darlene Johnson | 10.160.129 |  | 61 | 49 | 39 | 21 | 9 | 1 | 0 | 15 | 10 | 20.41% | 37 | 19 | WIN 10 Upgrade
| 6957097 | 2019-12-16 | [5 empty] | Yes | Y-6957 | TM | 6957097 | A110 Southeast Central Intake | 4511 North Himes Ave, STE 240 | Tampa | FL | 33614 | (800) 282-3010 | Sabrina Bolta |  |  | 2452 | 17 | 16 | 17 |  |  |  | 3 |  | 9 | 56.25% |  | 12 | WIN 10 Upgrade
| 2532201 | 2019-12-16 | 2019-07-28 |  | 2019-05-14 | 1 | 2 | Yes | Y-6959 | AL | 2532201 | 2532 HH - ANNISTON | 1328 Greenbrier Dear Road | Anniston | AL | 36207 | (256)835-7101 | Donna Honaker | Tami Crumley | 10.24.87 |  | 31 | 25 | 28 | 3 | 1 | 0 | 1 | 3 | 8 | 32% | 6 | 10 | WIN 10 Upgrade
| 2535201 | 2019-12-16 | 2019-07-28 |  | 2019-05-14 |  |  | Yes | Y-6959 | AL | 2535201 | 2535 HH - RAINBOW CITY | 3225 Rainbow Drive STE 256 | Rainbow City | AL | 35906 | (256)442-1138 | Caroline Milwee | Angela Barron | 10.24.120 |  | 41 | 36 | 38 | 3 | 7 | 0 | 1 | 9 | 13 | 36.11% | 12 | 21 | WIN 10 Upgrade
| 2540201 | 2019-12-16 | 2019-07-28 |  | 2019-05-14 | 1 | 2 | Yes | Y-6959 | AL | 2540201 | 2540 HH - MUSCLE SHOALS | 716 State Street | Muscle Shoals | AL | 35661 | (256)389-2855 | Terri Kennamore | Shanna Gardner | 10.24.114 |  | 29 | 29 | 27 | 2 | 4 | 0 | 1 | 3 | 8 | 27.59% | 5 | 13 | WIN 10 Upgrade
| 2538201 | 2019-12-16 | 2019-07-28 |  | 2019-05-14 |  |  | Yes | Y-6959 | AL | 2538201 | 2538 HH - RUSSELLVILLE | 12200 Highway 43 Bypass | Russellville | AL | 35653 | (256)332-3375 | Mollie Henson | Kelly Caldwell | 10.24.121 |  | 39 | 34 | 36 | 3 | 5 | 0 | 0 | 6 | 12 | 35.29% | 9 | 17 | WIN 10 Upgrade
| 2543201 | 2019-12-16 | 2019-07-28 |  | 2019-05-14 | 1 | 2 | Yes | Y-6959 | AL | 2543201 | 2543 HH - JASPER | 1458 Jones Dairy Road STE 100 | Jasper | AL | 35501 | (205)221-5234 | Deanna Barrett | Janis Rutland | 10.24.109 |  | 32 | 28 | 30 | 2 | 3 | 0 | 0 | 5 | 10 | 35.71% | 7 | 13 | WIN 10 Upgrade
| 2542201 | 2019-12-16 | 2019-07-28 |  | 2019-05-14 |  |  | Yes | Y-6959 | AL | 2542201 | 2542 HH - CULLMAN | 1015 1st Ave SW STE A | Cullman | AL | 35055 | (256)739-2992 | Narissa Alexander | Tammy Green | 10.24.94 |  | 31 | 27 | 29 | 1 | 2 | 1 | 0 | 8 | 7 | 25.93% | 10 | 9 | WIN 10 Upgrade
| 2541201 | 2019-12-16 | 2019-07-28 |  | 2019-05-14 | 2 | 1 | Yes | Y-6959 | AL | 2541201 | 2541 HH - HUNTSVILLE | 7067 Old Madison Pike NW STE 105 | Huntsville | AL | 35806 | (256)881-3266 | Paula Pressnell | Jeremy Cox | 10.24.108 |  | 57 | 51 | 49 | 4 | 11 | 4 | 3 | 15 | 12 | 23.53% | 23 | 26 | WIN 10 Upgrade
| 2470201 | 2019-12-16 | 2019-10-27 |  | 2019-08-13 | 1 | 2 | Yes | Y-2191 | AL | 2470201 | 2470 HH - DAPHNE | 9037 Independence Avenue STE B | Daphne | AL | 36526 | (251)621-0882 | Genny Holley | Clana Douglas | 10.24.95 |  | 52 | 43 | 45 | 7 | 4 | 0 | 7 | 11 | 15 | 34.88% | 18 | 26 | WIN 10 Upgrade
| 7019201 | 2019-12-16 | 2019-10-27 |  | 2019-08-13 |  |  | Yes | Y-2191 | AL | 7019201 | 7019 HH - FOLEY | 1628 N McKenzie St STE 101 | Foley | AL | 36535 | 251 943 3002 | Traci Vickrey | Jacqueline Rhodes | 10.24.102 |  | 27 | 27 | 24 | 2 | 2 | 1 | 6 | 5 | 9 | 33.33% | 8 | 17 | WIN 10 Upgrade
| 2503201 | 2019-12-16 | 2019-07-28 |  | 2019-05-14 | 2 | 2 | Yes |  | MS | 2503201 | 2503 HH - JACKSON MS | 106 Riverview Drive | Flowood | MS | 39232 | (601)362-7801 | Marcia Todd | Stacey Roth | 10.31.10 |  | 42 | 37 | 35 | 6 | 5 | 1 | 0 | 13 | 15 | 40.54% | 20 | 20 | WIN 10 Upgrade
| 3775097 | 2019-12-16 | [5 empty] | Yes |  | MS | 3775097 | 3775 HH - Mississippi Central Intake | 106 Riverview Drive | Flowood | MS | 39232 | (601)362-7801 |  |  | 10.31.10 | 2503 | 4 | 0 | 4 | [6 empty] | #DIV/0! |  | 0 | WIN 10 Upgrade
| 2539201 | 2020-01-06 | 2019-07-28 |  | 2019-05-14 | 1 | 2 | Yes | Y-6959 | AL | 2539201 | 2539 HH - ATHENS AL | 905A South Clinton Street | Athens | AL | 35611 | (256)232-9180 | Jerri Williams | Brooke Richardson | 10.24.88 |  | 38 | 39 | 35 | 3 | 2 | 0 | 1 | 9 | 7 | 17.95% | 12 | 10 | WIN 10 Upgrade
| 2537201 | 2020-01-06 | 2019-07-28 |  | 2019-05-14 |  |  | No | Y-6959 | AL | 2537201 | 2537 HH - MOULTON | 20 Almon Drive STE C | Moulton | AL | 35650 | (256)974-2741 | Pamela Parris Garrison | Belinda Kimbrough | 10.24.113 |  | 32 | 23 | 29 | 3 | 3 | 0 | 0 | 5 | 8 | 34.78% | 8 | 11 | WIN 10 Upgrade
| 2524201 | 2020-01-06 | 2019-08-25 |  | 2019-06-11 | 1 | 2 | Yes | Y-6959 | AL | 2524201 | 2524 HH - SYLACAUGA | 1025 West Fort Williams St. | Sylacauga | AL | 35150 | (256)249-4363 | Tracy Haney |  | 10.24.123 |  | 13 | 13 | 11 | 2 | 1 | 0 | 0 | 5 | 7 | 53.85% | 7 | 8 | WIN 10 Upgrade
| 2527201 | 2020-01-06 | 2019-08-25 |  | 2019-06-11 |  |  | Yes | Y-6959 | AL | 2527201 | 2527 HH - PELL CITY | 614 Martin Street North | Pell City | AL | 35125 | (205)338-8440 | Robin Jones (previously Nye) |  | 10.24.116 |  | 13 | 13 | 11 | 2 | 2 | 0 | 0 | 5 | 8 | 61.54% | 7 | 10 | WIN 10 Upgrade
| 2510201 | 2020-01-06 | 2019-08-25 |  | 2019-06-11 | 1 | 1 | Yes | Y-6959 | AL | 2510201 | 2510 HH - ENTERPRISE | 1239 Rucker Blvd. | Enterprise | AL | 36330 | (334)347-0234 | Shasta Moore | Teresa Boop | 10.24.98 |  | 33 | 28 | 28 | 4 | 1 | 1 | 4 | 11 | 17 | 60.71% | 16 | 22 | WIN 10 Upgrade
| 2509201 | 2020-01-06 | 2019-08-25 |  | 2019-06-11 | 1 | 2 | Yes | Y-6959 | AL | 2509201 | 2509 HH - ANDALUSIA | 1309 Antioch Road | Andalusia | AL | 36420 | (334)222-2172 | Sharon Kinsaul |  | 10.24.86 |  | 25 | 21 | 21 | 4 | 3 | 0 | 0 | 8 | 8 | 38.1% | 12 | 11 | WIN 10 Upgrade
| 2511201 | 2020-01-06 | 2019-08-25 |  | 2019-06-11 |  |  | Yes | Y-6959 | AL | 2511201 | 2511 HH - GENEVA | 1204 W. Magnolia Ave | Geneva | AL | 36340 | (334)684-3919 | JulieCarol Stephens |  | 10.24.104 |  | 23 | 19 | 20 | 3 | 3 | 0 | 0 | 6 | 7 | 36.84% | 9 | 10 | WIN 10 Upgrade
| 2531201 | 2020-01-06 | 2019-08-25 |  | 2019-06-11 | 2 | 2 | Yes | Y-6959 | AL | 2531201 | 2531 HH - MONTGOMERY | 11123 Chantilly Parkway, Unit L | Pike Road | AL | 36064 | (334)270-1151 | Sherry Ingram | Lydia Gallardo | 10.24.118 |  | 48 | 29 | 38 | 10 | 9 | 0 | 7 | 10 | 21 | 72.41% | 20 | 37 | WIN 10 Upgrade
| 2526201 | 2020-01-06 | 2019-08-25 |  | 2019-06-11 |  |  | Yes | Y-6959 | AL | 2526201 | 2526 HH - CLANTON | 118 6th Street South | Clanton | AL | 35045 | (205)755-9926 | Karen Varner | Patricia Taddicken | 10.24.93 |  | 19 | 14 | 16 | 3 | 3 | 0 | 1 | 3 | 6 | 42.86% | 6 | 10 | WIN 10 Upgrade
| 2529201 | 2020-01-06 | 2019-08-25 |  | 2019-06-11 | 1 | 1 | Yes | Y-6959 | AL | 2529201 | 2529 HH - SELMA | 200 Central Park Place | Selma | AL | 36701 | (334)872-6637 | Wanda Winfield | Sharron Stewart | 10.24.122 |  | 20 | 18 | 16 | 4 | 4 | 0 | 0 | 4 | 12 | 66.67% | 8 | 16 | WIN 10 Upgrade
| 3807201 | 2020-01-06 | 2019-08-25 |  | 2019-06-11 | 1 | 1 | Yes | Y-6959 | AL | 3807201 | 3807 HH - THOMASVILLE | 16820 US Highway 19 N | Thomasville | GA | 31757 | (229)233-6255 | Melissa Richardson |  | 10.160.170 |  | 49 | 44 | 46 | 3 | 6 | 0 | 1 | 12 | 8 | 18.18% | 15 | 15 | WIN 10 Upgrade
| 2513201 | 2020-01-06 | 2019-08-25 |  | 2019-06-11 | 1 | 1 | Yes | Y-6959 | AL | 2513201 | 2513 HH - BAINBRIDGE GA | 430 East Shotwell Street | Bainbridge | GA | 39819 | (229)246-1941 | Anna Trawick |  | 10.24.224 |  | 62 | 56 | 51 | 9 | 4 | 2 | 4 | 9 | 11 | 19.64% | 20 | 19 | WIN 10 Upgrade
| 2525201 | 2020-01-06 | 2019-08-25 |  | 2019-06-11 | 2 | 1 | Yes | Y-6959 | AL | 2525201 | 2525 HH - BIRMINGHAM | 2100 Riverchase Center Bldg 400 STE 450 | Hoover | AL | 35244 | (205)739-7800 | Amy Terrell | Misti Parsons | 10.24.89 |  | 71 | 39 | 43 | 25 | 5 | 3 | 5 | 9 | 7 | 17.95% | 37 | 17 | WIN 10 Upgrade
| 2459201 | 2020-01-13 | 2020-01-26 | 2019-10-15 | 2019-11-12 | 1 | 1 | Yes | Y-6959 | AL | 2459201 | 2459 HH - PHENIX CITY | River Chase Office Park, 5009 River Chase Dr., Bldg 100 STE D | Phenix City | AL | 36867 | (334)297-6900 | Brittany Waddell |  | 10.24.117 |  | 29 | 23 | 21 | 8 | 3 | 0 | 1 | 2 | 3 | 13.04% | 10 | 7 | WIN 10 Upgrade
| 2514201 | 2020-01-13 | 2019-08-25 |  | 2019-06-11 | 1 | 1 | Yes |  | AL | 2514201 | 2514 HH - TRUSSVILLE (now known as HOMEWOOD) | 2100 Southbridge Parkway STE 480 | Birmingham | AL | 35209 | (205)836-0777 | Catherine Kelley | Rosalyn Johnson | 10.24.90 |  | 55 | 41 | 47 | 8 | 6 | 0 | 0 | 5 | 12 | 29.27% | 13 | 18 | WIN 10 Upgrade
| 2383201 | 2020-01-13 | 2019-06-23 |  | 2019-04-09 | 1 | 1 | Yes |  |  | 2383201 | 2383 HH - CEDAR RAPIDS | 1305 Boyson Loop Suite B | Hiawatha | IA | 52233 | (319)393-4742 | Theresa Pint |  | 10.24.246 |  | 41 | 36 | 30 | 11 | 5 | 0 | 0 | 5 | 6 | 16.67% | 16 | 11 | WIN 10 Upgrade
| 2644201 | 2020-01-13 | 2019-07-28 |  | 2019-05-14 | 1 | 1 | Yes |  |  | 2644201 | 2644 HH - MESA AZ | 1910 South Stapely Drive STE 107 | Mesa | AZ | 85204 | (480)558-7504 | Suellen Meadows |  | 10.24.134 |  | 66 | 49 | 55 | 11 | 10 | 0 | 2 | 8 | 11 | 22.45% | 19 | 23 | WIN 10 Upgrade
| 2640201 | 2020-01-13 | 2019-07-28 |  | 2019-05-14 | 1 | 1 | Yes |  |  | 2640201 | 2640 HH - PHOENIX - CENTRAL | 14050 North 83rd Avenue STE 150 | Peoria | AZ | 85381 | (623)979-7471 | Erin Hetrick |  | 10.24.135 |  | 41 | 28 | 34 | 7 | 7 | 0 | 1 | 8 | 7 | 25% | 15 | 15 | WIN 10 Upgrade
| 7023201 | 2020-01-13 | 2019-07-28 |  | 2019-05-14 | 2 | 1 | Yes |  |  | 7023201 | 7023 HH - RENO (fka 2603) | 5424 Louie Lane STE B | Reno | NV | 89511 | (775)858-1900 | Debra Doran |  | 10.25.114 |  | 111 | 79 | 110 | 0 | 13 | 1 | 1 | 14 | 15 | 18.99% | 15 | 29 | WIN 10 Upgrade
| 7025201 | 2020-01-13 | 2019-07-28 |  | 2019-05-14 | 1 | 1 | Yes |  |  | 7025201 | 7025 HH - FERNLEY | 415 Highway 95A South STE F-604 | Fernley | NV | 89408 | (775)575-1286 | Heather Ludeman |  | 10.24.150 |  | 30 | 28 | 29 | 1 | 2 | 0 | 0 | 4 | 11 | 39.29% | 5 | 13 | WIN 10 Upgrade
| 2380201 | 2020-01-13 | 2019-09-29 |  | 2019-07-16 | 1 | 1 | Yes |  |  | 2380201 | 2380 HH - ROCK ISLAND | 1600 Fourth Ave STE 201 | Rock Island | IL | 61201 | (309)786-3700 | Corena Ferguson |  | 10.24.248 |  | 27 | 27 | 16 | 10 | 3 | 1 | 2 | 6 | 7 | 25.93% | 17 | 12 | WIN 10 Upgrade
| 7024201 | 2020-01-13 | 2019-07-28 |  | 2019-05-14 | 2 | 1 | Yes |  |  | 7024201 | 7024 HH - CARSON CITY | 725 Basque Way STE 3 | Carson City | NV | 89706 | (775)884-0100 | Tobias DeLuca |  | 10.24.151 |  | 89 | 59 | 87 | 2 | 2 | 0 | 0 | 9 | 14 | 23.73% | 11 | 16 | WIN 10 Upgrade
| 2643201 | 2020-01-13 | 2019-07-28 |  | 2019-05-14 | 1 | 2 | Yes |  |  | 2643201 | 2643 HH - SCOTTSDALE | 16620 North 40th Street STE D4 | Phoenix | AZ | 85032 | (602)992-0709 | Darlene Kaminski |  | 10.24.136 |  | 23 | 25 | 18 | 4 | 2 | 1 | 3 | 4 | 10 | 40% | 9 | 15 | WIN 10 Upgrade
| 2650201 | 2020-01-13 | 2019-07-28 |  | 2019-05-14 |  |  | Yes |  |  | 2650201 | 2650 HH - TUCSON | 5255 E. Williams Circle STE 6400 | Tucson | AZ | 85711 | (520)731-1333 | Tammy Susdorf | Julie Gaines | 10.24.138 |  | 48 |  | 41 | 7 | 6 | 0 | 0 | 11 | 17 | #DIV/0! | 18 | 23 | WIN 10 Upgrade
| 2528201 | 2020-01-20 | 2019-08-25 |  | 2019-06-11 | 1 | 1 | Yes | Y-6959 | AL | 2528201 | 2528 HH - PRATTVILLE | 1988 Fairview Avenue | Prattville | AL | 36066 | (334)361-9806 | Lynne Williams Vickery | Doris Gidley | 10.24.119 |  | 47 |  | 41 | 6 | 4 | 0 | 1 | 17 | 14 | #DIV/0! | 23 | 19 | WIN 10 Upgrade
| 2512201 | 2020-01-20 | 2019-08-25 |  | 2019-06-11 | 1 | 1 | Yes | Y-6959 | AL | 2512201 | 2512 HH - DOTHAN 2 | 2740 Headland Avenue | Dothan | AL | 36303 | (334)944-2290 | Jennifer Wade |  | 10.24.97 |  | 46 |  | 37 | 8 | 10 | 1 | 0 | 5 | 10 | #DIV/0! | 14 | 20 | WIN 10 Upgrade
| 2397201 | 2020-01-20 | 2019-09-29 |  | 2019-07-16 | 1 | 1 | Yes |  |  | 2397201 | 2397 HH - INDIANAPOLIS NORTH | 8606 Allisonville Rd STE 350 | Indianapolis | IN | 46250 | (317)915-1440 | Bobbie Furr |  | 10.24.253 |  | 34 |  | 22 | 12 | 10 | 0 | 2 | 8 | 10 | #DIV/0! | 20 | 22 | WIN 10 Upgrade
| 2433201 | 2020-01-20 | 2019-09-29 |  | 2019-07-16 | 1 | 1 | Yes |  |  | 2433201 | 2433 HH - INDIANAPOLIS SOUTH | 701 East County Line Road STE 205 | Greenwood | IN | 46143 | (317)881-3483 | Susan Ruble |  | 10.24.252 |  | 32 |  | 25 | 6 | 4 | 1 | 0 | 11 | 5 | #DIV/0! | 18 | 9 | WIN 10 Upgrade
| 7010201 | 2020-01-20 | 2019-09-29 |  | 2019-07-16 | 1 | 1 | Yes |  |  | 7010201 | 7010 HH - MUNCIE | 400 N High Street STE 202 | Muncie | IN | 47305 | (765)282-0351 | Tamera Nibarger | Kelli McCord | 10.25.2 |  | 32 |  | 26 | 5 | 2 | 1 | 3 | 4 | 7 | #DIV/0! | 10 | 12 | WIN 10 Upgrade
| 2387201 | 2020-01-20 | 2019-11-17 |  | 2019-09-03 | 1 | 1 | Yes |  | MN | 2387201 | 2387 HH - ST PAUL - ROSEVILLE | 1970 Oakcrest Avenue STE 107 | Roseville | MN | 55113 | (651)636-6330 | Vikki Lindstrom |  | 10.25.53 |  | 65 |  | 53 | 11 | 5 | 1 | 6 | 6 | 4 | #DIV/0! | 18 | 15 | WIN 10 Upgrade
| 2392201 | 2020-01-20 | 2019-11-17 |  | 2019-09-03 | 1 | 1 | Yes |  | MN | 2392201 | 2392 HH - ST PAUL - MAPLE GROVE | 7101 Northland Circle STE 5101 | Brooklyn Park | MN | 55428 | (763)416-0289 | Aimee Hager |  | 10.25.52 |  | 31 |  | 25 | 5 | 3 | 1 | 5 | 5 | 4 | #DIV/0! | 11 | 12 | WIN 10 Upgrade
| 2389201 | 2020-01-20 | 2019-11-17 |  | 2019-09-03 | 1 | 1 | Yes |  | MN | 2389201 | 2389 HH - DULUTH | 925 East Superior St STE 104 | Duluth | MN | 55802 | (218)723-8999 | Rachael Rhodes |  | 10.25.51 |  | 35 |  | 29 | 5 | 5 | 1 | 3 | 4 | 5 | #DIV/0! | 10 | 13 | WIN 10 Upgrade
| 2391201 | 2020-01-20 | 2019-11-17 |  | 2019-09-03 | 1 | 1 | Yes |  | MN | 2391201 | 2391 HH - ST PAUL - BLOOMINGTON | 7900 W 78th Street STE 180 | Edina | MN | 55439 | (952)854-9628 | Jenny Jackson |  | 10.25.49 |  | 86 |  | 77 | 8 | 8 | 1 | 6 | 5 | 8 | #DIV/0! | 14 | 22 | WIN 10 Upgrade
| 2632201 | 2020-01-20 | 2019-11-17 |  | 2019-09-03 | 1 | 1 | Yes |  | CO | 2632201 | 2632 HH - GRAND JUNCTION | 2764 Compass Drive STE 108B | Grand Junction | CO | 81506 | (970)257-1275 | Suzanne Mapes |  | 10.21.144 |  | 19 |  | 16 | 3 | 3 | 0 | 0 | 4 | 5 | #DIV/0! | 7 | 8 | WIN 10 Upgrade
| 2634201 | 2020-01-20 | 2019-11-17 |  | 2019-09-03 | 1 | 1 | Yes |  | CO | 2634201 | 2634 HH - COLORADO SPRINGS | 5755 Mark Dabling Blvd. STE 325 | Colorado Springs | CO | 80919 | (719)531-9585 | Kristala Carlisle |  | 10.24.4 |  | 43 |  | 35 | 7 | 4 | 1 | 1 | 6 | 6 | #DIV/0! | 14 | 11 | WIN 10 Upgrade
| 2638201 | 2020-01-20 | 2019-11-17 |  | 2019-09-03 | 1 | 1 | Yes |  | CO | 2638201 | 2638 HH - PUEBLO | 1315 Fortino Boulevard Suite A | Pueblo | CO | 81008 | (719)583-0832 | Alexa Dawn Medrano |  | 10.42.10 |  | 35 |  | 30 | 4 | 3 | 1 | 5 | 5 | 5 | #DIV/0! | 10 | 13 | WIN 10 Upgrade
| 7028201 | 2020-01-20 | 2019-12-15 | 2019-09-03 | 2019-10-01 | 1 | 1 | Yes |  | SP | 7028201 | 7028 HH - NORTH SPOKANE | 8502 North Nevada STE 2 | Spokane | WA | 99208 | (509)464-4970 | Tawnya Calkins | Sherri Barber | 10.25.113 |  | 57 |  | 54 | 1 | 2 | 2 | 1 | 9 | 11 | #DIV/0! | 12 | 14 | WIN 10 Upgrade
| 5015201 | 2020-01-20 | 2019-12-15 | 2019-09-03 | 2019-10-01 | 1 | 1 | Yes |  | SP | 5015201 | 5015 HH - LIBERTY LAKE | 22820 E. Appleway Ave | Liberty Lake | WA | 99019 | (509)473-4900 | Karen White | Kirby Clark | 10.160.202 |  | 93 |  | 75 | 17 | 5 | 1 | 7 | 22 | 24 | #DIV/0! | 40 | 36 | WIN 10 Upgrade
| 7029201 | 2020-01-20 | 2019-12-15 | 2019-09-03 | 2019-10-01 | 1 | 2 | Yes |  | SP | 7029201 | 7029 HH - COEUR D'ALENE ID | 1230 N NORTHWOOD CENTER CT, Suite C | Coeur D Alene | ID | 83814 | (208)667-5470 | Tena Flores |  | 10.25.205 |  | 32 |  | 26 | 6 | 3 | 0 | 0 | 5 | 7 | #DIV/0! | 11 | 10 | WIN 10 Upgrade
| 5016201 | 2020-01-20 | 2019-12-15 | 2019-09-03 | 2019-10-01 |  |  | Yes |  | SP | 5016201 | 5016 HH - PULLMAN | 1610 NE Eastgate Blvd STE 650 | Pullman | WA | 99163 | (509)334-6016 | Anne Cline | Susan Fleischman | 10.25.208 |  | 29 |  | 28 | 1 | 1 | 0 | 2 | 11 | 6 | #DIV/0! | 12 | 9 | WIN 10 Upgrade
| 2653201 | 2020-01-27 | 2019-12-15 | 2019-09-03 | 2019-10-01 | 1 | 1 |  |  | SP | 2653201 | 2653 HH - KENT | 20829 72nd Ave South STE 125 | Kent | WA | 98032 | (253)395-5133 | Denise Pascal | Karen Long-Kierig | 10.25.206 |  | 64 |  | 52 | 10 | 9 | 2 | 3 | 11 | 17 | #DIV/0! | 23 | 29 | WIN 10 Upgrade
| 2686201 | 2020-01-27 | 2019-12-15 | 2019-09-03 | 2019-10-01 | 1 | 1 |  |  | SP | 2686201 | 2686 HH - BREMERTON | 4660 Kitsap Way STE 101 | Bremerton | WA | 98312 | (360)373-6966 | Dodie Purnell | Dina Johnson | 10.25.203 |  | 52 |  | 50 | 2 | 1 | 0 | 0 | 14 | 15 | #DIV/0! | 16 | 16 | WIN 10 Upgrade
| 2550201 | 2020-01-27 | 2019-09-29 |  | 2019-07-16 | 1 | 1 |  |  | SC | 2550201 | 2550 HH - FARMINGTON | 4783 Flat River Road STE 100A | Farmington | MO | 63640 | (573)431-6685 | Crystal Rippee | Michelle Hamm | 10.21.77 |  | 50 |  | 41 | 9 | 5 | 0 | 2 | 3 | 9 | #DIV/0! | 12 | 16 | WIN 10 Upgrade
| 2586201 | 2020-01-27 | 2019-06-23 |  | 2019-04-09 | 2 | 1 |  |  | SC | 2586201 | 2586 HH - BEAUMONT - HARDEN | 2615 Calder Street STE 202 | Beaumont | TX | 77702 | (409)895-0009 | Polly Matlock |  | 10.21.87 |  | 180 |  | 167 | 13 | 10 | 0 | 0 | 9 | 10 | #DIV/0! | 22 | 20 | WIN 10 Upgrade
| 2547201 | 2020-01-27 | 2019-09-29 |  | 2019-07-16 | 1 | 1 |  |  | SC | 2547201 | 2547 HH - WEST PLAINS | 707 Kentucky Avenue | West Plains | MO | 65775 | (417)257-2080 | Laura Thorn |  |  |  | 29 |  | 22 | 7 | 4 | 0 | 0 | 17 | 6 | #DIV/0! | 25 | 10 | WIN 10 Upgrade
| 2552201 | 2020-01-27 | 2019-11-17 |  | 2019-09-03 | 1 | 1 |  |  | SC | 2552201 | 2552 HH - KANSAS CITY EAST | 20101 E. Jackson Drive STE D | Independence | MO | 64057 | (816)524-5087 | Wendy Kullberg | Melody Shanks | 10.25.56 |  | 51 |  | 41 | 10 | 11 | 0 | 3 | 11 | 11 | #DIV/0! | 21 | 25 | WIN 10 Upgrade
| 7015201 | 2020-01-27 | 2019-11-17 |  | 2019-09-03 | 1 | 1 |  |  | SC | 7015201 | 7015 HH - KANSAS CITY NORTH | 7280 NW 87th Terrace, Building C STE 206 | Kansas City | MO | 64153 | (816)587-0441 | Cindy Fahlgren | Melissa Goslee | 10.25.55 |  | 35 |  | 26 | 9 | 3 | 0 | 3 | 4 | 5 | #DIV/0! | 13 | 11 | WIN 10 Upgrade
| 2551201 | 2020-01-27 | 2019-11-17 |  | 2019-09-03 | 1 | 1 |  |  | SC | 2551201 | 2551 HH - KANSAS CITY SOUTH | 11880 College Blvd. STE 4A | Overland Park | KS | 66210 | (913)906-0522 | Cindy Fahlgren |  | 10.25.16 |  | 36 |  | 29 | 6 | 1 | 1 | 3 | 8 | 9 | #DIV/0! | 15 | 13 | WIN 10 Upgrade
| 2574201 | 2020-01-27 | 2020-01-05 | 2019-09-24 | 2019-10-22 | 1 | 2 |  |  | SC | 2574201 | 2574 HH - DALLAS (104T) | 4849 GREENVILLE AVE | DALLAS | TX | 75206 | (214)378-9913 | Robert Cleveland |  | 10.21.34 |  | 79 |  | 74 | 5 | 3 | 0 | 0 | 3 | 7 | #DIV/0! | 8 | 10 | WIN 10 Upgrade
| 2576201 | 2020-01-27 | 2020-01-05 | 2019-09-24 | 2019-10-22 |  |  |  |  | SC | 2576201 | 2576 HH - Fort Worth (105T) | 6421 Camp Bowie Blvd, Ste 203 | Fort Worth | TX | 76116 | (817)731-6124 | Robert Cleveland |  | 10.21.42 |  | 23 |  | 17 | 5 | 4 | 1 | 0 | 3 | 6 | #DIV/0! | 9 | 10 | WIN 10 Upgrade
| 2544201 | 2020-02-03 | 2019-09-29 |  | 2019-07-16 | 1 | 1 |  |  | SC | 2544201 | 2544 HH - COLUMBIA MO | 2404 Forum Boulevard STE 101 | Columbia | MO | 65203 | (573)256-4705 | Jamie Seifert |  | 10.21.24 |  | 26 |  | 18 | 8 | 5 | 0 | 3 | 5 | 5 | #DIV/0! | 13 | 13 | WIN 10 Upgrade
| 7014201 | 2020-02-03 | 2019-09-29 |  | 2019-07-16 | 1 | 1 |  |  | SC | 7014201 | 7014 HH - ST LOUIS-WEST | 12125 Woodcrest Executive Dr. STE 340 | Creve Coeur | MO | 63141 | (314)434-3030 | Robyn Walton |  | 10.25.58 |  | 24 |  | 18 | 4 | 6 | 2 | 5 | 6 | 5 | #DIV/0! | 12 | 16 | WIN 10 Upgrade
| 2578201 | 2020-02-03 | 2020-01-05 | 2019-09-24 | 2019-10-22 | 1 | 1 |  |  | SC | 2578201 | 2578 HH - LONGVIEW | 434 East Loop 281 STE 100 | Longview | TX | 75605 | (903)938-6776 | Delphine Andrews |  | 10.21.69 |  | 80 |  | 76 | 3 | 0 | 1 | 0 | 5 | 7 | #DIV/0! | 9 | 7 | WIN 10 Upgrade
| 2591201 | 2020-02-03 | 2020-01-05 | 2019-09-24 | 2019-10-22 | 1 | 1 |  |  | SC | 2591201 | 2591 HH - SAN ANTONIO - HARDEN | 4335 West Piedras Drive STE 100 | San Antonio | TX | 78228 | (210)614-0473 | Yolanda Gonzalez | Jo Ann Silvas | 10.21.96 |  | 127 |  | 127 | 0 | 8 | 0 | 1 | 18 | 14 | #DIV/0! | 18 | 23 | WIN 10 Upgrade
| 2592201 | 2020-02-03 | 2020-01-05 | 2019-09-24 | 2019-10-22 | 1 | 2 |  |  | SC | 2592201 | 2592 HH - SCHULENBURG | 85 North Kessler Avenue | Schulenburg | TX | 78956 | (979)743-2633 | Renee Hinze |  | 10.21.101 |  | 59 |  | 56 | 3 | 4 | 0 | 0 | 5 | 4 | #DIV/0! | 8 | 8 | WIN 10 Upgrade
| 2593201 | 2020-02-03 | 2020-01-05 | 2019-09-24 | 2019-10-22 |  |  |  |  | SC | 2593201 | 2593 HH - VICTORIA | 1501 East Mockingbird Lane STE 301 | Victoria | TX | 77904 | (361)576-2179 | Deana Lewis |  | 10.21.119 |  | 62 |  | 57 | 5 | 1 | 0 | 1 | 9 | 11 | #DIV/0! | 14 | 13 | WIN 10 Upgrade
| 2573201 | 2020-02-03 | 2020-01-05 | 2019-09-24 | 2019-10-22 | 1 | 1 |  |  | SC | 2573201 | 2573 HH - CORSICANA | 800 North Main Street STE Q | Corsicana | TX | 75110 | (903)874-9147 | Shirley Irvin |  | 10.21.102 |  | 102 |  | 99 | 3 | 2 | 0 | 2 | 5 | 7 | #DIV/0! | 8 | 11 | WIN 10 Upgrade
| 2575201 | 2020-02-03 | 2020-01-05 | 2019-09-24 | 2019-10-22 | 1 | 2 |  |  | SC | 2575201 | 2575 HH - EASTLAND | 405 East Commerce Street | Eastland | TX | 76448 | (254)629-1268 | Gina Young Harper |  | 10.21.38 |  | 49 |  | 46 | 2 | 4 | 1 | 0 | 6 | 15 | #DIV/0! | 9 | 19 | WIN 10 Upgrade
| 3539201 | 2020-02-03 | 2020-01-05 | 2019-09-24 | 2019-10-22 |  |  |  |  | SC | 3539201 | 3539 HH - BROWNWOOD | 118 South Park Drive STE D | Brownwood | TX | 76801 | (325)643-5525 | Rosa Cervantez |  | 10.21.135 |  | 33 |  | 33 | 0 | 3 | 0 | 0 | 9 | 9 | #DIV/0! | 9 | 12 | WIN 10 Upgrade
| 2580201 | 2020-02-03 | 2020-01-05 | 2019-09-24 | 2019-10-22 | 1 | 1 |  |  | SC | 2580201 | 2580 HH - SAN ANGELO - HARDEN | 1518 West Beauregard Avenue | San Angelo | TX | 76901 | (325)949-1108 | Audra Clark |  | 10.21.91 |  | 91 |  | 85 | 6 | 2 | 0 | 1 | 8 | 8 | #DIV/0! | 14 | 11 | WIN 10 Upgrade
| 2579201 | 2020-02-03 |  |  |  | 2 | 1 |  |  |  | 2579201 | 2579 HH - LUBBOCK (added 10/11/2019) | 3223 South Loop 289 Suite 325 | Lubbock | TX | 79423 | (806) 788-5566 | Grant Innes |  |  |  | 38 |  | 23 | 14 | 5 | 1 | 2 | 5 | 5 | #DIV/0! | 20 | 12 | WIN 10 Upgrade
| 2587201 | 2020-02-03 | 2020-01-05 | 2019-09-24 | 2019-10-22 | 1 | 1 |  |  | SC | 2587201 | 2587 HH - BELLAIRE | 6700 West Loop South STE 200 | Bellaire | TX | 77401 | (713)781-6691 | Lindsey Bradley |  | 10.21.52 |  | 204 |  | 199 | 5 | 2 | 0 | 1 | 29 | 3 | #DIV/0! | 34 | 6 | WIN 10 Upgrade
| 2585201 | 2020-02-03 | 2020-01-05 | 2019-09-24 | 2019-10-22 | 2 | 1 |  |  | SC | 2585201 | 2585 HH - HUMBLE | 9810 FM 1960 Bypass Road West STE 215 | Humble | TX | 77338 | (281)446-5366 | Toni BrooksGrowe |  | 10.21.54 |  | 142 |  | 130 | 12 | 4 | 0 | 9 | 17 | 28 | #DIV/0! | 29 | 41 | WIN 10 Upgrade
| 2565201 | 2020-02-03 | 2019-08-25 |  | 2019-06-11 | 1 | 1 |  |  | SC | 2565201 | 2565 HH - FT SMITH | 2120 South Waldron STE Bldg C | Fort Smith | AR | 72903 | (479)452-0424 | Ginger Carr |  | 10.24.125 |  | 75 |  | 65 | 5 | 1 | 5 | 8 | 19 | 16 | #DIV/0! | 29 | 25 | WIN 10 Upgrade
| 2396201 | 2020-02-03 | 2019-09-29 |  | 2019-07-16 | 1 | 1 |  |  |  | 2396201 | 2396 HH - CHICAGO | 2211 York Road STE 215 | Oak Brook | IL | 60523 | (708)442-6420 | Tracy Jakusz |  | 10.21.22 |  | 73 |  | 62 | 11 | 4 | 0 | 0 | 9 | 8 | #DIV/0! | 20 | 12 | WIN 10 Upgrade
| 2382201 | 2020-02-10 | 2019-11-17 |  | 2019-09-03 | 1 | 1 |  |  |  | 2382201 | 2382 HH - RACINE | 6233 Bankers Road STE 1 | Racine | WI | 53403 | (262)636-9036 | Kristin Parey |  | 10.25.215 |  | 40 |  | 34 | 4 | 5 | 2 | 2 | 2 | 6 | #DIV/0! | 8 | 13 | WIN 10 Upgrade
| 7017201 | 2020-02-10 | 2019-11-17 |  | 2019-09-03 | 1 | 2 |  |  |  | 7017201 | 7017 HH - WEST ALLIS (MILWAUKEE) | 10150 W National Avenue, Ste 300 | West Allis | WI | 53227 | (414)327-4553 | Traci Bitters |  | 10.25.216 |  | 30 |  | 22 | 8 | 4 | 0 | 5 | 4 | 5 | #DIV/0! | 12 | 14 | WIN 10 Upgrade
| 7018201 | 2020-02-10 | 2019-11-17 |  | 2019-09-03 | [5 empty] | 7018201 | 7018 HH - GERMANTOWN | W177 N9886 Rivercrest Drive STE 112 | Germantown | WI | 53022 | (262)251-3807 | Traci Bitters |  | 10.25.214 |  | 31 |  | 29 | 2 | 4 | 0 | 2 | 1 | 2 | #DIV/0! | 3 | 8 | WIN 10 Upgrade
| 2388201 | 2020-02-10 | 2019-11-17 |  | 2019-09-03 | 1 | 1 |  |  |  | 2388201 | 2388 HH - OMAHA | 9140 West Dodge Road STE 401 | Omaha | NE | 68114 | (402)343-9433 | Shari Ellison | Michelle Yanes | 10.25.103 |  | 63 |  | 53 | 9 | 12 | 1 | 0 | 5 | 8 | #DIV/0! | 15 | 20 | WIN 10 Upgrade
| 7016201 | 2020-02-10 | 2019-11-17 |  | 2019-09-03 | 1 | 1 |  |  |  | 7016201 | 7016 HH - LINCOLN | 8055 O Street STE 111 | Lincoln | NE | 68510 | (402)434-8081 | Carrie Budd |  | 10.25.102 |  | 26 |  | 22 | 4 | 4 | 0 | 0 | 5 | 5 | #DIV/0! | 9 | 9 | WIN 10 Upgrade
| 2618201 | 2020-02-10 | 2019-12-15 | 2019-09-03 | 2019-10-01 | 1 | 1 |  |  |  | 2618201 | 2618 HH - STOCKTON | 10100 Trinity Parkway STE 425 | Stockton | CA | 95219 | (209)474-7881 | Tulsi Parikh |  | 10.24.154 |  | 62 |  | 45 | 12 | 6 | 5 | 0 | 15 | 16 | #DIV/0! | 32 | 22 | WIN 10 Upgrade
| 2599201 | 2020-02-10 | 2019-12-15 | 2019-09-03 | 2019-10-01 | 1 | 1 |  |  |  | 2599201 | 2599 HH - MODESTO CA | 4216 Kiernan Avenue STE 100 | Modesto | CA | 95356 | (209)545-7803 | Shelley Phillips | Michelle Green | 10.24.145 |  | 47 |  | 44 | 3 | 3 | 0 | 0 | 9 | 14 | #DIV/0! | 12 | 17 | WIN 10 Upgrade
| 7022201 | 2020-02-10 | 2019-12-15 | 2019-09-03 | 2019-10-01 | 1 | 1 |  |  |  | 7022201 | 7022 HH - SAN DIEGO | 2525 Camino Del Rio South STE 220 | San Diego | CA | 92108 | (619)299-9900 | Michael Barnard | Karla Laird | 10.25.128 |  | 52 |  | 42 | 10 | 8 | 0 | 0 | 6 | 12 | #DIV/0! | 16 | 20 | WIN 10 Upgrade
| 2620201 | 2020-02-10 | 2019-12-15 | 2019-09-03 | 2019-10-01 | 1 | 1 |  |  |  | 2620201 | 2620 HH - SAN LUIS OBISPO HHA | 3220 S. Higuera St. STE 101 | San Luis Obispo | CA | 93401 | (805)544-4402 | Desarae Dolan |  | 10.24.149 |  | 38 |  | 28 | 9 | 0 | 1 | 2 | 5 | 11 | #DIV/0! | 15 | 13 | WIN 10 Upgrade
| 2631201 | 2020-02-10 | 2020-01-05 | 2019-09-24 | 2019-10-22 | 1 | 2 |  |  |  | 2631201 | 2631 HH - ALBUQUERQUE | 4401 Masthead Street NE STE 105 | Albuquerque | NM | 87109 | (505)345-3754 | Mayra Santiago |  | 10.25.107 |  | 49 |  | 38 | 11 | 6 | 0 | 2 | 9 | 8 | #DIV/0! | 20 | 16 | WIN 10 Upgrade
| 2629201 | 2020-02-10 | 2020-01-05 | 2019-09-24 | 2019-10-22 | [5 empty] | 2629201 | 2629 HH - LAS CRUCES | 505 South Main STE 132B | Las Cruces | NM | 88001 | (575)528-5620 | Mayra Santiago |  | 10.25.109 |  | 18 |  | 15 | 3 | 3 | 0 | 0 | 3 | 4 | #DIV/0! | 6 | 7 | WIN 10 Upgrade
| 5025201 | 2020-02-10 | 2019-10-27 |  | 2019-08-13 | 1 | 1 |  |  | WS | 5025201 | 5025 HH - VICEROY | 720 Park Centre Drive Suite 350-A | Kernersville | NC | 27284 | (336)497-3870 | Susan Wilson |  | 10.25.97 | 5024 | 50 |  | 47 | 3 | 1 | 0 | 0 | 11 | 5 | #DIV/0! | 14 | 6 | WIN 10 Upgrade
| 2546201 | 2020-02-17 | 2019-09-29 |  | 2019-07-16 | 1 | 1 |  |  | SC | 2546201 | 2546 HH - ROLLA | 1206 Homelife Plaza | Rolla | MO | 65401 | (573)341-3456 | Linda Baehr |  | 10.21.221 |  | 42 |  | 37 | 5 | 3 | 0 | 8 | 9 | 11 | #DIV/0! | 14 | 22 | WIN 10 Upgrade
| 5022201 | 2020-02-17 | 2019-10-27 |  | 2019-08-13 | 1 | 1 |  | Y-1143 | WS | 5022201 | 5022 HH - GREENSBORO | 3150 N Elm Street STE 102 | Greensboro | NC | 27408 | (336)288-1181 | Janice Wilkinson |  | 10.25.78 |  | 126 |  | 102 | 19 |  | 5 |  | 14 |  | #DIV/0! | 38 | 0 | WIN 10 Upgrade
| 3875201 | 2020-02-17 | 2019-10-27 |  | 2019-08-13 | 1 | 1 |  | Y-1143 | CH | 3875201 | 3875 HH - DELCO NC | 27385 Andrew Jackson Highway East STE C | Delco | NC | 28436 | (910)655-4946 | Herbert Erne |  | 10.160.194 |  | 22 |  | 20 | 2 |  | 0 |  | 5 |  | #DIV/0! | 7 | 0 | WIN 10 Upgrade
| 5037201 | 2020-02-17 | 2019-10-27 |  | 2019-08-13 | 1 | 1 |  | Y-1143 | WS | 5037201 | 5037 HH - ROCKY MOUNT | 4013 Capital Drive | Rocky Mount | NC | 27804 | (252)443-7083 | Tony Gesell | Joann Montgomery | 10.25.91 |  | 85 |  | 79 | 6 |  | 0 |  | 16 |  | #DIV/0! | 22 | 0 | WIN 10 Upgrade
| 5035201 | 2020-02-17 | 2019-10-27 |  | 2019-08-13 | 1 | 1 |  | Y-1143 | WS | 5035201 | 5035 HH - PINK HILL | 206 S. Turner Street | Pink Hill | NC | 28572 | (252)568-6022 | Nan Kennedy |  | 10.81.10 |  | 24 |  | 23 | 1 |  | 0 |  | 5 |  | #DIV/0! | 6 | 0 | WIN 10 Upgrade
| 5067201 | 2020-02-17 | 2020-01-26 | 2019-10-15 | 2019-11-12 | 2 | 1 |  | Y-1143 | VB | 5067201 | 5067 HH - ANNAPOLIS | 180 Admiral Cochrane Drive STE 310 | Annapolis | MD | 21401 | (410)224-2988 | Nikkisha Mills | Tonya Malloy | 10.25.38 |  | 62 |  | 46 | 15 |  | 1 |  | 2 |  | #DIV/0! | 18 | 0 | WIN 10 Upgrade
| 5069201 | 2020-02-17 | 2020-01-26 | 2019-10-15 | 2019-11-12 | 1 | 2 |  | Y-1143 | VB | 5069201 | 5069 HH - COLUMBIA MD | 9250 Rumsey Road STE 200 | Columbia | MD | 21045 | (410)997-5257 | Robbin Lewis | Carolyn Faidley | 10.25.106 |  | 40 |  | 32 | 6 |  | 2 |  | 8 |  | #DIV/0! | 16 | 0 | WIN 10 Upgrade
| 5068201 | 2020-02-17 | 2020-01-26 | 2019-10-15 | 2019-11-12 |  |  |  | Y-1143 | VB | 5068201 | 5068 HH - TOWSON MD | 8600 LaSalle Road STE 315 | Towson | MD | 21286 | (410)337-3663 | Leslie Gee | Kayla Christopher | 10.25.38 |  | 43 |  | 38 | 5 |  | 0 |  | 5 |  | #DIV/0! | 10 | 0 | WIN 10 Upgrade
| 7034201 | 2020-02-17 | 2020-01-26 | 2019-10-15 | 2019-11-12 | 1 | 2 |  | Y-1143 | VB | 7034201 | 7034 HH - ROANOKE (fka 5073) | 1302 Plantation Road NE | Roanoke | VA | 24012 | (540)362-7578 | Consuela Lemasters | Lauren Hurley | 10.25.156 |  | 73 |  | 66 | 6 |  | 1 |  | 9 |  | #DIV/0! | 16 | 0 | WIN 10 Upgrade
| 7036201 | 2020-02-17 | 2019-06-23 |  | 2019-04-09 |  |  |  | Y-1143 | VB | 7036201 | 7036 HH - LYNCHBURG (fka 5075) | 1928 Thomson Drive | Lynchburg | VA | 24501 | (434)846-5219 | Rachel Osborne | Nicole Carter-Dominguez | 10.25.197 |  | 35 |  | 25 | 10 |  | 0 |  | 2 |  | #DIV/0! | 12 | 0 | WIN 10 Upgrade
| 5064201 | 2020-02-17 | 2019-10-27 |  | 2019-08-13 | 1 | 1 |  | Y-6964 | CH | 5064201 | 5064 HH - BOONE | 579 Greenway Road STE 103 | Boone | NC | 28607 | (828)266-1166 | Ginger Jordan |  | 10.25.70 |  | 44 |  | 39 | 5 |  | 0 |  | 4 |  | #DIV/0! | 9 | 0 | WIN 10 Upgrade
| 2545201 | 2020-02-17 | 2019-10-27 |  | 2019-08-13 | 1 | 1 |  |  |  | 2545201 | 2545 HH - OSAGE BEACH (added 1/21/20) | 980 Executive Drive, Suite D | Osage Beach | MO | 65065 | (573) 302-7898 | Kristin Brent |  |  |  | 22 |  | 0 | 0 |  | 0 |  | 0 |  | #DIV/0! | 0 | 0 | WIN 10 Upgrade
| 5076201 | 2020-02-17 | 2020-01-26 | 2019-10-15 | 2019-11-12 | 1 | 1 |  | Y-1143 | VB | 5076201 | 5076 HH - CHRISTIANSBURG | 15 West Main Street STE 200 | Christiansburg | VA | 24073 | (540)382-9311 | Carolyn Morgan | Rebecca Wilson | 10.25.194 |  | 53 |  | 42 | 11 |  | 0 |  | 7 |  | #DIV/0! | 18 | 0 | WIN 10 Upgrade
| 5886201 | 2020-02-17 | 2020-01-26 | 2019-10-15 | 2019-11-12 | 1 | 1 |  | Y-6964 | VB | 5886201 | 5886 HH - PRINCETON WV | 150 Courthouse Road STE 301A | Princeton | WV | 24740 | (304)325-3378 | Melissa Burks |  | 10.25.219 |  | 42 |  | 37 | 5 |  | 0 |  | 6 |  | #DIV/0! | 11 | 0 | WIN 10 Upgrade
| 5066201 | 2020-02-17 | 2019-10-27 |  | 2019-08-13 | 1 | 1 |  | Y-6964 | CH | 5066201 | 5066 HH - WAKE FOREST - WILKES JV | 126 Executive Drive Suite 104 | Wilkesboro | NC | 28697 | (336)818-3170 | Sandra Faw | Christina Johnson | 10.25.96 |  | 44 |  | 41 | 3 |  |  |  | 14 |  | #DIV/0! | 17 | 0 | WIN 10 Upgrade
| 5065201 | 2020-02-17 |  |  |  | 1 | 1 |  | Y-6964 | CH | 5065201 | 5065 HH - NORTH WILKESBORO | 126 Executive Drive STE 120 | Wilkesboro | NC | 28697 | (336)667-3389 | Sandra Faw | Christina Johnson | 10.25.96 | 5066 | 3 |  | 0 | 3 |  | 0 |  | 11 |  | #DIV/0! | 14 | 0 | WIN 10 Upgrade
| 5059201 | 2020-02-17 | 2019-10-27 |  | 2019-08-13 | 1 | 1 |  | Y-6964 | CH | 5059201 | 5059 HH - GASTONIA | 934 Cox Road | Gastonia | NC | 28054 | (704)824-7099 | Kristy Linder |  | 10.25.76 |  | 74 |  | 63 | 9 |  | 2 |  | 12 |  | #DIV/0! | 23 | 0 | WIN 10 Upgrade
| 5048201 | 2020-02-17 | 2019-10-27 |  | 2019-08-13 | 1 | 1 |  | Y-6964 | WS | 5048201 | 5048 HH - KANNAPOLIS | 201 Security Street | Kannapolis | NC | 28083 | (704)933-1001 | Elizabeth Record | Patricia Coppin | 10.25.82 |  | 115 |  | 110 | 4 |  | 1 |  | 9 |  | #DIV/0! | 14 | 0 | WIN 10 Upgrade
| 6528201 | 2020-02-24 | 2019-11-17 |  | 2019-09-03 | 1 | 1 |  | Y-6964 | CH | 6528201 | 6528 HH - AUGUSTA GA | 1225 West Wheeler Parkway Bldg C | Augusta | GA | 30909 | (706)651-1211 | Jennifer Sergent | Heather Hagan | 10.160.147 |  | 67 |  | 56 | 9 |  | 2 |  | 9 |  | #DIV/0! | 20 | 0 | WIN 10 Upgrade
| 5070201 | 2020-02-24 | 2020-01-26 | 2019-10-15 | 2019-11-12 | 1 | 1 |  | Y-1143 | VB | 5070201 | 5070 HH - SILVER SPRINGS MD | 12501 Prosperity Drive STE 225 | Silver Spring | MD | 20904 | (301)622-2320 | Deborah Watt | Francesca Manguiri | 10.25.37 |  | 69 |  | 61 | 7 |  | 1 |  | 8 |  | #DIV/0! | 16 | 0 | WIN 10 Upgrade
| 6532201 | 2020-02-24 | 2019-11-17 |  | 2019-09-03 | 2 | 1 |  | Y-6964 | CH | 6532201 | 6532 HH - SPARTANBURG | 905 East Main Street STE 1 | Spartanburg | SC | 29302 | (864)582-5936 | April Reininger |  | 10.25.164 |  | 66 |  | 56 | 10 |  | 0 |  | 20 |  | #DIV/0! | 30 | 0 | WIN 10 Upgrade
| 6529201 | 2020-02-24 | 2019-11-17 |  | 2019-09-03 | 1 | 1 |  | Y-6964 | CH | 6529201 | 6529 HH - GREENVILLE SC | 15 Brendan Way STE 250 | Greenville | SC | 29615 | (864)297-5711 | Cynthia Fry |  | 10.25.159 |  | 70 |  | 58 | 11 |  | 1 |  | 7 |  | #DIV/0! | 19 | 0 | WIN 10 Upgrade
| 6533201 | 2020-02-24 | 2019-11-17 |  | 2019-09-03 | 1 | 1 |  | Y-6964 | CH | 6533201 | 6533 HH - GAFFNEY | 206 Chesnee Highway STE G & H | Gaffney | SC | 29341 | (864)488-0898 | Teresa Randolph |  | 10.160.251 |  | 29 |  | 25 | 4 |  | 0 |  | 5 |  | #DIV/0! | 9 | 0 | WIN 10 Upgrade
| 7030201 | 2020-02-24 | 2019-11-17 |  | 2019-09-03 | 1 | 1 |  | Y-6964 | CH | 7030201 | 7030 HH - SAVANNAH | 2280 East Victory Drive STE B | Savannah | GA | 31404 | (912)355-3409 | Stephanie Fagnan |  | 10.25.202 |  | 45 |  | 40 | 5 |  | 0 |  | 5 |  | #DIV/0! | 10 | 0 | WIN 10 Upgrade
| 6527201 | 2020-02-24 | 2019-11-17 |  | 2019-09-03 | 1 | 1 |  | Y-6964 | CH | 6527201 | 6527 HH - STATESBORO | 1525 Fair Road STE 106 | Statesboro | GA | 30458 | (912)486-1900 | Amanda Anderson |  | 10.24.238 |  | 66 |  | 56 | 10 |  | 0 |  | 7 |  | #DIV/0! | 17 | 0 | WIN 10 Upgrade
| 5040201 | 2020-02-24 | 2019-11-17 |  | 2019-09-03 | 2 | 1 |  | Y-6964 | CH | 5040201 | 5040 HH - MYRTLE BEACH | 1240 21st Avenue North STE 200 | Myrtle Beach | SC | 29577 | (843)448-7060 | Amanda Miller |  | 10.25.161 |  | 114 |  | 96 | 15 |  | 3 |  | 13 |  | #DIV/0! | 31 | 0 | WIN 10 Upgrade
| 3207201 | 2020-02-24 | 2019-11-17 |  | 2019-09-03 | 1 | 1 |  | Y-6964 | CH | 3207201 | 3207 HH - AIKEN | 80 Physician Drive | Aiken | SC | 29801 | (803)220-3818 | Erin Hamilton |  | 10.160.145 |  | 63 |  | 54 | 9 |  | 0 |  | 11 |  | #DIV/0! | 20 | 0 | WIN 10 Upgrade
| 5039201 | 2020-02-24 | 2019-11-17 |  | 2019-09-03 | 1 | 1 |  | Y-6964 | CH | 5039201 | 5039 HH - COLUMBIA SC | 2000 Center Point Road STE 2300 | Columbia | SC | 29210 | (803)731-2365 | Natasha Brown | Samantha Dittmar | 10.25.157 |  | 118 |  | 108 | 8 |  | 2 |  | 13 |  | #DIV/0! | 23 | 0 | WIN 10 Upgrade
| 3183201 | 2020-02-24 | 2019-11-17 |  | 2019-09-03 | 1 | 1 |  | Y-6964 | CH | 3183201 | 3183 HH - NEWBERRY | 2521 Evans Street | Newberry | SC | 29108 | (803)276-0273 | Harriet Guy |  | 10.24.6 |  | 26 |  | 23 | 3 |  | 0 |  | 3 |  | #DIV/0! | 6 | 0 | WIN 10 Upgrade
| 5044201 | 2020-03-02 | 2019-11-17 |  | 2019-09-03 | 1 | 1 |  | Y-6964 | CH | 5044201 | 5044 HH - NORTH CHARLOTTE (Now Charlotte HUMANA) | 9009-C Perimeter Woods Drive | Charlotte | NC | 28216 | (704)598-2716 |  |  | 10.25.72 |  | 23 |  | 3 | 20 |  | 0 |  | 12 |  | #DIV/0! | 32 | 0 | WIN 10 Upgrade
| 5062201 | 2020-03-02 | 2019-11-17 |  | 2019-09-03 | 1 | 1 |  | Y-6964 | CH | 5062201 | 5062 HH - MONROE, NC | 1995 Wellness Boulevard STE 220 | Monroe | NC | 28110 | (704)283-0535 | Kimberly Cheek | Michelle Plyler | 10.25.85 |  | 81 |  | 71 | 10 |  | 0 |  | 12 |  | #DIV/0! | 22 | 0 | WIN 10 Upgrade
| 5045201 | 2020-03-02 | 2019-11-17 |  | 2019-09-03 | 2 | 2 |  | Y-6964 | CH | 5045201 | 5045 HH - SOUTH CHARLOTTE | 11111 Carmel Commons Blvd. STE 350 | Charlotte | NC | 28226 | (704)543-1167 | Kimberly Selph | DeeAnn Niehaus | 10.25.73 | 7032 | 182 |  | 177 | 5 |  | 0 |  | 14 |  | #DIV/0! | 19 | 0 | WIN 10 Upgrade
| 7032201 | 2020-03-02 | 2019-11-17 |  | 2019-09-03 |  |  |  | Y-6964 | CH | 7032201 | 7032 HH - CHARLOTTE UNIVERSITY (Now North Charlotte) | 11111 Carmel Commons Blvd. Suite 350-B | Charlotte | NC | 28226 | (704)594-9029 |  |  | 10.25.73 | 5045 | 5 |  | 3 | 2 |  | 0 |  | 0 |  | #DIV/0! | 2 | 0 | WIN 10 Upgrade
| 3182201 | 2020-03-02 | 2019-11-17 |  | 2019-09-03 | 1 | 1 |  | Y-6964 | CH | 3182201 | 3182 HH - ANDERSON DHEC | 1704 E. Greenville Street STE 2D | Anderson | SC | 29621 | (864)332-8200 | Melissa Price | Alysse Ford | 10.25.154 |  | 64 |  | 54 | 10 |  | 0 |  | 10 |  | #DIV/0! | 20 | 0 | WIN 10 Upgrade
| 6531201 | 2020-03-02 | 2019-11-17 |  | 2019-09-03 | 1 | 1 |  | Y-6964 | CH | 6531201 | 6531 HH - SENECA | 977 Tiger Boulevard | Clemson | SC | 29631 | (864)885-1085 | Sherri Smith |  | 10.25.163 |  | 69 |  | 53 | 15 |  | 1 |  | 1 |  | #DIV/0! | 17 | 0 | WIN 10 Upgrade
| 6534201 | 2020-03-02 | 2019-11-17 |  | 2019-09-03 | 1 | 1 |  | Y-6964 | CH | 6534201 | 6534 HH - UNION 2 | 1261 South Duncan Bypass | Union | SC | 29379 | (864)429-4821 | Elizabeth Moore |  | 10.25.166 |  | 28 |  | 24 | 4 |  | 0 |  | 6 |  | #DIV/0! | 10 | 0 | WIN 10 Upgrade
| 5041201 | 2020-03-02 | 2019-11-17 |  | 2019-09-03 | 1 | 1 |  | Y-6964 | CH | 5041201 | 5041 HH - ROCK HILL 2 | 250 Piedmont Blvd | Rock Hill | SC | 29732 | (803)329-3184 | Kay Hull |  | 10.25.162 |  | 135 |  | 118 | 15 |  | 2 |  | 22 |  | #DIV/0! | 39 | 0 | WIN 10 Upgrade
| 3186201 | 2020-03-02 | 2019-11-17 |  | 2019-09-03 | 2 | 1 |  | Y-6964 | CH | 3186201 | 3186 HH - CHESTERFIELD | 515 Market Street | Cheraw | SC | 29520 | (843)320-8859 | Janice Privette |  | 10.24.9 |  | 26 |  | 19 | 7 |  | 0 |  | 13 |  | #DIV/0! | 20 | 0 | WIN 10 Upgrade
| 3185201 | 2020-03-02 | 2019-11-17 |  | 2019-09-03 | 1 | 1 |  | Y-6964 | CH | 3185201 | 3185 HH - FLORENCE | 702 Pamplico Highway STE B | Florence | SC | 29505 | (843)317-9686 | Edith Odom | Rebecca Snipes | 10.24.8 |  | 61 |  | 53 | 8 |  | 0 |  | 10 |  | #DIV/0! | 18 | 0 | WIN 10 Upgrade
| 3187201 | 2020-03-02 | 2019-11-17 |  | 2019-09-03 | 1 | 1 |  | Y-6964 | CH | 3187201 | 3187 HH - DILLON | 1311 N Main Street STE 102 | Marion | SC | 29571 | (843)774-2284 | Lauren Jensen |  | 10.24.10 |  | 29 |  | 25 | 4 |  | 0 |  | 2 |  | #DIV/0! | 6 | 0 | WIN 10 Upgrade
| 3209201 | 2020-03-02 | 2019-11-17 |  | 2019-09-03 | 1 | 2 |  | Y-6964 | CH | 3209201 | 3209 HH - ORANGEBURG | 1739 Village Park Drive | Orangeburg | SC | 29118 | (803)937-2490 | Lauren McNeill |  | 10.160.173 |  | 5 |  | 2 | 3 |  | 0 |  | 3 |  | #DIV/0! | 6 | 0 | WIN 10 Upgrade
| 3188201 | 2020-03-02 | 2019-11-17 |  | 2019-09-03 |  |  |  | Y-6964 | CH | 3188201 | 3188 HH - MANNING | 122 N. Brooks Street | Manning | SC | 29102 | (803)435-2559 | April Gladden |  | 10.24.11 |  | 41 |  | 36 | 5 |  | 0 |  | 5 |  | #DIV/0! | 10 | 0 | WIN 10 Upgrade
| 7031201 | 2020-03-09 | 2019-11-17 |  | 2019-09-03 | 1 | 1 |  | Y-6964 | CH | 7031201 | 7031 HH - CHARLESTON SC | 4975 Lacross Road STE 354 | North Charleston | SC | 29406 | (843)744-1191 | Alison Holloway | Karen Kasper | 10.25.156 |  | 93 |  | 81 | 12 |  | 0 |  | 16 |  | #DIV/0! | 28 | 0 | WIN 10 Upgrade
| 3190201 | 2020-03-09 | 2019-11-17 |  | 2019-09-03 | 1 | 1 |  | Y-6964 | CH | 3190201 | 3190 HH - WALTERBORO | 415-E Robertson Boulevard | Walterboro | SC | 29488 | (843)542-9540 | Angela Bunton | Rhonda Evans | 10.24.12 |  | 50 |  | 43 | 7 |  | 0 |  | 6 |  | #DIV/0! | 13 | 0 | WIN 10 Upgrade
| 5884201 | 2020-03-09 | 2020-01-26 | 2019-10-15 | 2019-11-12 | 1 | 2 |  | Y-6964 | VB | 5884201 | 5884 HH - BECKLEY WV | 112 Mellon Street | Beckley | WV | 25801 | (304)255-5263 | Ashley Hall | Robert Furey | 10.25.218 |  | 54 |  | 50 | 4 |  | 0 |  | 9 |  | #DIV/0! | 13 | 0 | WIN 10 Upgrade
| 5887201 | 2020-03-09 | 2019-06-23 |  | 2019-04-09 |  |  |  | Y-6964 | VB | 5887201 | 5887 HH - SUMMERSVILLE WV | 800 Broad Street | Summersville | WV | 26651 | (304)872-7380 | Sarah Nichols |  | 10.25.223 |  | 39 |  | 33 | 6 |  | 0 |  | 7 |  | #DIV/0! | 13 | 0 | WIN 10 Upgrade
| 6524201 | 2020-03-09 | 2020-01-26 | 2019-10-15 | 2019-11-12 | 1 | 1 |  | Y-6964 | VB | 6524201 | 6524 HH - DANVILLE - NEW | 105 Citation Dr STE B | Danville | KY | 40422 | (859)236-2193 | Nancy Yeager | Caitlin Norris | 10.25.24 |  | 48 |  | 39 | 9 |  | 0 |  | 11 |  | #DIV/0! | 20 | 0 | WIN 10 Upgrade
| 5079201 | 2020-03-09 | 2019-12-15 | 2019-09-03 | 2019-10-01 | 1 | 2 |  | Y-6964 | VB | 5079201 | 5079 HH - NASHVILLE | 624 Grassmere Park Drive STE 8 | Nashville | TN | 37211 | (615)360-9000 | Valerie Flint |  | 10.25.174 |  | 39 |  | 26 | 12 |  | 1 |  | 12 |  | #DIV/0! | 25 | 0 | WIN 10 Upgrade
| 5078201 | 2020-03-09 | 2019-12-15 | 2019-09-03 | 2019-10-01 |  |  |  | Y-6964 | VB | 5078201 | 5078 HH - HOPKINSVILLE HHA | 540 Noel Avenue | Hopkinsville | KY | 42240 | (270)885-7887 | Gilbert Rosales | Mary Bouldin | 10.25.23 |  | 33 |  | 29 | 4 |  | 0 |  | 6 |  | #DIV/0! | 10 | 0 | WIN 10 Upgrade
| 6227201 | 2020-03-09 | 2020-01-26 | 2019-10-15 | 2019-11-12 | 2 | 1 |  | Y-6964 | VB | 6227201 | 6227 HH - LOUISVILLE | 710 Executive Park | Louisville | KY | 40207 | (502)895-4213 | Dana Fallot | Tamara Nash | 10.25.25 |  | 94 |  | 91 | 2 |  | 1 |  | 15 |  | #DIV/0! | 18 | 0 | WIN 10 Upgrade
| 6522201 | 2020-03-09 | 2020-01-26 | 2019-10-15 | 2019-11-12 | 1 | 1 |  | Y-6964 | VB | 6522201 | 6522 HH - SHELBYVILLE | 140 Stonecrest Road STE 203 | Shelbyville | KY | 40065 | (502)647-1025 | Linda Binion |  | 10.25.26 |  | 60 |  | 52 | 8 |  | 0 |  | 6 |  | #DIV/0! | 14 | 0 | WIN 10 Upgrade
| 5885201 | 2020-03-09 | 2020-01-26 | 2019-10-15 | 2019-11-12 | 1 | 2 |  | Y-6964 | VB | 5885201 | 5885 HH - HUNTINGTON WV | 5187 US Route 60 STE 28 | Huntington | WV | 25705 | (304)733-9430 | Jason Gibson | April Blanton | 10.25.221 |  | 57 |  | 53 | 4 |  | 0 |  | 5 |  | #DIV/0! | 9 | 0 | WIN 10 Upgrade
| 5089201 | 2020-03-09 | 2020-01-26 | 2019-10-15 | 2019-11-12 |  |  |  | Y-6964 | VB | 5089201 | 5089 HH - PARKERSBURG WV | 39 12th Street | Parkersburg | WV | 26101 | (304)424-7172 | Jackie Benton | Lora Toncray | 10.25.222 |  | 20 |  | 15 | 4 |  | 1 |  | 2 |  | #DIV/0! | 7 | 0 | WIN 10 Upgrade
| 6248201 | 2020-03-09 | 2020-01-26 | 2019-10-15 | 2019-11-12 | 1 | 1 |  | Y-6964 | VB | 6248201 | 6248 HH - LEXINGTON | 1300 E New Circle Road STE 180 | Lexington | KY | 40505 | (859)252-4206 | Michele Baysore | Vickie Middleton | 10.25.24 |  | 57 |  | 55 | 2 |  | 0 |  | 14 |  | #DIV/0! | 16 | 0 | WIN 10 Upgrade
| 6238201 | 2020-03-09 | 2020-01-26 | 2019-10-15 | 2019-11-12 |  | 1 |  | Y-6964 | VB | 6238201 | 6238 HH - N KENTUCKY | 2114 Chamber Center Drive | Fort Mitchell | KY | 41017 | (859)331-5800 | Julie Brown | Sharon Mason | 10.25.22 |  | 64 |  | 57 | 5 |  | 2 |  | 15 |  | #DIV/0! | 22 | 0 | WIN 10 Upgrade
| 5764201 | 2020-03-09 | 2020-01-26 | 2019-10-15 | 2019-11-12 | 1 | 1 |  | Y-6964 | VB | 5764201 | 5764 HH - CHARLESTON WV | 100 Kanawha Blvd West | Charleston | WV | 25302 | (304)346-9667 | Sharon Chambers |  | 10.25.220 |  | 78 |  | 71 | 6 |  | 1 |  | 9 |  | #DIV/0! | 16 | 0 | WIN 10 Upgrade
| 5883201 | 2020-03-09 | 2019-06-23 |  | 2019-04-09 | 1 | 1 |  | Y-6964 | VB | 5883201 | 5883 HH - CHAPMANVILLE | 46 Friendly Neighbor Drive | Chapmanville | WV | 25508 | (304)855-7104 | Lori Anderson |  | 10.21.21 |  | 34 |  | 25 | 9 |  | 0 |  | 7 |  | #DIV/0! | 16 | 0 | WIN 10 Upgrade
| 6964201 | 2020-03-16 |  |  |  | 2 | 1 |  | Y-6964 | CH | 6964201 | 6964 HH - CHARLOTTE CNTRL INTK-SHRD SVCS | 2221 EDGE LAKE DRIVE | CHARLOTTE | NC | 28217 | (704)559-8121 | Tina Scott |  | 10.25.75 |  | 71 |  | 10 | 58 |  | 3 |  | 0 |  | #DIV/0! | 61 | 0 | WIN 10 Upgrade
| 3714201 | 2020-03-16 | 2020-01-05 | 2019-09-24 | 2019-10-22 | 1 | 2 |  |  | VB | 3714201 | 3714 HH - NORFOLK | 410 N. Center Drive, Bldg. 9, Suite 102 | Norfolk | VA | 23502 | (757)961-0049 |  |  | 10.25.110 |  |  |  | -1 | 1 |  | 0 |  | 11 |  | #DIV/0! | 12 | 0 | WIN 10 Upgrade
| 7033201 | 2020-03-16 | 2020-01-26 | 2019-10-15 | 2019-11-12 |  |  |  | Y-1154 | VB | 7033201 | 7033 HH - RICHMOND | 7113 Three Chopt Road STE 201 | Richmond | VA | 23226 | (804)672-7500 | Onika Samuel | Dollie Hamlin | 10.24.236 |  | 25 |  | 24 | 1 |  | 0 |  | 5 |  | #DIV/0! | 6 | 0 | WIN 10 Upgrade
| 2466201 | 2020-03-16 | 2019-07-28 |  | 2019-05-14 | 2 | 1 |  | Y-6952 | GA | 2466201 | 2466 HH - SANDY SPRINGS | 1303 Hightower Trail STE 105 | Atlanta | GA | 30350 | (770)998-1393 | Tara Etheredge | Nicole Dyke | 10.24.227 |  | 102 |  | 81 | 19 |  | 2 |  | 8 |  | #DIV/0! | 25 | 0 | WIN 10 Upgrade
| 2467201 | 2020-03-16 | 2020-01-26 | 2019-10-15 | 2019-11-12 | 1 | 1 |  | Y-6952 | GA | 2467201 | 2467 HH - CUMMINGS | 2080 Ronald Reagan Blvd STE 500 | Cumming | GA | 30041 | (770)781-1999 | Kasey Brown | Audrey Lindsay | 10.24.225 |  | 53 |  | 40 | 12 |  | 1 |  | 3 |  | #DIV/0! | 16 | 0 | WIN 10 Upgrade
| 2463201 | 2020-03-16 | 2020-01-26 | 2019-10-15 | 2019-11-12 | 1 | 1 |  | Y-6952 | GA | 2463201 | 2463 HH - GRIFFIN | 246 O'Dell Road STE Unit 3 | Griffin | GA | 30224 | (770)233-0023 | Tequillia Flewellen |  | 10.24.228 |  | 58 |  | 50 | 8 |  | 0 |  | 6 |  | #DIV/0! | 14 | 0 | WIN 10 Upgrade
| 2464201 | 2020-03-16 | 2020-01-26 | 2019-10-15 | 2019-11-12 | 1 | 1 |  | Y-6952 | GA | 2464201 | 2464 HH - VILLA RICA GA | 845 South Carroll Road STE C | Villa Rica | GA | 30180 | (678)840-4475 | Dana Noland | Newana Williams | 10.24.241 |  | 41 |  | 35 | 4 |  | 2 |  | 7 |  | #DIV/0! | 13 | 0 | WIN 10 Upgrade
| 2460201 | 2020-03-16 | 2020-01-26 | 2019-10-15 | 2019-11-12 | 1 | 1 |  | Y-6952 | GA | 2460201 | 2460 HH - GWINNETT | 1075 Old Norcross Road STE S | Lawrenceville | GA | 30046 | (678)985-3300 | Sandra Epps | Felicia Thomas | 10.24.230 |  | 127 |  | 126 | 1 |  | 0 |  | 13 |  | #DIV/0! | 14 | 0 | WIN 10 Upgrade
| 2461201 | 2020-03-16 | 2020-01-26 | 2019-10-15 | 2019-11-12 | 2 | 1 |  | Y-6952 | GA | 2461201 | 2461 HH - STOCKBRIDGE | 200 Business Center Drive STE 218 | Stockbridge | GA | 30281 | (678)289-6044 | Pamela Heminger | Irenee Phillips | 10.24.240 |  | 74 |  | 60 | 14 |  | 0 |  | 13 |  | #DIV/0! | 27 | 0 | WIN 10 Upgrade
| 2469201 | 2020-03-16 | 2020-01-26 | 2019-10-15 | 2019-11-12 | 2 | 1 |  | Y-6952 | GA | 2469201 | 2469 HH - MARIETTA | 1395 South Marietta Pkwy. STE 902 | Marietta | GA | 30067 | (470)795-7907 | LaTonya Jones | Jannis Parsons | 10.24.231 |  | 54 |  | 35 | 17 |  | 2 |  | 14 |  | #DIV/0! | 33 | 0 | WIN 10 Upgrade
| 2465201 | 2020-03-16 | 2020-01-26 | 2019-10-15 | 2019-11-12 | 2 | 1 |  | Y-6952 | GA | 2465201 | 2465 HH - PEACHTREE CITY | 277 Hwy 74 North STE 307 | Peachtree City | GA | 30269 | (770)487-1399 | Althea Walker | Michelle Parks | 10.24.234 |  | 76 |  | 57 | 17 |  | 2 |  | 7 |  | #DIV/0! | 26 | 0 | WIN 10 Upgrade
| 6952097 | 2020-03-16 |  |  |  | 1 | 1 |  | Y-6952 | GA | 6952097 | A113 - Atlanta Central Intake | 1303 Hightower Trail, Suite 160 | Sandy Springs | GA | 30350 |  | Terron Taylor |  |  |  | 18 |  | 18 | [6 empty] | #DIV/0! |  | 0 | WIN 10 Upgrade
| 2361201 | 2020-03-16 | 2019-06-23 |  | 2019-04-09 | 1 | 2 |  | Y-6956 | NY | 2361201 | 2361 HH - BANGOR | 175 Exchange Street STE 100 | Bangor | ME | 4401 | (207)990-9000 | Sheldon Brett |  | 10.25.39 |  | 52 |  | 45 | 5 |  | 2 |  | 6 |  | #DIV/0! | 13 | 0 | WIN 10 Upgrade
| 7013201 | 2020-03-16 | 2020-01-26 | 2019-10-15 | 2019-11-12 |  |  |  | Y-6956 | NY | 7013201 | 7013 HH - SANFORD ME | 2 Livewell Drive STE 101 | Kennebunk | ME | 4043 | (207)324-8790 | Christopher Sylvia |  | 10.25.40 |  | 24 |  | 23 | 0 |  | 1 |  | 3 |  | #DIV/0! | 4 | 0 | WIN 10 Upgrade
| 2435201 | 2020-03-16 | 2019-06-23 |  | 2019-04-09 | 1 | 1 |  | Y-6956 | NY | 2435201 | 2435 HH - LANCASTER (PA) | 1860 Charter Lane STE 106 | Lancaster | PA | 17601 | (717)291-5943 | Sandra Acton |  | 10.25.136 |  | 70 |  | 65 | 5 |  | 0 |  | 6 |  | #DIV/0! | 11 | 0 | WIN 10 Upgrade
| 2355201 | 2020-03-23 | 2020-01-26 | 2019-10-15 | 2019-11-12 | 1 | 1 |  | Y-6956 | NY | 2355201 | 2355 HH - SPRINGFIELD BEHAV HEALTH | 2069 Roosevelt Avenue | Springfield | MA | 1104 | (413)733-1132 | Meg Gleason | Nicole Nicholson | 10.25.35 |  | 48 |  | 45 | 3 |  | 0 |  | 8 |  | #DIV/0! | 11 | 0 | WIN 10 Upgrade
| 2363201 | 2020-03-23 | 2020-01-26 | 2019-10-15 | 2019-11-12 | 1 | 1 |  | Y-6956 | NY | 2363201 | 2363 HH - PITTSFIELD | 279 Dalton Ave. STE B | Pittsfield | MA | 1201 | (413)443-3525 | Melissa Radovanovic |  | 10.25.33 |  | 51 |  | 44 | 7 |  | 0 |  | 11 |  | #DIV/0! | 18 | 0 | WIN 10 Upgrade
| 7012201 | 2020-03-23 | 2020-01-26 | 2019-10-15 | 2019-11-12 | 1 | 1 |  | Y-6956 | NY | 7012201 | 7012 HH - SANDWICH (fka 2364) | 88 Route 6A STE 101 | Sandwich | MA | 2563 | (508)888-2932 | Maureen Clancy |  | 10.25.34 |  | 52 |  | 44 | 7 |  | 1 |  | 4 |  | #DIV/0! | 12 | 0 | WIN 10 Upgrade
| 2378201 | 2020-03-23 | 2020-01-26 | 2019-10-15 | 2019-11-12 | 1 | 2 |  | Y-6956 | NY | 2378201 | 2378 HH - OLD SAYBROOK | 210 Main Street STE 1A & 2 | Old Saybrook | CT | 6475 | (860)510-0210 | Lee Bridgewater |  | 10.24.170 |  | 48 |  | 42 | 5 |  | 1 |  | 3 |  | #DIV/0! | 9 | 0 | WIN 10 Upgrade
| 2357201 | 2020-03-23 | 2020-01-26 | 2019-10-15 | 2019-11-12 |  |  |  | Y-6956 | NY | 2357201 | 2375 HH - FARMINGTON CT | 30 Stanford Drive | Farmington | CT | 6032 | (860)674-1302 | Carissa Beaulieu |  | 10.24.168 |  | 43 |  | 33 | 9 |  | 1 |  | 2 |  | #DIV/0! | 12 | 0 | WIN 10 Upgrade
| 2372201 | 2020-03-23 | 2020-01-26 | 2019-10-15 | 2019-11-12 | 1 | 1 |  | Y-6956 | NY | 2372201 | 2372 HH - AUBURN NY | 425 Grant Ave. | Auburn | NY | 13021 | (315)255-1781 | Lisa Minnoe |  | 10.25.116 |  | 41 |  | 33 | 8 |  | 0 |  | 10 |  | #DIV/0! | 18 | 0 | WIN 10 Upgrade
| 2377201 | 2020-03-23 | 2020-01-26 | 2019-10-15 | 2019-11-12 | 1 | 1 |  | Y-6956 | NY | 2377201 | 2377 HH - HAMDEN | 1952 Whitney Avenue, 1st Floor | Hamden | CT | 6517 | (203)287-3174 | Jullie Nuzzolillo |  | 10.24.169 |  | 48 |  | 36 | 12 |  | 0 |  | 6 |  | #DIV/0! | 18 | 0 | WIN 10 Upgrade
| 2376201 | 2020-03-23 | 2020-01-26 | 2019-10-15 | 2019-11-12 | 1 | 1 |  | Y-6956 | NY | 2376201 | 2376 HH - STRATFORD | 99 Hawley Lane STE 1101 | Stratford | CT | 6614 | (203)377-5117 | Louise Giardina |  | 10.24.171 |  | 37 |  | 31 | 5 |  | 1 |  | 8 |  | #DIV/0! | 14 | 0 | WIN 10 Upgrade
| 2434201 | 2020-03-23 | 2020-01-26 | 2019-10-15 | 2019-11-12 | 1 | 1 |  | Y-6956 | NY | 2434201 | 2434 HH - CORNING | 11849 East Corning Road STE 108 | Corning | NY | 14830 | (607)962-0102 | Kevin Devine | Kimberly Calkins | 10.25.117 |  | 62 |  | 52 | 9 |  | 1 |  | 4 |  | #DIV/0! | 14 | 0 | WIN 10 Upgrade
| 2366201 | 2020-03-23 | 2020-01-26 | 2019-10-15 | 2019-11-12 | 1 | 1 |  | Y-6956 | NY | 2366201 | 2366 HH - PORTLAND ME | 51 Baxter Boulevard | Portland | ME | 4101 | (207)772-0954 | Catherine Graham |  | 10.25.41 |  | 36 |  | 29 | 6 |  | 1 |  | 6 |  | #DIV/0! | 13 | 0 | WIN 10 Upgrade
| 2374201 | 2020-03-23 | 2020-01-26 | 2019-10-15 | 2019-11-12 | 1 | 1 |  | Y-6956 | NY | 2374201 | 2374 HH - LIVERPOOL | 200 Elwood Davis Rd | Liverpool | NY | 13088 | (315)461-0209 | Christine Fordyce |  | 10.25.119 |  | 50 |  | 43 | 7 |  | 0 |  | 5 |  | #DIV/0! | 12 | 0 | WIN 10 Upgrade
| 2373201 | 2020-03-23 | 2020-01-26 | 2019-10-15 | 2019-11-12 | 1 | 1 |  | Y-6956 | NY | 2373201 | 2373 HH - OSWEGO | 19 Fourth Avenue | Oswego | NY | 13126 | (315)342-0521 | Tracy Bender |  | 10.25.121 |  | 53 |  | 49 | 3 |  | 1 |  | 11 |  | #DIV/0! | 15 | 0 | WIN 10 Upgrade
| 2379201 | 2020-03-23 | 2020-01-26 | 2019-10-15 | 2019-11-12 | 2 | 2 |  | Y-6956 | NY | 2379201 | 2379 HH - MALTA NY | Clifton Park Center, 320 Ushers Road | Ballston Lake | NY | 12065 | (518)899-1158 | Sue Peterson |  | 10.25.120 |  | 62 |  | 56 | 6 |  | 0 |  | 11 |  | #DIV/0! | 17 | 0 | WIN 10 Upgrade
| 6956097 | 2020-03-23 | [7 empty] | NY | 6956097 | 6956 HH - NO Central Malta Cntrl Intake - SS | Clifton Park Center, 320 Ushers Road | Ballston Lake | NY | 12065 | (518)899-1158 |  |  |  | 2379 | 13 |  | 13 |  |  |  |  | 0 |  | #DIV/0! |  | 0 | WIN 10 Upgrade
| 3849097 | 2020-03-23 | [7 empty] | SC | 3849097 | 3849 HH - Kansas City Central Intake | 20101 E. Jackson Drive STE D | Independence | MO | 64057 | [5 empty] | 0 |  | 0 | [6 empty] | #DIV/0! |  | 0 | WIN 10 Upgrade
| 2086201 | 2019-09-16 |  |  |  | 2 | 1 | Yes |  |  | 2086201 | Corporate Finance Office (Atlanta) | 3350 Riverwood Parkway, Suite 1400 | Atlanta | GA | 30339 | [5 empty] | 100 |  |  | 76 |  | 25 | 55 |  |  | #DIV/0! |  |  | WIN 10 Upgrade
| 1142201 | 2019-09-16 | [5 empty] | Yes |  |  | 1142201 | R140 HH - South Region (need # migrated at sites) (10) | 3350 Riverwood Parkway, Suite 1400 | Atlanta | GA | 30339 | [5 empty] | 1 | [8 empty] | #DIV/0! |  |  | WIN 10 Upgrade
| 1159979 | 2019-11-18 |  |  |  |  | 1 | 2019-12-13 |  |  | 1159979 | Atlanta FSU HomeHealth | 3350 Riverwood Parkway, Suite 1400 | Atlanta | GA | 30339 | [5 empty] | 97 |  |  | 10 |  | 1 | 5 | 106 |  | #DIV/0! |  |  | WIN 10 Upgrade
| 1157201 | 2019-11-18 |  |  |  | 3 | 1 | 2019-12-20 |  |  | 1157201 | Overland Park FSU Home Health | 12900 Foster Street, Suite 400 | Overland Park | KS | 66213 | [5 empty] | 275 |  |  | 138 |  | 8 | 28 | 155 |  | #DIV/0! |  |  | WIN 10 Upgrade
| 1066201 | 2020-02-17 |  |  |  | 2 | 1 | 2 wks |  |  | 1066201 | R100 - HH North Region | 7900 International Drive, Suite 140 | Bloomington | MN | 55425 |  | Dianna Morgel (EA) |  |  |  | 20 |  |  | 13 |  | 1 |  | 11 |  | #DIV/0! |  |  | WIN 10 Upgrade
| 1197201 | 2020-02-17 | [8 empty] | 1197201 | North Regional Sales HH | 7900 International Drive, Suite 140 | Bloomington | MN | 55425 |  | Dianna Morgel (EA) |  |  |  | 14 |  |  | 2 | [5 empty] | #DIV/0! |  |  | WIN 10 Upgrade
| 1049201 | 2020-02-17 |  |  |  | 2 | 1 | 3 wks |  |  | 1049201 | South Regional Sales HH | 3525 Whitehall Park Drive, Suite 220 | Charlotte | NC | 28273 |  |  |  |  | 1087 | 5 |  |  | 4 | [5 empty] | #DIV/0! |  |  | WIN 10 Upgrade
| 1087201 | 2020-02-17 | [8 empty] | 1087201 | HH South Regional Topside - Admin | 3525 Whitehall Park Drive, Suite 220 | Charlotte | NC | 28273 |  |  |  |  | 1049 | 56 |  |  | 19 |  | 13 |  | 8 |  | #DIV/0! |  |  | WIN 10 Upgrade
TOTALS | [21 empty] | 13354 | 4878 | 11522 | 1661 | 927 | 171 | 365 | 2065 | 1761 | 36.1% | 3894 | 3053
Sites below this line will not be included
| 7020201 |  | 2020-01-05 | 2019-09-24 | 2019-10-22 | 1 | 1 |  |  | SC | 7020201 | 7020 HH - HUGO (fka 2558) (DM project) | 804 East Jackson Street | Hugo | OK | 74743 | (580)326-8376 | Lou Ellis | Rhonda Bozeman | 10.25.128 |  | 32 |  | 32 | 0 |  | 0 |  | 3 |  | #DIV/0! | 3 | 0 | WIN 10 Upgrade
| 2582201 |  | 2020-01-05 | 2019-09-24 | 2019-10-22 |  |  |  |  | SC | 2582201 | 2582 HH - TYLER - HARDEN (DM project) | 1700 S Southeast Loop 323 STE 110 | Tyler | TX | 75701 | (903)595-5266 | Shavontrola Rodriguez |  | 10.153.98 |  | 36 |  | 32 | 4 |  | 0 |  | 10 |  | #DIV/0! | 14 | 0 | WIN 10 Upgrade
| 3282201 |  |  |  |  | 1 | 1 |  |  | SC | 3282201 | RF3282 - Kindred at Home Billing (DM project) | 2560 SW GRAPEVINE PKWY | GRAPEVINE | TX | 76051 | (817)310-3905 |  |  | 10.140.148-10.140.151 |  | 2 |  | -4 | 4 |  | 2 |  | 6 |  | #DIV/0! | 12 | 0 | WIN 10 Upgrade
| 3776201 |  | 2019-09-29 |  | 2019-07-16 | 1 | 1 |  |  |  | 3776201 | 3776 HH - KOKOMO, IN closed | 2130 Sycamore St. STE 240 | Kokomo | IN | 46901 | (765)878-6519 | Hannah Klepinger |  | 10.160.193 |  | 23 |  | 16 | 6 |  | 1 |  | 4 |  | #DIV/0! | 11 | 0 | WIN 10 Upgrade
| 2583201 |  | 2020-01-05 | 2019-09-24 | 2019-10-22 |  |  |  |  | SC | 2583201 | 2583 HH - WACO - HARDEN - Moved to DM project | 5400 Bosque Boulevard STE 245 | Waco | TX | 76710 | (254)405-6800 | Andrea Martin |  | 10.160.141 |  | 117 |  |  | 6 |  | 1 |  | 9 |  | #DIV/0! | 16 |  | WIN 10 Upgrade
| 3535201 |  |  |  |  | 1 | 1 |  |  |  | 3535201 | West Region Office 1 (moved to DM project) | 2560 SW Grapevine Pkwy, Suite 120 | Grapevine | TX | 76051 | [5 empty] | 105 | [8 empty] | #DIV/0! |  |  | WIN 10 Upgrade
| 8400201 |  |  |  |  | 1 | 1 |  |  |  | 8400201 | Girling Community Care Texas by Harden Healthcare of Austin Admin | 3307 Northland Drive, Suite 260 | Austin | TX | 78731 | [5 empty] | 32 |  |  | 1 |  |  |  | 25 |  | #DIV/0! |  |  | WIN 10 Upgrade
| 1120201 |  |  |  |  | 2 | 1 | 2 wks |  |  | 1120201 | R130 - HH West Region | 14614 N Kierland Blvd, Suite 300N | Scottsdale | AZ | 85254 | [5 empty] | 17 |  |  | 17 |  | 6 |  | 2 |  | #DIV/0! |  |  | WIN 10 Upgrade
| 1058201 | [9 empty] | 1058201 | West Regional Sales HH | 14614 N Kierland Blvd, Suite 300N | Scottsdale | AZ | 85254 | [5 empty] | 36 |  |  |  |  | 1 |  |  |  | #DIV/0! |  |  | WIN 10 Upgrade
SHELF | 5024201 | [7 empty] | Y-1143 | WS | 5024201 | 5024 HH - KERNERSVILLE | 720 Park Centre Drive STE B | Kernersville | NC | 27284 | (336)564-0185 | Rebecca Vaughn |  | 10.25.97 | 5025 | 1 |  |  | 3 |  | 0 |  | 11 |  | #DIV/0! | 14 |  | WIN 10 Upgrade
SHELF | 3122201 |  |  |  | 2019-08-13 |  |  |  | Y-6964 |  | 3122201 | 3122 HH-Catawba Co | 1771 Tate Blvd. SE STE 102 | Hickory | NC | 28602 | (828)270-3990 | Bobbi Willis |  | 10.25.81 | 5060 | 0 |  |  | 0 |  | 0 |  | 0 |  | #DIV/0! | 0 |  | WIN 10 Upgrade
Indicates site was not listed in CI spreadsheet
Indicates possible question regarding rollout schedule
Indicates Corp site
Indicates Win10 date is inside 75 HCHB go-live window
Formulas:
HCHB+75 days HCHB = [HCHB Go Live Date]-35
HCHB+75 days HCHB = [HCHB Go Live Date]+75
H-4 HCHB OLH Training = [HCHB Go Live Date]-28
Note on AC152: Carmack, Tim: Add 2 for scanners
Note on AC153: Carmack, Tim: Add 2 for scanners
Note on AC179: Carmack, Tim: Add 5 for scanners

## Service Tickets (hidden)
Facility ID | Site | Address | City | State | Zip | City_State_Zip | Thin Clients | Net New Laptops | Laptop Upgrade | Migration Date | Onsite By | Order By | Thin Client PO | Laptop PO | Ticket Title | Ticket Verbage | Ticket Number | Site Updated | Completed | Year Completed | Notes
5031201 | 5031 HH - GOLDSBORO | 1200 Parkway Dr. | Goldsboro | NC | 27534 | Goldsboro, NC 27534 | 16 | 0 | 4 | 2019-06-24 | 2019-06-21 | 2019-06-10 | 703300 | 703301 | 5031 HH - GOLDSBORO KAH Win10 Upgrade Project Equipment Request | Please ship 16 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 06/21/19. Ship to: ATTN: Kindred Implementation Services Tech 1200 Parkway Dr. Goldsboro, NC 27534 | INC0028801 | No | Yes | 2019
5033201 | 5033 HH - KINSTON | 2111 North Queen Street STE C | Kinston | NC | 28501 | Kinston, NC 28501 | 9 | 1 | 4 | 2019-06-24 | 2019-06-21 | 2019-06-10 | 703300 | 703301 | 5033 HH - KINSTON KAH Win10 Upgrade Project Equipment Request | Please ship 9 UD3 Thin Client devices and 1 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 06/21/19. Ship to: ATTN: Kindred Implementation Services Tech 2111 North Queen Street STE C Kinston, NC 28501 | INC0028420 | No | Yes | 2019
2475201 | 2475 HH - PANAMA CITY | 1013 Beck Avenue | Panama City | FL | 32401 | Panama City, FL 32401 | 9 | 0 | 9 | 2019-06-24 | 2019-06-21 | 2019-06-10 | 703300 | 703301 | 2475 HH - PANAMA CITY KAH Win10 Upgrade Project Equipment Request | Please ship 9 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 06/21/19. Ship to: ATTN: Kindred Implementation Services Tech 1013 Beck Avenue Panama City, FL 32401 | INC0028844 | No | Yes | 2019
5049201 | 5049 HH - SALISBURY | 1834 West Jake Alexander Blvd. STE 503 | Salisbury | NC | 28147 | Salisbury, NC 28147 | 14 | 0 | 5 | 2019-06-24 | 2019-06-21 | 2019-06-10 | 703300 | 703301 | 5049 HH - SALISBURY KAH Win10 Upgrade Project Equipment Request | Please ship 14 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 06/21/19. Ship to: ATTN: Kindred Implementation Services Tech 1834 West Jake Alexander Blvd. STE 503 Salisbury, NC 28147 | INC0029583 | No | Yes | 2019
5056201 | 5056 HH - IREDELL CO | 1905 East Broad Street | Statesville | NC | 28625 | Statesville, NC 28625 | 19 | 5 | 3 | 2019-06-24 | 2019-06-21 | 2019-06-10 | 703300 | 703301 | 5056 HH - IREDELL CO KAH Win10 Upgrade Project Equipment Request | Please ship 19 UD3 Thin Client devices and 5 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 06/21/19. Ship to: ATTN: Kindred Implementation Services Tech 1905 East Broad Street Statesville, NC 28625 | INC0029502 | No | Yes | 2019
1294201 | 1294 HH - LILLINGTON NC | 87 W Cornelius Harnett Boulevard | Lillington | NC | 27546 | Lillington, NC 27546 | 4 | 0 | 2 | 2019-07-01 | 2019-06-28 | 2019-06-17 | 703300 | 703301 | 1294 HH - LILLINGTON NC KAH Win10 Upgrade Project Equipment Request | Please ship 4 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 06/28/19. Ship to: ATTN: Kindred Implementation Services Tech 87 W Cornelius Harnett Boulevard Lillington, NC 27546 | INC0035911 | Yes | Yes | 2019
2472201 | 2472 HH - FT WALTON BEACH | 340 Beal Parkway NW STE A | Fort Walton Beach | FL | 32548 | Fort Walton Beach, FL 32548 | 6 | 1 | 38 | 2019-07-01 | 2019-06-28 | 2019-06-17 | 703300 | 703301 | 2472 HH - FT WALTON BEACH KAH Win10 Upgrade Project Equipment Request | Please ship 6 UD3 Thin Client devices and 1 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 06/28/19. Ship to: ATTN: Kindred Implementation Services Tech 340 Beal Parkway NW STE A Fort Walton Beach, FL 32548 | INC0035916 | Yes | Yes | 2019
5023201 | 5023 HH - KIMEL PARK | 2000 Frontis Plaza Blvd STE 300 | Winston-Salem | NC | 27103 | Winston-Salem, NC 27103 | 17 | 2 | 8 | 2019-07-01 | 2019-06-28 | 2019-06-17 | 703300 | 703301 | 5023 HH - KIMEL PARK KAH Win10 Upgrade Project Equipment Request | Please ship 17 UD3 Thin Client devices and 2 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 06/28/19. Ship to: ATTN: Kindred Implementation Services Tech 2000 Frontis Plaza Blvd STE 300 Winston-Salem, NC 27103 | INC0039422 | Yes | Yes | 2019
5027201 | 5027 HH - WAKE FOREST JV (fka 2353) | 2000 Frontis Plaza Blvd STE 303 | Winston-Salem | NC | 27103 | Winston-Salem, NC 27103 | 14 | 1 | 4 | 2019-07-01 | 2019-06-28 | 2019-06-17 | 703300 | 703301 | 5027 HH - WAKE FOREST JV (fka 2353) KAH Win10 Upgrade Project Equipment Request | Please ship 14 UD3 Thin Client devices and 1 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 06/28/19. Ship to: ATTN: Kindred Implementation Services Tech 2000 Frontis Plaza Blvd STE 303 Winston-Salem, NC 27103 | INC0039169 | Yes | Yes | 2019
5029201 | 5029 HH - YOUNGSVILLE | 74 Wheaton Avenue | Youngsville | NC | 27596 | Youngsville, NC 27596 | 9 | 2 | 3 | 2019-07-01 | 2019-06-28 | 2019-06-17 | 703300 | 703301 | 5029 HH - YOUNGSVILLE KAH Win10 Upgrade Project Equipment Request | Please ship 9 UD3 Thin Client devices and 2 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 06/28/19. Ship to: ATTN: Kindred Implementation Services Tech 74 Wheaton Avenue Youngsville, NC 27596 | INC0035928 | Yes | Yes | 2019
5032201 | 5032 HH - GREENVILLE NC | 1970 West Arlington Blvd. STE B-2 | Greenville | NC | 27834 | Greenville, NC 27834 | 10 | 1 | 7 | 2019-07-01 | 2019-06-28 | 2019-06-17 | 703300 | 703301 | 5032 HH - GREENVILLE NC KAH Win10 Upgrade Project Equipment Request | Please ship 10 UD3 Thin Client devices and 1 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 06/28/19. Ship to: ATTN: Kindred Implementation Services Tech 1970 West Arlington Blvd. STE B-2 Greenville, NC 27834 | INC0035932 | Yes | Yes | 2019
5034201 | 5034 HH - MOREHEAD | Cypress Bay Plaza, 5167 US Hwy 70 West STE 100 | Morehead City | NC | 28557 | Morehead City, NC 28557 | 6 | 1 | 6 | 2019-07-01 | 2019-06-28 | 2019-06-17 | 703300 | 703301 | 5034 HH - MOREHEAD KAH Win10 Upgrade Project Equipment Request | Please ship 6 UD3 Thin Client devices and 1 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 06/28/19. Ship to: ATTN: Kindred Implementation Services Tech Cypress Bay Plaza, 5167 US Hwy 70 West STE 100 Morehead City, NC 28557 | INC0035936 | Yes | Yes | 2019
5036201 | 5036 HH - POLLOCKSVILLE | P. O. Box 399, 124 Main Street | Pollocksville | NC | 28573 | Pollocksville, NC 28573 | 7 | 0 | 7 | 2019-07-01 | 2019-06-28 | 2019-06-17 | 703300 | 703301 | 5036 HH - POLLOCKSVILLE KAH Win10 Upgrade Project Equipment Request | Please ship 7 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 06/28/19. Ship to: ATTN: Kindred Implementation Services Tech P. O. Box 399, 124 Main Street Pollocksville, NC 28573 | INC0035942 | Yes | Yes | 2019
5038201 | 5038 HH - WASHINGTON | 1638 Carolina Ave. | Washington | NC | 27889 | Washington, NC 27889 | 20 | 0 | 5 | 2019-07-01 | 2019-06-28 | 2019-06-17 | 703300 | 703301 | 5038 HH - WASHINGTON KAH Win10 Upgrade Project Equipment Request | Please ship 20 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 06/28/19. Ship to: ATTN: Kindred Implementation Services Tech 1638 Carolina Ave. Washington, NC 27889 | INC0038656 | Yes | Yes | 2019
5047201 | 5047 HH - KING | 621 Ingram Drive STE B | King | NC | 27021 | King, NC 27021 | 11 | 6 | 5 | 2019-07-01 | 2019-06-28 | 2019-06-17 | 703300 | 703301 | 5047 HH - KING KAH Win10 Upgrade Project Equipment Request | Please ship 11 UD3 Thin Client devices and 6 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 06/28/19. Ship to: ATTN: Kindred Implementation Services Tech 621 Ingram Drive STE B King, NC 27021 | INC0035945 | Yes | Yes | 2019
5058201 | 5058 HH - ASHEVILLE | 9 Olde Eastwood Village Blvd. | Asheville | NC | 28803 | Asheville, NC 28803 | 29 | 4 | 10 | 2019-07-01 | 2019-06-28 | 2019-06-17 | 703300 | 703301 | 5058 HH - ASHEVILLE KAH Win10 Upgrade Project Equipment Request | Please ship 29 UD3 Thin Client devices and 4 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 06/28/19. Ship to: ATTN: Kindred Implementation Services Tech 9 Olde Eastwood Village Blvd. Asheville, NC 28803 | INC0039441 | Yes | Yes | 2019
5060201 | 5060 HH - HICKORY | 1771 Tate Blvd. SE STE 104 | Hickory | NC | 28602 | Hickory, NC 28602 | 12 | 0 | 1 | 2019-07-01 | 2019-06-28 | 2019-06-17 | 703300 | 703301 | 5060 HH - HICKORY KAH Win10 Upgrade Project Equipment Request | Please ship 12 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 06/28/19. Ship to: ATTN: Kindred Implementation Services Tech 1771 Tate Blvd. SE STE 104 Hickory, NC 28602 |  | Yes | Yes | 2019
5061201 | 5061 HH - HICKORY (Healthfield) | 1771 Tate Blvd. SE STE 101 | Hickory | NC | 28602 | Hickory, NC 28602 | 23 | 0 | 14 | 2019-07-01 | 2019-06-28 | 2019-06-17 | 703300 | 703301 | 5061 HH - HICKORY (Healthfield) KAH Win10 Upgrade Project Equipment Request | Please ship 23 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 06/28/19. Ship to: ATTN: Kindred Implementation Services Tech 1771 Tate Blvd. SE STE 101 Hickory, NC 28602 |  | Yes | Yes | 2019
5063201 | 5063 HH - SHELBY | 1405 N Lafayette Street | Shelby | NC | 28150 | Shelby, NC 28150 | 28 | 5 | 10 | 2019-07-08 | 2019-07-05 | 2019-06-24 | 703300 | 703301 | 5063 HH - SHELBY KAH Win10 Upgrade Project Equipment Request | Please ship 28 UD3 Thin Client devices and 5 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 07/05/19. Ship to: ATTN: Kindred Implementation Services Tech 1405 N Lafayette Street Shelby, NC 28150 | INC0035950 | Yes | Yes | 2019
6989201 | 6989 HH - LINCOLN COUNTY | 308 S Academy Street | Lincolnton | NC | 28092 | Lincolnton, NC 28092 | 6 | 0 | 2 | 2019-07-08 | 2019-07-05 | 2019-06-24 | 703300 | 703301 | 6989 HH - LINCOLN COUNTY KAH Win10 Upgrade Project Equipment Request | Please ship 6 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 07/05/19. Ship to: ATTN: Kindred Implementation Services Tech 308 S Academy Street Lincolnton, NC 28092 | 1958902 | Yes | Yes | 2019
2439201 | 2439 HH - STROUDSBURG PA | 1250 N. 9th St. STE 105 | Stroudsburg | PA | 18360 | Stroudsburg, PA 18360 | 13 | 6 | 7 | 2019-07-15 | 2019-07-12 | 2019-07-01 | 703300 | 703301 | 2439 HH - STROUDSBURG PA KAH Win10 Upgrade Project Equipment Request | Please ship 13 UD3 Thin Client devices and 6 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 07/12/19. Ship to: ATTN: Kindred Implementation Services Tech 1250 N. 9th St. STE 105 Stroudsburg, PA 18360 | INC0054897 | Yes | Yes | 2019 | Cherwell - 1960304
2399201 | 2399 HH - AKRON | 1531 Boettler Road STE E | Uniontown | OH | 44685 | Uniontown, OH 44685 | 4 | 0 | 4 | 2019-07-15 | 2019-07-12 | 2019-07-01 | 703300 | 703301 | 2399 HH - AKRON KAH Win10 Upgrade Project Equipment Request | Please ship 4 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 07/12/19. Ship to: ATTN: Kindred Implementation Services Tech 1531 Boettler Road STE E Uniontown, OH 44685 | INC0055015 | Yes | Yes | 2019 | Cherwell - 1960301
2439201 | 2439 HH - STROUDSBURG PA | 1250 N. 9th St. STE 105 | Stroudsburg | PA | 18360 | Stroudsburg, PA 18360 | 13 | 6 | 7 | 2019-07-15 | 2019-07-12 | 2019-07-01 | 703300 | 703301 | 2439 HH - STROUDSBURG PA KAH Win10 Upgrade Project Equipment Request | Please ship 13 UD3 Thin Client devices and 6 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 07/12/19. Ship to: ATTN: Kindred Implementation Services Tech 1250 N. 9th St. STE 105 Stroudsburg, PA 18360 |  | No | Yes | 2020
5024201 | 5024 HH - KERNERSVILLE | 720 Park Centre Drive STE B | Kernersville | NC | 27284 | Kernersville, NC 27284 | 0 | 0 | 0 | 0 | #NUM! | -14 | 703300 | 703301 | 5024 HH - KERNERSVILLE KAH Win10 Upgrade Project Equipment Request | #NUM! |  | No | 0 | 2020
2473201 | 2473 HH - CRESTVIEW | 370 W Redstone Ave | Crestview | FL | 32536 | Crestview, FL 32536 | 12 | 2 | 10 | 2019-07-22 | 2019-07-19 | 2019-07-08 | 703300 | 703301 | 2473 HH - CRESTVIEW KAH Win10 Upgrade Project Equipment Request | Please ship 12 UD3 Thin Client devices and 2 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 07/19/19. Ship to: ATTN: Kindred Implementation Services Tech 370 W Redstone Ave Crestview, FL 32536 | INC0035921 | Yes | Yes | 2019
5030201 | 5030 HH - RALEIGH | 3301 Benson Drive STE 222 | Raleigh | NC | 27609 | Raleigh, NC 27609 | 23 | 10 | 22 | 2019-07-22 | 2019-07-19 | 2019-07-08 | 703300 | 703301 | 5030 HH - RALEIGH KAH Win10 Upgrade Project Equipment Request | Please ship 23 UD3 Thin Client devices and 10 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 07/19/19. Ship to: ATTN: Kindred Implementation Services Tech 3301 Benson Drive STE 222 Raleigh, NC 27609 | INC0036253; 1959779 | Yes | Yes | 2019 | Equipment had to go to Hickory, created new ticket
5083201 | 5083 HH - KINGSPORT | 2004 American Way STE 121 | Kingsport | TN | 37660 | Kingsport, TN 37660 | 10 | 0 | 5 | 2019-07-22 | 2019-07-19 | 2019-07-08 | 703300 | 703301 | 5083 HH - KINGSPORT KAH Win10 Upgrade Project Equipment Request | Please ship 10 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 07/19/19. Ship to: ATTN: Kindred Implementation Services Tech 2004 American Way STE 121 Kingsport, TN 37660 |  | No | Yes | 2020
5084201 | 5084 HH - KNOXVILLE | 320 North Cedar Bluff Road STE 380/360 | Knoxville | TN | 37923 | Knoxville, TN 37923 | 7 | 0 | 7 | 2019-07-22 | 2019-07-19 | 2019-07-08 | 703300 | 703301 | 5084 HH - KNOXVILLE KAH Win10 Upgrade Project Equipment Request | Please ship 7 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 07/19/19. Ship to: ATTN: Kindred Implementation Services Tech 320 North Cedar Bluff Road STE 380/360 Knoxville, TN 37923 |  | No | Yes | 2020
2468201 | 2468 HH - ROME | 504 Riverside Parkway NE STE 500 | Rome | GA | 30161 | Rome, GA 30161 | 13 | 2 | 6 | 2019-08-05 | 2019-08-02 | 2019-07-22 | 703300 | 703301 | 2468 HH - ROME KAH Win10 Upgrade Project Equipment Request | Please ship 13 UD3 Thin Client devices and 2 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 08/02/19. Ship to: ATTN: Kindred Implementation Services Tech 504 Riverside Parkway NE STE 500 Rome, GA 30161 | 1962311 | Yes | Yes | 2019
5080201 | 5080 HH - LEBANON TN | 115 Winwood Dr. STE 101 | Lebanon | TN | 37087 | Lebanon, TN 37087 | 9 | 1 | 4 | 2019-08-05 | 2019-08-02 | 2019-07-22 | 703300 | 703301 | 5080 HH - LEBANON TN KAH Win10 Upgrade Project Equipment Request | Please ship 9 UD3 Thin Client devices and 1 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 08/02/19. Ship to: ATTN: Kindred Implementation Services Tech 115 Winwood Dr. STE 101 Lebanon, TN 37087 | 1962307 | Yes | Yes | 2019
5085201 | 5085 HH - CHATTANOOGA | 5751 Cornelison Road Bldg 6400 B STE 100 | Chattanooga | TN | 37411 | Chattanooga, TN 37411 | 4 | 1 | 3 | 2019-08-05 | 2019-08-02 | 2019-07-22 | 703300 | 703301 | 5085 HH - CHATTANOOGA KAH Win10 Upgrade Project Equipment Request | Please ship 4 UD3 Thin Client devices and 1 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 08/02/19. Ship to: ATTN: Kindred Implementation Services Tech 5751 Cornelison Road Bldg 6400 B STE 100 Chattanooga, TN 37411 | 1962310 | Yes | Yes | 2019
5082201 | 5082 HH - SMYRNA | 697 President Place STE 303B | Smyrna | TN | 37167 | Smyrna, TN 37167 | 2 | 0 | 0 | 2019-08-05 | 2019-08-02 | 2019-07-22 | 703300 | 703301 | 5082 HH - SMYRNA KAH Win10 Upgrade Project Equipment Request | Please ship 2 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 08/02/19. Ship to: ATTN: Kindred Implementation Services Tech 697 President Place STE 303B Smyrna, TN 37167 |  | No | Yes | 2020
2394201 | 2394 HH - FLINT | 4458 Oakbridge Drive STE B | Flint | MI | 48532 | Flint, MI 48532 | 7 | 0 | 3 | 2019-08-12 | 2019-08-09 | 2019-07-29 | 703300 | 703301 | 2394 HH - FLINT KAH Win10 Upgrade Project Equipment Request | Please ship 7 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 08/09/19. Ship to: ATTN: Kindred Implementation Services Tech 4458 Oakbridge Drive STE B Flint, MI 48532 | 1962688 | Yes | Yes | 2019
2655201 | 2655 HH - SEATTLE | 155 NE 100th Street STE 510 | Seattle | WA | 98125 | Seattle, WA 98125 | 14 | 0 | 9 | 2019-08-12 | 2019-08-09 | 2019-07-29 | 703300 | 703301 | 2655 HH - SEATTLE KAH Win10 Upgrade Project Equipment Request | Please ship 14 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 08/09/19. Ship to: ATTN: Kindred Implementation Services Tech 155 NE 100th Street STE 510 Seattle, WA 98125 | 1962690 | Yes | Yes | 2019
2685201 | 2685 HH - VANCOUVER | 204 SE Stone Mill Drive STE 260 | Vancouver | WA | 98684 | Vancouver, WA 98684 | 11 | 2 | 6 | 2019-08-12 | 2019-08-09 | 2019-07-29 | 703300 | 703301 | 2685 HH - VANCOUVER KAH Win10 Upgrade Project Equipment Request | Please ship 11 UD3 Thin Client devices and 2 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 08/09/19. Ship to: ATTN: Kindred Implementation Services Tech 204 SE Stone Mill Drive STE 260 Vancouver, WA 98684 | 1962686 | Yes | Yes | 2019
2697201 | 2697 HH - PORTLAND OR HHA | 4500 Kruse Way STE 310 | Lake Oswego | OR | 97035 | Lake Oswego, OR 97035 | 8 | 0 | 6 | 2019-08-12 | 2019-08-09 | 2019-07-29 | 703300 | 703301 | 2697 HH - PORTLAND OR HHA KAH Win10 Upgrade Project Equipment Request | Please ship 8 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 08/09/19. Ship to: ATTN: Kindred Implementation Services Tech 4500 Kruse Way STE 310 Lake Oswego, OR 97035 | 1962687 | Yes | Yes | 2019
3197201 | 3197 HH - RIVERHEAD NEW | 877 East Main St. | Riverhead | NY | 11901 | Riverhead, NY 11901 | 12 | 1 | 5 | 2019-08-12 | 2019-08-09 | 2019-07-29 | 703300 | 703301 | 3197 HH - RIVERHEAD NEW KAH Win10 Upgrade Project Equipment Request | Please ship 12 UD3 Thin Client devices and 1 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 08/09/19. Ship to: ATTN: Kindred Implementation Services Tech 877 East Main St. Riverhead, NY 11901 | 1962685 | Yes | Yes | 2019
7026201 | 7026 HH - EVERETT (fka 2654) | 728 134TH ST SW, Suite 203 | Everett | WA | 98204 | Everett, WA 98204 | 13 | 0 | 7 | 2019-08-12 | 2019-08-09 | 2019-07-29 | 703300 | 703301 | 7026 HH - EVERETT (fka 2654) KAH Win10 Upgrade Project Equipment Request | Please ship 13 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 08/09/19. Ship to: ATTN: Kindred Implementation Services Tech 728 134TH ST SW, Suite 203 Everett, WA 98204 | 1962684 | Yes | Yes | 2019
7027201 | 7027 HH - BELLEVUE WA | 10940 NE 33rd Place STE 103 | Bellevue | WA | 98004 | Bellevue, WA 98004 | 12 | 1 | 8 | 2019-08-12 | 2019-08-09 | 2019-07-29 | 703300 | 703301 | 7027 HH - BELLEVUE WA KAH Win10 Upgrade Project Equipment Request | Please ship 12 UD3 Thin Client devices and 1 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 08/09/19. Ship to: ATTN: Kindred Implementation Services Tech 10940 NE 33rd Place STE 103 Bellevue, WA 98004 | 1962700 | Yes | Yes | 2019
2393201 | 2393 HH - KALAMAZOO | 5148 Lovers Lane STE 210 | Portage | MI | 49002 | Portage, MI 49002 | 10 | 0 | 6 | 2019-08-12 | 2019-08-09 | 2019-07-29 | 703300 | 703301 | 2393 HH - KALAMAZOO KAH Win10 Upgrade Project Equipment Request | Please ship 10 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 08/09/19. Ship to: ATTN: Kindred Implementation Services Tech 5148 Lovers Lane STE 210 Portage, MI 49002 | 1962694 | Yes | Yes | 2019
2438201 | 2438 HH - WESTBURY | 865 Merrick Avenue STE 340 South | Westbury | NY | 11590 | Westbury, NY 11590 | 10 | 0 | 5 | 2019-08-12 | 2019-08-09 | 2019-07-29 | 703300 | 703301 | 2438 HH - WESTBURY KAH Win10 Upgrade Project Equipment Request | Please ship 10 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 08/09/19. Ship to: ATTN: Kindred Implementation Services Tech 865 Merrick Avenue STE 340 South Westbury, NY 11590 | 1962696 | Yes | Yes | 2019
2617201 | 2617 HH - SAN JOSE HHA | 4030 Moorpark Ave. STE 251 | San Jose | CA | 95117 | San Jose, CA 95117 | 6 | 0 | 7 | 2019-08-12 | 2019-08-09 | 2019-07-29 | 703300 | 703301 | 2617 HH - SAN JOSE HHA KAH Win10 Upgrade Project Equipment Request | Please ship 6 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 08/09/19. Ship to: ATTN: Kindred Implementation Services Tech 4030 Moorpark Ave. STE 251 San Jose, CA 95117 | 1962691 | Yes | Yes | 2019
2626201 | 2626 HH - SAN JOSE - HARDEN | 1840 The Alameda | San Jose | CA | 95126 | San Jose, CA 95126 | 19 | 0 | 3 | 2019-08-12 | 2019-08-09 | 2019-07-29 | 703300 | 703301 | 2626 HH - SAN JOSE - HARDEN KAH Win10 Upgrade Project Equipment Request | Please ship 19 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 08/09/19. Ship to: ATTN: Kindred Implementation Services Tech 1840 The Alameda San Jose, CA 95126 | 1962698 | Yes | Yes | 2019
2395201 | 2395 HH - GRAND RAPIDS | 625 Kenmoor Avenue SE STE 306 | Grand Rapids | MI | 49546 | Grand Rapids, MI 49546 | 7 | 7 | 7 | 2019-08-12 | 2019-08-09 | 2019-07-29 | 703300 | 703301 | 2395 HH - GRAND RAPIDS KAH Win10 Upgrade Project Equipment Request | Please ship 7 UD3 Thin Client devices and 7 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 08/09/19. Ship to: ATTN: Kindred Implementation Services Tech 625 Kenmoor Avenue SE STE 306 Grand Rapids, MI 49546 | 1962768 | Yes | Yes | 2019 | laptops shipped from here (775926327268)
2436201 | 2436 HH - HAUPPAUGE | 888 Veterans Memorial Highway STE 210 | Hauppauge | NY | 11788 | Hauppauge, NY 11788 | 18 | 5 | 7 | 2019-08-19 | 2019-08-16 | 2019-08-05 | 703300 | 703301 | 2436 HH - HAUPPAUGE KAH Win10 Upgrade Project Equipment Request | Please ship 18 UD3 Thin Client devices and 5 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 08/16/19. Ship to: ATTN: Kindred Implementation Services Tech 888 Veterans Memorial Highway STE 210 Hauppauge, NY 11788 |  | Yes | Yes | 2019
2111201 | 2111 HH - TACOMA | 4020 South 56th St. STE 101 | Tacoma | WA | 98409 | Tacoma, WA 98409 | 13 | 3 | 11 | 2019-08-26 | 2019-08-23 | 2019-08-12 | 703300 | 703301 | 2111 HH - TACOMA KAH Win10 Upgrade Project Equipment Request | Please ship 13 UD3 Thin Client devices and 3 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 08/23/19. Ship to: ATTN: Kindred Implementation Services Tech 4020 South 56th St. STE 101 Tacoma, WA 98409 |  | Yes | Yes | 2019
2730201 | 2730 HH - PUYALLUP WA (2134 in KD) | 2913 NE 5th Avenue STE 202 | Puyallup | WA | 98372 | Puyallup, WA 98372 | 5 | 0 | 0 | 2019-08-26 | 2019-08-23 | 2019-08-12 | 703300 | 703301 | 2730 HH - PUYALLUP WA (2134 in KD) KAH Win10 Upgrade Project Equipment Request | Please ship 5 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 08/23/19. Ship to: ATTN: Kindred Implementation Services Tech 2913 NE 5th Avenue STE 202 Puyallup, WA 98372 | 1961407 | Yes | Yes | 2019
2623201 | 2623 HH - OAKLAND | 1301 Marina Village Parkway STE 103 | Alameda | CA | 94501 | Alameda, CA 94501 | 17 | 0 | 1 | 2019-08-26 | 2019-08-23 | 2019-08-12 | 703300 | 703301 | 2623 HH - OAKLAND KAH Win10 Upgrade Project Equipment Request | Please ship 17 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 08/23/19. Ship to: ATTN: Kindred Implementation Services Tech 1301 Marina Village Parkway STE 103 Alameda, CA 94501 | 1965877 | Yes | Yes | 2019
7021201 | 7021 HH - SANTA ROSA (fka 2622) | 5341 Old Redwood Highway, STE 350 | Peteluma | CA | 94954 | Peteluma, CA 94954 | 10 | 0 | 7 | 2019-08-26 | 2019-08-23 | 2019-08-12 | 703300 | 703301 | 7021 HH - SANTA ROSA (fka 2622) KAH Win10 Upgrade Project Equipment Request | Please ship 10 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 08/23/19. Ship to: ATTN: Kindred Implementation Services Tech 5341 Old Redwood Highway, STE 350 Peteluma, CA 94954 | 1965875 | Yes | Yes | 2019
2533201 | 2533 HH - ALBERTVILLE | 700 AL Hwy 75 N | Albertville | AL | 35951 | Albertville, AL 35951 | 7 | 1 | 4 | 2019-09-09 | 2019-09-06 | 2019-08-26 | 703300 | 703301 | 2533 HH - ALBERTVILLE KAH Win10 Upgrade Project Equipment Request | Please ship 7 UD3 Thin Client devices and 1 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 09/06/19. Ship to: ATTN: Kindred Implementation Services Tech 700 AL Hwy 75 N Albertville, AL 35951 | 1966805 | Yes | Yes | 2019 | added 1 additional on ticket 1967268
2534201 | 2534 HH - FORT PAYNE | 716 Gault Avenue N | Fort Payne | AL | 35967 | Fort Payne, AL 35967 | 3 | 2 | 2 | 2019-09-09 | 2019-09-06 | 2019-08-26 | 703300 | 703301 | 2534 HH - FORT PAYNE KAH Win10 Upgrade Project Equipment Request | Please ship 3 UD3 Thin Client devices and 2 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 09/06/19. Ship to: ATTN: Kindred Implementation Services Tech 716 Gault Avenue N Fort Payne, AL 35967 | 1966806 | Yes | Yes | 2019
2458201 | 2458 HH - COLUMBUS GA | 1921 Whittlesey Road STE 310 | Columbus | GA | 31904 | Columbus, GA 31904 | 9 | 1 | 9 | 2019-09-16 | 2019-09-13 | 2019-09-02 | 703300 | 703301 | 2458 HH - COLUMBUS GA KAH Win10 Upgrade Project Equipment Request | Please ship 9 UD3 Thin Client devices and 1 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 09/13/19. Ship to: ATTN: Kindred Implementation Services Tech 1921 Whittlesey Road STE 310 Columbus, GA 31904 | 1967724 | Yes | Yes | 2019
2536201 | 2536 HH - FLORENCE | 3242 Florence Boulevard | Florence | AL | 35634 | Florence, AL 35634 | 10 | 0 | 2 | 2019-09-16 | 2019-09-13 | 2019-09-02 | 703300 | 703301 | 2536 HH - FLORENCE KAH Win10 Upgrade Project Equipment Request | Please ship 10 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 09/13/19. Ship to: ATTN: Kindred Implementation Services Tech 3242 Florence Boulevard Florence, AL 35634 | 1967737 | Yes | Yes | 2019
2492201 | 2492 HH - GILBERTOWN AL | 114 North Academy Ave | Butler | AL | 36904 | Butler, AL 36904 | 5 | 1 | 3 | 2019-09-30 | 2019-09-27 | 2019-09-16 | 703300 | 703301 | 2492 HH - GILBERTOWN AL KAH Win10 Upgrade Project Equipment Request | Please ship 5 UD3 Thin Client devices and 1 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 09/27/19. Ship to: ATTN: Kindred Implementation Services Tech 114 North Academy Ave Butler, AL 36904 | 1969948 | Yes | Yes | 2019
2490201 | 2490 HH - MERIDIAN MS | 2600 Old North Hills Street | Meridian | MS | 39305 | Meridian, MS 39305 | 10 | 1 | 9 | 2019-11-04 | 2019-11-01 | 2019-10-21 | 703300 | 703301 | 2490 HH - MERIDIAN MS KAH Win10 Upgrade Project Equipment Request | Please ship 10 UD3 Thin Client devices and 1 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 11/01/19. Ship to: ATTN: Kindred Implementation Services Tech 2600 Old North Hills Street Meridian, MS 39305 | 1975758 | Yes | Yes | 2019
2491201 | 2491 HH - PHILADELPHIA MS | 250 Canal Place | Philadelphia | MS | 39350 | Philadelphia, MS 39350 | 10 | 2 | 3 | 2019-11-04 | 2019-11-01 | 2019-10-21 | 703300 | 703301 | 2491 HH - PHILADELPHIA MS KAH Win10 Upgrade Project Equipment Request | Please ship 10 UD3 Thin Client devices and 2 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 11/01/19. Ship to: ATTN: Kindred Implementation Services Tech 250 Canal Place Philadelphia, MS 39350 | 1975762 | Yes | Yes | 2019
2493201 | 2493 HH - TUPELO | 3402 West Main St. | Tupelo | MS | 38801 | Tupelo, MS 38801 | 7 | 1 | 5 | 2019-11-04 | 2019-11-01 | 2019-10-21 | 703300 | 703301 | 2493 HH - TUPELO KAH Win10 Upgrade Project Equipment Request | Please ship 7 UD3 Thin Client devices and 1 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 11/01/19. Ship to: ATTN: Kindred Implementation Services Tech 3402 West Main St. Tupelo, MS 38801 | 1976567 | Yes | Yes | 2019
2496201 | 2496 HH - AMORY | 1225 Hwy 278 East | Amory | MS | 38821 | Amory, MS 38821 | 7 | 2 | 4 | 2019-11-04 | 2019-11-01 | 2019-10-21 | 703300 | 703301 | 2496 HH - AMORY KAH Win10 Upgrade Project Equipment Request | Please ship 7 UD3 Thin Client devices and 2 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 11/01/19. Ship to: ATTN: Kindred Implementation Services Tech 1225 Hwy 278 East Amory, MS 38821 | 1980965 | Yes | Yes | 2019
2497201 | 2497 HH - BOONEVILLE | 200 South Second St. | Booneville | MS | 38829 | Booneville, MS 38829 | 10 | 0 | 5 | 2019-11-04 | 2019-11-01 | 2019-10-21 | 703300 | 703301 | 2497 HH - BOONEVILLE KAH Win10 Upgrade Project Equipment Request | Please ship 10 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 11/01/19. Ship to: ATTN: Kindred Implementation Services Tech 200 South Second St. Booneville, MS 38829 | 1976598 | Yes | Yes | 2019
2498201 | 2498 HH - NEW ALBANY MS | 407 Doctors Dr. | New Albany | MS | 38652 | New Albany, MS 38652 | 6 | 1 | 4 | 2019-11-04 | 2019-11-01 | 2019-10-21 | 703300 | 703301 | 2498 HH - NEW ALBANY MS KAH Win10 Upgrade Project Equipment Request | Please ship 6 UD3 Thin Client devices and 1 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 11/01/19. Ship to: ATTN: Kindred Implementation Services Tech 407 Doctors Dr. New Albany, MS 38652 | 1976601 | Yes | Yes | 2019
2499201 | 2499 HH - RIPLEY MS | 902 North Main Street STE D | Ripley | MS | 38663 | Ripley, MS 38663 | 6 | 0 | 4 | 2019-11-04 | 2019-11-01 | 2019-10-21 | 703300 | 703301 | 2499 HH - RIPLEY MS KAH Win10 Upgrade Project Equipment Request | Please ship 6 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 11/01/19. Ship to: ATTN: Kindred Implementation Services Tech 902 North Main Street STE D Ripley, MS 38663 | 1976651 | Yes | Yes | 2019
2504201 | 2504 HH - VICKSBURG | 2080 S. Frontage Rd. STE 101 | Vicksburg | MS | 39180 | Vicksburg, MS 39180 | 7 | 0 | 3 | 2019-11-04 | 2019-11-01 | 2019-10-21 | 703300 | 703301 | 2504 HH - VICKSBURG KAH Win10 Upgrade Project Equipment Request | Please ship 7 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 11/01/19. Ship to: ATTN: Kindred Implementation Services Tech 2080 S. Frontage Rd. STE 101 Vicksburg, MS 39180 | 1980968 | Yes | Yes | 2019
2505201 | 2505 HH - MADISON | 1082 Gluckstadt Road STE B | Madison | MS | 39110 | Madison, MS 39110 | 3 | 0 | 2 | 2019-11-04 | 2019-11-01 | 2019-10-21 | 703300 | 703301 | 2505 HH - MADISON KAH Win10 Upgrade Project Equipment Request | Please ship 3 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 11/01/19. Ship to: ATTN: Kindred Implementation Services Tech 1082 Gluckstadt Road STE B Madison, MS 39110 | 1976655 | Yes | Yes | 2019
2506201 | 2506 HH - HAZLEHURST | 217 Caldwell Drive | Hazlehurst | MS | 39083 | Hazlehurst, MS 39083 | 5 | 0 | 3 | 2019-11-04 | 2019-11-01 | 2019-10-21 | 703300 | 703301 | 2506 HH - HAZLEHURST KAH Win10 Upgrade Project Equipment Request | Please ship 5 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 11/01/19. Ship to: ATTN: Kindred Implementation Services Tech 217 Caldwell Drive Hazlehurst, MS 39083 | 1976680 | Yes | Yes | 2019
2494201 | 2494 HH - COLUMBUS MS | 189 Park Creek Drive | Columbus | MS | 39705 | Columbus, MS 39705 | 8 | 1 | 6 | 2019-11-11 | 2019-11-08 | 2019-10-28 | 703300 | 703301 | 2494 HH - COLUMBUS MS KAH Win10 Upgrade Project Equipment Request | Please ship 8 UD3 Thin Client devices and 1 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 11/08/19. Ship to: ATTN: Kindred Implementation Services Tech 189 Park Creek Drive Columbus, MS 39705 | 1982282 | Yes | Yes | 2019
2507201 | 2507 HH - MORTON MS | 5325 Hwy 80 | Morton | MS | 39117 | Morton, MS 39117 | 6 | 0 | 7 | 2019-11-11 | 2019-11-08 | 2019-10-28 | 703300 | 703301 | 2507 HH - MORTON MS KAH Win10 Upgrade Project Equipment Request | Please ship 6 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 11/08/19. Ship to: ATTN: Kindred Implementation Services Tech 5325 Hwy 80 Morton, MS 39117 | 1982297 | Yes | Yes | 2019
2508201 | 2508 HH - MAGEE | 306 2nd Street SE | Magee | MS | 39111 | Magee, MS 39111 | 8 | 0 | 4 | 2019-11-11 | 2019-11-08 | 2019-10-28 | 703300 | 703301 | 2508 HH - MAGEE KAH Win10 Upgrade Project Equipment Request | Please ship 8 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 11/08/19. Ship to: ATTN: Kindred Implementation Services Tech 306 2nd Street SE Magee, MS 39111 | 1982299 | Yes | Yes | 2019
2479201 | 2479 HH - DAYTONA BEACH | 1717 North Clyde Morris Blvd. STE 140 | Daytona Beach | FL | 32117 | Daytona Beach, FL 32117 | 11 | 2 | 9 | 2019-11-11 | 2019-11-08 | 2019-10-28 | 703300 | 703301 | 2479 HH - DAYTONA BEACH KAH Win10 Upgrade Project Equipment Request | Please ship 11 UD3 Thin Client devices and 2 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 11/08/19. Ship to: ATTN: Kindred Implementation Services Tech 1717 North Clyde Morris Blvd. STE 140 Daytona Beach, FL 32117 | 1982328 | Yes | Yes | 2019
2480201 | 2480 HH - DELAND | 929 North Spring Garden Ave STE 100 | Deland | FL | 32720 | Deland, FL 32720 | 6 | 0 | 7 | 2019-11-11 | 2019-11-08 | 2019-10-28 | 703300 | 703301 | 2480 HH - DELAND KAH Win10 Upgrade Project Equipment Request | Please ship 6 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 11/08/19. Ship to: ATTN: Kindred Implementation Services Tech 929 North Spring Garden Ave STE 100 Deland, FL 32720 | 1982301 | Yes | Yes | 2019
2483201 | 2483 HH - ORANGE PARK | 350 Corporate Way STE 250 | Orange Park | FL | 32073 | Orange Park, FL 32073 | 0 | 0 | 0 | 2019-11-11 | 2019-11-08 | 2019-10-28 | 703300 | 703301 | 2483 HH - ORANGE PARK KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 11/08/19. Ship to: ATTN: Kindred Implementation Services Tech 350 Corporate Way STE 250 Orange Park, FL 32073 | 1982411 | Yes | Yes | 2019
2487201 | 2487 HH - OCALA | 311 SE 17th Place | Ocala | FL | 34471 | Ocala, FL 34471 | 14 | 6 | 6 | 2019-11-11 | 2019-11-08 | 2019-10-28 | 703300 | 703301 | 2487 HH - OCALA KAH Win10 Upgrade Project Equipment Request | Please ship 14 UD3 Thin Client devices and 6 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 11/08/19. Ship to: ATTN: Kindred Implementation Services Tech 311 SE 17th Place Ocala, FL 34471 | 1982305 | Yes | Yes | 2019
2488201 | 2488 HH - PALATKA-PUTNAM | 205 Zeagler Dr STE 401 | Palatka | FL | 32177 | Palatka, FL 32177 | 6 | 1 | 4 | 2019-11-11 | 2019-11-08 | 2019-10-28 | 703300 | 703301 | 2488 HH - PALATKA-PUTNAM KAH Win10 Upgrade Project Equipment Request | Please ship 6 UD3 Thin Client devices and 1 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 11/08/19. Ship to: ATTN: Kindred Implementation Services Tech 205 Zeagler Dr STE 401 Palatka, FL 32177 | 1982306 | Yes | Yes | 2019
2481201 | 2481 HH - GAINESVILLE | 3951 NW 48th Terrace STE 201 | Gainesville | FL | 32606 | Gainesville, FL 32606 | 10 | 0 | 9 | 2019-11-18 | 2019-11-15 | 2019-11-04 | 703300 | 703301 | 2481 HH - GAINESVILLE KAH Win10 Upgrade Project Equipment Request | Please ship 10 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 11/15/19. Ship to: ATTN: Kindred Implementation Services Tech 3951 NW 48th Terrace STE 201 Gainesville, FL 32606 | 1982665 | Yes | Yes | 2019
2489201 | 2489 HH - TALLAHASSEE | 2450 Tim Gamble Place | Tallahassee | FL | 32308 | Tallahassee, FL 32308 | 16 | 0 | 12 | 2019-11-18 | 2019-11-15 | 2019-11-04 | 703300 | 703301 | 2489 HH - TALLAHASSEE KAH Win10 Upgrade Project Equipment Request | Please ship 16 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 11/15/19. Ship to: ATTN: Kindred Implementation Services Tech 2450 Tim Gamble Place Tallahassee, FL 32308 | 1982934 | Yes | Yes | 2019
2484201 | 2484 HH - LIVE OAK | 712 Ohio Avenue South | Live Oak | FL | 32064 | Live Oak, FL 32064 | 6 | 0 | 3 | 2019-11-18 | 2019-11-15 | 2019-11-04 | 703300 | 703301 | 2484 HH - LIVE OAK KAH Win10 Upgrade Project Equipment Request | Please ship 6 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 11/15/19. Ship to: ATTN: Kindred Implementation Services Tech 712 Ohio Avenue South Live Oak, FL 32064 | 1982939 | Yes | Yes | 2019
2485201 | 2485 HH - LAKE CITY | 419 SW State Road 247 STE 109 | Lake City | FL | 32025 | Lake City, FL 32025 | 11 | 0 | 4 | 2019-11-18 | 2019-11-15 | 2019-11-04 | 703300 | 703301 | 2485 HH - LAKE CITY KAH Win10 Upgrade Project Equipment Request | Please ship 11 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 11/15/19. Ship to: ATTN: Kindred Implementation Services Tech 419 SW State Road 247 STE 109 Lake City, FL 32025 | 1982942 | Yes | Yes | 2019
2474201 | 2474 HH - MOBILE | 824 Western America Drive | Mobile | AL | 36609 | Mobile, AL 36609 | 11 | 1 | 10 | 2019-11-18 | 2019-11-15 | 2019-11-04 | 703300 | 703301 | 2474 HH - MOBILE KAH Win10 Upgrade Project Equipment Request | Please ship 11 UD3 Thin Client devices and 1 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 11/15/19. Ship to: ATTN: Kindred Implementation Services Tech 824 Western America Drive Mobile, AL 36609 | 1982943 | Yes | Yes | 2019
2477201 | 2477 HH - MARIANNA 2 | 2491 Commercial Park Dr. | Marianna | FL | 32448 | Marianna, FL 32448 | 28 | 4 | 24 | 2019-11-18 | 2019-11-15 | 2019-11-04 | 703300 | 703301 | 2477 HH - MARIANNA 2 KAH Win10 Upgrade Project Equipment Request | Please ship 28 UD3 Thin Client devices and 4 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 11/15/19. Ship to: ATTN: Kindred Implementation Services Tech 2491 Commercial Park Dr. Marianna, FL 32448 | 1982946 | Yes | Yes | 2019
2445201 | 2445 HH - ORLANDO SOUTH | 4776 New Broad St. STE 110 | Orlando | FL | 32814 | Orlando, FL 32814 | 22 | 1 | 12 | 2019-11-18 | 2019-11-15 | 2019-11-04 | 703300 | 703301 | 2445 HH - ORLANDO SOUTH KAH Win10 Upgrade Project Equipment Request | Please ship 22 UD3 Thin Client devices and 1 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 11/15/19. Ship to: ATTN: Kindred Implementation Services Tech 4776 New Broad St. STE 110 Orlando, FL 32814 | 1982953 | Yes | Yes | 2019
2495201 | 2495 HH - CALHOUN CITY | 200 South Pontotoc Drive, Suite A | Bruce | MS | 38915 | Bruce, MS 38915 | 8 | 0 | 5 | 2019-11-18 | 2019-11-15 | 2019-11-04 | 703300 | 703301 | 2495 HH - CALHOUN CITY KAH Win10 Upgrade Project Equipment Request | Please ship 8 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 11/15/19. Ship to: ATTN: Kindred Implementation Services Tech 200 South Pontotoc Drive, Suite A Bruce, MS 38915 | 1982284 | Yes | Yes | 2019 | Moved from wk of 11/11 (Adam resigned)
2502201 | 2502 HH - STARKVILLE MS | 1085 Stark Road STE 306 | Starkville | MS | 39759 | Starkville, MS 39759 | 7 | 2 | 5 | 2019-11-18 | 2019-11-15 | 2019-11-04 | 703300 | 703301 | 2502 HH - STARKVILLE MS KAH Win10 Upgrade Project Equipment Request | Please ship 7 UD3 Thin Client devices and 2 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 11/15/19. Ship to: ATTN: Kindred Implementation Services Tech 1085 Stark Road STE 306 Starkville, MS 39759 | 1982288 | Yes | Yes | 2019 | Moved from wk of 11/11 (Adam resigned)
2482201 | 2482 HH - TRENTON | 413 East Wade Street | Trenton | FL | 32693 | Trenton, FL 32693 | 11 | 3 | 2 | 2019-11-18 | 2019-11-15 | 2019-11-04 | 703300 | 703301 | 2482 HH - TRENTON KAH Win10 Upgrade Project Equipment Request | Please ship 11 UD3 Thin Client devices and 3 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 11/15/19. Ship to: ATTN: Kindred Implementation Services Tech 413 East Wade Street Trenton, FL 32693 | 1982936 | Yes | Yes | 2019 | Started wk of 11/18; scanner issue, added 3 laptops
2447201 | 2447 HH - APOPKA | 527 Wekiva Commons Circle | Apopka | FL | 32712 | Apopka, FL 32712 | 5 | 0 | 3 | 2019-12-02 | 2019-11-29 | 2019-11-18 | 703300 | 703301 | 2447 HH - APOPKA KAH Win10 Upgrade Project Equipment Request | Please ship 5 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 11/29/19. Ship to: ATTN: Kindred Implementation Services Tech 527 Wekiva Commons Circle Apopka, FL 32712 | 1984932 | Yes | Yes | 2019
2446201 | 2446 HH - KISSIMMEE | 3296 North Greenwald Way | Kissimmee | FL | 34741 | Kissimmee, FL 34741 | 8 | 0 | 2 | 2019-12-02 | 2019-11-29 | 2019-11-18 | 703300 | 703301 | 2446 HH - KISSIMMEE KAH Win10 Upgrade Project Equipment Request | Please ship 8 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 11/29/19. Ship to: ATTN: Kindred Implementation Services Tech 3296 North Greenwald Way Kissimmee, FL 34741 | 1984935 | Yes | Yes | 2019
2455201 | 2455 HH - BRADENTON EAST | 101 Riverfront Blvd STE 400 | Bradenton | FL | 34205 | Bradenton, FL 34205 | 10 | 3 | 8 | 2019-12-02 | 2019-11-29 | 2019-11-18 | 703300 | 703301 | 2455 HH - BRADENTON EAST KAH Win10 Upgrade Project Equipment Request | Please ship 10 UD3 Thin Client devices and 3 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 11/29/19. Ship to: ATTN: Kindred Implementation Services Tech 101 Riverfront Blvd STE 400 Bradenton, FL 34205 | 1984940 | Yes | Yes | 2019
2454201 | 2454 HH - SARASOTA | 2601 Cattlemen Road STE 102 | Sarasota | FL | 34232 | Sarasota, FL 34232 | 10 | 0 | 9 | 2019-12-02 | 2019-11-29 | 2019-11-18 | 703300 | 703301 | 2454 HH - SARASOTA KAH Win10 Upgrade Project Equipment Request | Please ship 10 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 11/29/19. Ship to: ATTN: Kindred Implementation Services Tech 2601 Cattlemen Road STE 102 Sarasota, FL 34232 | 1984964 | Yes | Yes | 2019
2441201 | 2441 HH - LAKELAND | 3671 Innovation Drive | Lakeland | FL | 33812 | Lakeland, FL 33812 | 10 | 0 | 7 | 2019-12-02 | 2019-11-29 | 2019-11-18 | 703300 | 703301 | 2441 HH - LAKELAND KAH Win10 Upgrade Project Equipment Request | Please ship 10 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 11/29/19. Ship to: ATTN: Kindred Implementation Services Tech 3671 Innovation Drive Lakeland, FL 33812 | 1985029 | Yes | Yes | 2019
2503201 | 2503 HH - JACKSON MS | 106 Riverview Drive | Flowood | MS | 39232 | Flowood, MS 39232 | 15 | 0 | 5 | 2019-12-16 | 2019-12-13 | 2019-12-02 | 703300 | 703301 | 2503 HH - JACKSON MS KAH Win10 Upgrade Project Equipment Request | Please ship 15 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 12/13/19. Ship to: ATTN: Kindred Implementation Services Tech 106 Riverview Drive Flowood, MS 39232 | 1982292/1984573 | Yes | Yes | 2019 | Started wk of 11/11; IGELs delayed
2470201 | 2470 HH - DAPHNE | 9037 Independence Avenue STE B | Daphne | AL | 36526 | Daphne, AL 36526 | 15 | 7 | 4 | 2019-12-16 | 2019-12-13 | 2019-12-02 | 703300 | 703301 | 2470 HH - DAPHNE KAH Win10 Upgrade Project Equipment Request | Please ship 15 UD3 Thin Client devices and 7 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 12/13/19. Ship to: ATTN: Kindred Implementation Services Tech 9037 Independence Avenue STE B Daphne, AL 36526 | 1982948 | Yes | Yes | 2019 | Started wk of 11/18; scanner issue, added 6 laptops
7019201 | 7019 HH - FOLEY | 1628 N McKenzie St STE 101 | Foley | AL | 36535 | Foley, AL 36535 | 9 | 6 | 2 | 2019-12-16 | 2019-12-13 | 2019-12-02 | 703300 | 703301 | 7019 HH - FOLEY KAH Win10 Upgrade Project Equipment Request | Please ship 9 UD3 Thin Client devices and 6 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 12/13/19. Ship to: ATTN: Kindred Implementation Services Tech 1628 N McKenzie St STE 101 Foley, AL 36535 | 1982950 | Yes | Yes | 2019 | Started wk of 11/18; scanner issue, added 2 laptops, + Luke Retherford
2442201 | 2442 HH - VIERA | 8247 Devereux Drive STE 103 | Melbourne | FL | 32940 | Melbourne, FL 32940 | 10 | 2 | 2 | 2019-12-16 | 2019-12-13 | 2019-12-02 | 703300 | 703301 | 2442 HH - VIERA KAH Win10 Upgrade Project Equipment Request | Please ship 10 UD3 Thin Client devices and 2 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 12/13/19. Ship to: ATTN: Kindred Implementation Services Tech 8247 Devereux Drive STE 103 Melbourne, FL 32940 | 1986640 | Yes | Yes | 2019
2444201 | 2444 HH - PALM BAY | 2080 W Eau Gallie Blvd STE B | Melbourne | FL | 32935 | Melbourne, FL 32935 | 10 | 4 | 1 | 2019-12-16 | 2019-12-13 | 2019-12-02 | 703300 | 703301 | 2444 HH - PALM BAY KAH Win10 Upgrade Project Equipment Request | Please ship 10 UD3 Thin Client devices and 4 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 12/13/19. Ship to: ATTN: Kindred Implementation Services Tech 2080 W Eau Gallie Blvd STE B Melbourne, FL 32935 | 1986641 | Yes | Yes | 2019
2452201 | 2452 HH - TAMPA | 4511 North Himes Ave STE 240 | Tampa | FL | 33614 | Tampa, FL 33614 | 10 | 0 | 9 | 2019-12-16 | 2019-12-13 | 2019-12-02 | 703300 | 703301 | 2452 HH - TAMPA KAH Win10 Upgrade Project Equipment Request | Please ship 10 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 12/13/19. Ship to: ATTN: Kindred Implementation Services Tech 4511 North Himes Ave STE 240 Tampa, FL 33614 | 1986643 | Yes | Yes | 2019
6957097 | A110 Southest Central Intake | 4511 North Himes Ave, STE 240 | Tampa | FL | 33614 | Tampa, FL 33614 | 9 | 3 | 0 | 2019-12-16 | 2019-12-13 | 2019-12-02 | 703300 | 703301 | A110 Southest Central Intake KAH Win10 Upgrade Project Equipment Request | Please ship 9 UD3 Thin Client devices and 3 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 12/13/19. Ship to: ATTN: Kindred Implementation Services Tech 4511 North Himes Ave, STE 240 Tampa, FL 33614 | 1986979 | Yes | Yes | 2019
2532201 | 2532 HH - ANNISTON | 1328 Greenbrier Dear Road | Anniston | AL | 36207 | Anniston, AL 36207 | 8 | 1 | 1 | 2019-12-16 | 2019-12-13 | 2019-12-02 | 703300 | 703301 | 2532 HH - ANNISTON KAH Win10 Upgrade Project Equipment Request | Please ship 8 UD3 Thin Client devices and 1 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 12/13/19. Ship to: ATTN: Kindred Implementation Services Tech 1328 Greenbrier Dear Road Anniston, AL 36207 | 1986983 | Yes | Yes | 2019
2535201 | 2535 HH - RAINBOW CITY | 3225 Rainbow Drive STE 256 | Rainbow City | AL | 35906 | Rainbow City, AL 35906 | 13 | 1 | 7 | 2019-12-16 | 2019-12-13 | 2019-12-02 | 703300 | 703301 | 2535 HH - RAINBOW CITY KAH Win10 Upgrade Project Equipment Request | Please ship 13 UD3 Thin Client devices and 1 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 12/13/19. Ship to: ATTN: Kindred Implementation Services Tech 3225 Rainbow Drive STE 256 Rainbow City, AL 35906 | 1987007 | Yes | Yes | 2019
2540201 | 2540 HH - MUSCLE SHOALS | 716 State Street | Muscle Shoals | AL | 35661 | Muscle Shoals, AL 35661 | 8 | 1 | 4 | 2019-12-16 | 2019-12-13 | 2019-12-02 | 703300 | 703301 | 2540 HH - MUSCLE SHOALS KAH Win10 Upgrade Project Equipment Request | Please ship 8 UD3 Thin Client devices and 1 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 12/13/19. Ship to: ATTN: Kindred Implementation Services Tech 716 State Street Muscle Shoals, AL 35661 | 1986988 | Yes | Yes | 2019
2538201 | 2538 HH - RUSSELLVILLE | 12200 Highway 43 Bypass | Russellville | AL | 35653 | Russellville, AL 35653 | 12 | 0 | 5 | 2019-12-16 | 2019-12-13 | 2019-12-02 | 703300 | 703301 | 2538 HH - RUSSELLVILLE KAH Win10 Upgrade Project Equipment Request | Please ship 12 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 12/13/19. Ship to: ATTN: Kindred Implementation Services Tech 12200 Highway 43 Bypass Russellville, AL 35653 | 1986999 | Yes | Yes | 2019
2543201 | 2543 HH - JASPER | 1458 Jones Dairy Road STE 100 | Jasper | AL | 35501 | Jasper, AL 35501 | 10 | 0 | 3 | 2019-12-16 | 2019-12-13 | 2019-12-02 | 703300 | 703301 | 2543 HH - JASPER KAH Win10 Upgrade Project Equipment Request | Please ship 10 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 12/13/19. Ship to: ATTN: Kindred Implementation Services Tech 1458 Jones Dairy Road STE 100 Jasper, AL 35501 | 1987013 | Yes | Yes | 2019
2542201 | 2542 HH - CULLMAN | 1015 1st Ave SW STE A | Cullman | AL | 35055 | Cullman, AL 35055 | 7 | 0 | 2 | 2019-12-16 | 2019-12-13 | 2019-12-02 | 703300 | 703301 | 2542 HH - CULLMAN KAH Win10 Upgrade Project Equipment Request | Please ship 7 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 12/13/19. Ship to: ATTN: Kindred Implementation Services Tech 1015 1st Ave SW STE A Cullman, AL 35055 | 1987017 | Yes | Yes | 2019
2541201 | 2541 HH - HUNTSVILLE | 7067 Old Madison Pike NW STE 105 | Huntsville | AL | 35806 | Huntsville, AL 35806 | 12 | 3 | 11 | 2019-12-16 | 2019-12-13 | 2019-12-02 | 703300 | 703301 | 2541 HH - HUNTSVILLE KAH Win10 Upgrade Project Equipment Request | Please ship 12 UD3 Thin Client devices and 3 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 12/13/19. Ship to: ATTN: Kindred Implementation Services Tech 7067 Old Madison Pike NW STE 105 Huntsville, AL 35806 | 1987019 | Yes | Yes | 2019
2583201 | 2583 HH - WACO - HARDEN | 5400 Bosque Boulevard STE 245 | Waco | TX | 76710 | Waco, TX 76710 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | 703300 | 703301 | 2583 HH - WACO - HARDEN KAH Win10 Upgrade Project Equipment Request | #VALUE! |  | No | 0 | 2020
2539201 | 2539 HH - ATHENS AL | 905A South Clinton Street | Athens | AL | 35611 | Athens, AL 35611 | 7 | 1 | 2 | 2020-01-06 | 2020-01-03 | 2019-12-23 | 703300 | 703301 | 2539 HH - ATHENS AL KAH Win10 Upgrade Project Equipment Request | Please ship 7 UD3 Thin Client devices and 1 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/03/20. Ship to: ATTN: Kindred Implementation Services Tech 905A South Clinton Street Athens, AL 35611 | 1988117 | No | Yes | 2020
2537201 | 2537 HH - MOULTON | 20 Almon Drive STE C | Moulton | AL | 35650 | Moulton, AL 35650 | 8 | 0 | 3 | 2020-01-06 | 2020-01-03 | 2019-12-23 | 703300 | 703301 | 2537 HH - MOULTON KAH Win10 Upgrade Project Equipment Request | Please ship 8 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/03/20. Ship to: ATTN: Kindred Implementation Services Tech 20 Almon Drive STE C Moulton, AL 35650 | 1988119 | No | No | 2020
2524201 | 2524 HH - SYLACAUGA | 1025 West Fort Williams St. | Sylacauga | AL | 35150 | Sylacauga, AL 35150 | 7 | 0 | 1 | 2020-01-06 | 2020-01-03 | 2019-12-23 | 703300 | 703301 | 2524 HH - SYLACAUGA KAH Win10 Upgrade Project Equipment Request | Please ship 7 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/03/20. Ship to: ATTN: Kindred Implementation Services Tech 1025 West Fort Williams St. Sylacauga, AL 35150 | 1988122 | No | Yes | 2020
2527201 | 2527 HH - PELL CITY | 614 Martin Street North | Pell City | AL | 35125 | Pell City, AL 35125 | 8 | 0 | 2 | 2020-01-06 | 2020-01-03 | 2019-12-23 | 703300 | 703301 | 2527 HH - PELL CITY KAH Win10 Upgrade Project Equipment Request | Please ship 8 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/03/20. Ship to: ATTN: Kindred Implementation Services Tech 614 Martin Street North Pell City, AL 35125 | 1988124 | No | Yes | 2020
2510201 | 2510 HH - ENTERPRISE | 1239 Rucker Blvd. | Enterprise | AL | 36330 | Enterprise, AL 36330 | 17 | 4 | 1 | 2020-01-06 | 2020-01-03 | 2019-12-23 | 703300 | 703301 | 2510 HH - ENTERPRISE KAH Win10 Upgrade Project Equipment Request | Please ship 17 UD3 Thin Client devices and 4 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/03/20. Ship to: ATTN: Kindred Implementation Services Tech 1239 Rucker Blvd. Enterprise, AL 36330 | 1988125 | No | Yes | 2020
2509201 | 2509 HH - ANDALUSIA | 1309 Antioch Road | Andalusia | AL | 36420 | Andalusia, AL 36420 | 8 | 0 | 3 | 2020-01-06 | 2020-01-03 | 2019-12-23 | 703300 | 703301 | 2509 HH - ANDALUSIA KAH Win10 Upgrade Project Equipment Request | Please ship 8 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/03/20. Ship to: ATTN: Kindred Implementation Services Tech 1309 Antioch Road Andalusia, AL 36420 | 1988126 | No | Yes | 2020
2511201 | 2511 HH - GENEVA | 1204 W. Magnolia Ave | Geneva | AL | 36340 | Geneva, AL 36340 | 7 | 0 | 3 | 2020-01-06 | 2020-01-03 | 2019-12-23 | 703300 | 703301 | 2511 HH - GENEVA KAH Win10 Upgrade Project Equipment Request | Please ship 7 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/03/20. Ship to: ATTN: Kindred Implementation Services Tech 1204 W. Magnolia Ave Geneva, AL 36340 | 1988128 | No | Yes | 2020
2531201 | 2531 HH - MONTGOMERY | 11123 Chantilly Parkway, Unit L | Pike Road | AL | 36064 | Pike Road, AL 36064 | 21 | 7 | 9 | 2020-01-06 | 2020-01-03 | 2019-12-23 | 703300 | 703301 | 2531 HH - MONTGOMERY KAH Win10 Upgrade Project Equipment Request | Please ship 21 UD3 Thin Client devices and 7 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/03/20. Ship to: ATTN: Kindred Implementation Services Tech 11123 Chantilly Parkway, Unit L Pike Road, AL 36064 | 1988129 | No | Yes | 2020
2526201 | 2526 HH - CLANTON | 118 6th Street South | Clanton | AL | 35045 | Clanton, AL 35045 | 6 | 1 | 3 | 2020-01-06 | 2020-01-03 | 2019-12-23 | 703300 | 703301 | 2526 HH - CLANTON KAH Win10 Upgrade Project Equipment Request | Please ship 6 UD3 Thin Client devices and 1 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/03/20. Ship to: ATTN: Kindred Implementation Services Tech 118 6th Street South Clanton, AL 35045 | 1988133 | No | Yes | 2020
2529201 | 2529 HH - SELMA | 200 Central Park Place | Selma | AL | 36701 | Selma, AL 36701 | 12 | 0 | 4 | 2020-01-06 | 2020-01-03 | 2019-12-23 | 703300 | 703301 | 2529 HH - SELMA KAH Win10 Upgrade Project Equipment Request | Please ship 12 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/03/20. Ship to: ATTN: Kindred Implementation Services Tech 200 Central Park Place Selma, AL 36701 | 1988134 | No | Yes | 2020
3807201 | 3807 HH - THOMASVILLE | 16820 US Highway 19 N | Thomasville | GA | 31757 | Thomasville, GA 31757 | 8 | 1 | 6 | 2020-01-06 | 2020-01-03 | 2019-12-23 | 703300 | 703301 | 3807 HH - THOMASVILLE KAH Win10 Upgrade Project Equipment Request | Please ship 8 UD3 Thin Client devices and 1 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/03/20. Ship to: ATTN: Kindred Implementation Services Tech 16820 US Highway 19 N Thomasville, GA 31757 | 1988136 | No | Yes | 2020
2513201 | 2513 HH - BAINBRIDGE GA | 430 East Shotwell Street | Bainbridge | GA | 39819 | Bainbridge, GA 39819 | 11 | 4 | 4 | 2020-01-06 | 2020-01-03 | 2019-12-23 | 703300 | 703301 | 2513 HH - BAINBRIDGE GA KAH Win10 Upgrade Project Equipment Request | Please ship 11 UD3 Thin Client devices and 4 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/03/20. Ship to: ATTN: Kindred Implementation Services Tech 430 East Shotwell Street Bainbridge, GA 39819 | 1988141 | No | Yes | 2020
2525201 | 2525 HH - BIRMINGHAM | 2100 Riverchase Center Bldg 400 STE 450 | Hoover | AL | 35244 | Hoover, AL 35244 | 7 | 5 | 5 | 2020-01-06 | 2020-01-03 | 2019-12-23 | 703300 | 703301 | 2525 HH - BIRMINGHAM KAH Win10 Upgrade Project Equipment Request | Please ship 7 UD3 Thin Client devices and 5 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/03/20. Ship to: ATTN: Kindred Implementation Services Tech 2100 Riverchase Center Bldg 400 STE 450 Hoover, AL 35244 | 1988143 | No | Yes | 2020
2459201 | 2459 HH - PHENIX CITY | River Chase Office Park, 5009 River Chase Dr., Bldg 100 STE D | Phenix City | AL | 36867 | Phenix City, AL 36867 | 3 | 1 | 3 | 2020-01-13 | 2020-01-10 | 2019-12-30 | 703300 | 703301 | 2459 HH - PHENIX CITY KAH Win10 Upgrade Project Equipment Request | Please ship 3 UD3 Thin Client devices and 1 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/10/20. Ship to: ATTN: Kindred Implementation Services Tech River Chase Office Park, 5009 River Chase Dr., Bldg 100 STE D Phenix City, AL 36867 | 1988841 | No | Yes | 2020
2514201 | 2514 HH - TRUSSVILLE | 2100 Southbridge Parkway STE 480 | Birmingham | AL | 35209 | Birmingham, AL 35209 | 12 | 0 | 6 | 2020-01-13 | 2020-01-10 | 2019-12-30 | 703300 | 703301 | 2514 HH - TRUSSVILLE KAH Win10 Upgrade Project Equipment Request | Please ship 12 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/10/20. Ship to: ATTN: Kindred Implementation Services Tech 2100 Southbridge Parkway STE 480 Birmingham, AL 35209 | 1988843 | No | Yes | 2020
2383201 | 2383 HH - CEDAR RAPIDS | 1305 Boyson Loop Suite B | Hiawatha | IA | 52233 | Hiawatha, IA 52233 | 6 | 0 | 5 | 2020-01-13 | 2020-01-10 | 2019-12-30 | 703300 | 703301 | 2383 HH - CEDAR RAPIDS KAH Win10 Upgrade Project Equipment Request | Please ship 6 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/10/20. Ship to: ATTN: Kindred Implementation Services Tech 1305 Boyson Loop Suite B Hiawatha, IA 52233 | 1988846 | No | Yes | 2020
2644201 | 2644 HH - MESA AZ | 1910 South Stapely Drive STE 107 | Mesa | AZ | 85204 | Mesa, AZ 85204 | 11 | 2 | 10 | 2020-01-13 | 2020-01-10 | 2019-12-30 | 703300 | 703301 | 2644 HH - MESA AZ KAH Win10 Upgrade Project Equipment Request | Please ship 11 UD3 Thin Client devices and 2 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/10/20. Ship to: ATTN: Kindred Implementation Services Tech 1910 South Stapely Drive STE 107 Mesa, AZ 85204 | 1988851 | No | Yes | 2020
2640201 | 2640 HH - PHOENIX - CENTRAL | 14050 North 83rd Avenue STE 150 | Peoria | AZ | 85381 | Peoria, AZ 85381 | 7 | 1 | 7 | 2020-01-13 | 2020-01-10 | 2019-12-30 | 703300 | 703301 | 2640 HH - PHOENIX - CENTRAL KAH Win10 Upgrade Project Equipment Request | Please ship 7 UD3 Thin Client devices and 1 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/10/20. Ship to: ATTN: Kindred Implementation Services Tech 14050 North 83rd Avenue STE 150 Peoria, AZ 85381 | 1989188 | No | Yes | 2020
7023201 | 7023 HH - RENO (fka 2603) | 5424 Louie Lane STE B | Reno | NV | 89511 | Reno, NV 89511 | 15 | 1 | 13 | 2020-01-13 | 2020-01-10 | 2019-12-30 | 703300 | 703301 | 7023 HH - RENO (fka 2603) KAH Win10 Upgrade Project Equipment Request | Please ship 15 UD3 Thin Client devices and 1 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/10/20. Ship to: ATTN: Kindred Implementation Services Tech 5424 Louie Lane STE B Reno, NV 89511 | 1988958 | No | Yes | 2020
7025201 | 7025 HH - FERNLEY | 415 Highway 95A South STE F-604 | Fernley | NV | 89408 | Fernley, NV 89408 | 11 | 0 | 2 | 2020-01-13 | 2020-01-10 | 2019-12-30 | 703300 | 703301 | 7025 HH - FERNLEY KAH Win10 Upgrade Project Equipment Request | Please ship 11 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/10/20. Ship to: ATTN: Kindred Implementation Services Tech 415 Highway 95A South STE F-604 Fernley, NV 89408 | 1988961 | No | Yes | 2020
2380201 | 2380 HH - ROCK ISLAND | 1600 Fourth Ave STE 201 | Rock Island | IL | 61201 | Rock Island, IL 61201 | 7 | 2 | 3 | 2020-01-13 | 2020-01-10 | 2019-12-30 | 703300 | 703301 | 2380 HH - ROCK ISLAND KAH Win10 Upgrade Project Equipment Request | Please ship 7 UD3 Thin Client devices and 2 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/10/20. Ship to: ATTN: Kindred Implementation Services Tech 1600 Fourth Ave STE 201 Rock Island, IL 61201 | 1988963 | No | Yes | 2020
7024201 | 7024 HH - CARSON CITY | 725 Basque Way STE 3 | Carson City | NV | 89706 | Carson City, NV 89706 | 14 | 0 | 2 | 2020-01-13 | 2020-01-10 | 2019-12-30 | 703300 | 703301 | 7024 HH - CARSON CITY KAH Win10 Upgrade Project Equipment Request | Please ship 14 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/10/20. Ship to: ATTN: Kindred Implementation Services Tech 725 Basque Way STE 3 Carson City, NV 89706 | 1988964 | No | Yes | 2020
2643201 | 2643 HH - SCOTTSDALE | 16620 North 40th Street STE D4 | Phoenix | AZ | 85032 | Phoenix, AZ 85032 | 10 | 3 | 2 | 2020-01-13 | 2020-01-10 | 2019-12-30 | 703300 | 703301 | 2643 HH - SCOTTSDALE KAH Win10 Upgrade Project Equipment Request | Please ship 10 UD3 Thin Client devices and 3 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/10/20. Ship to: ATTN: Kindred Implementation Services Tech 16620 North 40th Street STE D4 Phoenix, AZ 85032 | 1988965 | No | Yes | 2020
2650201 | 2650 HH - TUCSON | 5255 E. Williams Circle STE 6400 | Tucson | AZ | 85711 | Tucson, AZ 85711 | 17 | 0 | 6 | 2020-01-13 | 2020-01-10 | 2019-12-30 | 703300 | 703301 | 2650 HH - TUCSON KAH Win10 Upgrade Project Equipment Request | Please ship 17 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/10/20. Ship to: ATTN: Kindred Implementation Services Tech 5255 E. Williams Circle STE 6400 Tucson, AZ 85711 | 1988966/1989189 | Yes | Yes | 2020 | Added 1 IGEL on 1/2/2020
2528201 | 2528 HH - PRATTVILLE | 1988 Fairview Avenue | Prattville | AL | 36066 | Prattville, AL 36066 | 14 | 1 | 4 | 2020-01-20 | 2020-01-17 | 2020-01-06 | 703300 | 703301 | 2528 HH - PRATTVILLE KAH Win10 Upgrade Project Equipment Request | Please ship 14 UD3 Thin Client devices and 1 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/17/20. Ship to: ATTN: Kindred Implementation Services Tech 1988 Fairview Avenue Prattville, AL 36066 | 1990217 | No | Yes | 2020
2512201 | 2512 HH - DOTHAN 2 | 2740 Headland Avenue | Dothan | AL | 36303 | Dothan, AL 36303 | 10 | 0 | 10 | 2020-01-20 | 2020-01-17 | 2020-01-06 | 703300 | 703301 | 2512 HH - DOTHAN 2 KAH Win10 Upgrade Project Equipment Request | Please ship 10 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/17/20. Ship to: ATTN: Kindred Implementation Services Tech 2740 Headland Avenue Dothan, AL 36303 | 1990272 | No | Yes | 2020
2397201 | 2397 HH - INDIANAPOLIS NORTH | 8606 Allisonville Rd STE 350 | Indianapolis | IN | 46250 | Indianapolis, IN 46250 | 10 | 2 | 10 | 2020-01-20 | 2020-01-17 | 2020-01-06 | 703300 | 703301 | 2397 HH - INDIANAPOLIS NORTH KAH Win10 Upgrade Project Equipment Request | Please ship 10 UD3 Thin Client devices and 2 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/17/20. Ship to: ATTN: Kindred Implementation Services Tech 8606 Allisonville Rd STE 350 Indianapolis, IN 46250 | 1990274 | Yes | Yes | 2020 | Added 2 laptops because inventory was incomplete
2433201 | 2433 HH - INDIANAPOLIS SOUTH | 701 East County Line Road STE 205 | Greenwood | IN | 46143 | Greenwood, IN 46143 | 5 | 0 | 4 | 2020-01-20 | 2020-01-17 | 2020-01-06 | 703300 | 703301 | 2433 HH - INDIANAPOLIS SOUTH KAH Win10 Upgrade Project Equipment Request | Please ship 5 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/17/20. Ship to: ATTN: Kindred Implementation Services Tech 701 East County Line Road STE 205 Greenwood, IN 46143 | 1990275 | No | Yes | 2020
7010201 | 7010 HH - MUNCIE | 400 N High Street STE 202 | Muncie | IN | 47305 | Muncie, IN 47305 | 7 | 3 | 2 | 2020-01-20 | 2020-01-17 | 2020-01-06 | 703300 | 703301 | 7010 HH - MUNCIE KAH Win10 Upgrade Project Equipment Request | Please ship 7 UD3 Thin Client devices and 3 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/17/20. Ship to: ATTN: Kindred Implementation Services Tech 400 N High Street STE 202 Muncie, IN 47305 | 1990276 | No | Yes | 2020 | Add 1 laptop for scanner
2387201 | 2387 HH - ST PAUL - ROSEVILLE | 1970 Oakcrest Avenue STE 107 | Roseville | MN | 55113 | Roseville, MN 55113 | 4 | 6 | 5 | 2020-01-20 | 2020-01-17 | 2020-01-06 | 703300 | 703301 | 2387 HH - ST PAUL - ROSEVILLE KAH Win10 Upgrade Project Equipment Request | Please ship 4 UD3 Thin Client devices and 6 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/17/20. Ship to: ATTN: Kindred Implementation Services Tech 1970 Oakcrest Avenue STE 107 Roseville, MN 55113 | 1990278 | No | Yes | 2020 | Add 3 laptop for scanner
2392201 | 2392 HH - ST PAUL - MAPLE GROVE | 7101 Northland Circle STE 5101 | Brooklyn Park | MN | 55428 | Brooklyn Park, MN 55428 | 4 | 5 | 3 | 2020-01-20 | 2020-01-17 | 2020-01-06 | 703300 | 703301 | 2392 HH - ST PAUL - MAPLE GROVE KAH Win10 Upgrade Project Equipment Request | Please ship 4 UD3 Thin Client devices and 5 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/17/20. Ship to: ATTN: Kindred Implementation Services Tech 7101 Northland Circle STE 5101 Brooklyn Park, MN 55428 | 1990279 | No | Yes | 2020 | Add 2 laptop for scanner
2389201 | 2389 HH - DULUTH | 925 East Superior St STE 104 | Duluth | MN | 55802 | Duluth, MN 55802 | 5 | 3 | 5 | 2020-01-20 | 2020-01-17 | 2020-01-06 | 703300 | 703301 | 2389 HH - DULUTH KAH Win10 Upgrade Project Equipment Request | Please ship 5 UD3 Thin Client devices and 3 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/17/20. Ship to: ATTN: Kindred Implementation Services Tech 925 East Superior St STE 104 Duluth, MN 55802 | 1990280 | No | Yes | 2020
2391201 | 2391 HH - ST PAUL - BLOOMINGTON | 7900 W 78th Street STE 180 | Edina | MN | 55439 | Edina, MN 55439 | 8 | 6 | 8 | 2020-01-20 | 2020-01-17 | 2020-01-06 | 703300 | 703301 | 2391 HH - ST PAUL - BLOOMINGTON KAH Win10 Upgrade Project Equipment Request | Please ship 8 UD3 Thin Client devices and 6 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/17/20. Ship to: ATTN: Kindred Implementation Services Tech 7900 W 78th Street STE 180 Edina, MN 55439 | 1990282 | Yes | Yes | 2020 | Add 4 laptops for scanners
2632201 | 2632 HH - GRAND JUNCTION | 2764 Compass Drive STE 108B | Grand Junction | CO | 81506 | Grand Junction, CO 81506 | 5 | 0 | 3 | 2020-01-20 | 2020-01-17 | 2020-01-06 | 703300 | 703301 | 2632 HH - GRAND JUNCTION KAH Win10 Upgrade Project Equipment Request | Please ship 5 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/17/20. Ship to: ATTN: Kindred Implementation Services Tech 2764 Compass Drive STE 108B Grand Junction, CO 81506 | 1990283 | No | Yes | 2020
2634201 | 2634 HH - COLORADO SPRINGS | 5755 Mark Dabling Blvd. STE 325 | Colorado Springs | CO | 80919 | Colorado Springs, CO 80919 | 6 | 1 | 4 | 2020-01-20 | 2020-01-17 | 2020-01-06 | 703300 | 703301 | 2634 HH - COLORADO SPRINGS KAH Win10 Upgrade Project Equipment Request | Please ship 6 UD3 Thin Client devices and 1 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/17/20. Ship to: ATTN: Kindred Implementation Services Tech 5755 Mark Dabling Blvd. STE 325 Colorado Springs, CO 80919 | 1990284 | No | Yes | 2020
2638201 | 2638 HH - PUEBLO | 1315 Fortino Boulevard Suite A | Pueblo | CO | 81008 | Pueblo, CO 81008 | 5 | 5 | 3 | 2020-01-20 | 2020-01-17 | 2020-01-06 | 703300 | 703301 | 2638 HH - PUEBLO KAH Win10 Upgrade Project Equipment Request | Please ship 5 UD3 Thin Client devices and 5 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/17/20. Ship to: ATTN: Kindred Implementation Services Tech 1315 Fortino Boulevard Suite A Pueblo, CO 81008 | 1990285 | Yes | Yes | 2020 | Add 3 laptops for scanners
7028201 | 7028 HH - NORTH SPOKANE | 8502 North Nevada STE 2 | Spokane | WA | 99208 | Spokane, WA 99208 | 11 | 1 | 2 | 2020-01-20 | 2020-01-17 | 2020-01-06 | 703300 | 703301 | 7028 HH - NORTH SPOKANE KAH Win10 Upgrade Project Equipment Request | Please ship 11 UD3 Thin Client devices and 1 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/17/20. Ship to: ATTN: Kindred Implementation Services Tech 8502 North Nevada STE 2 Spokane, WA 99208 | 1990286 | No | Yes | 2020
5015201 | 5015 HH - LIBERTY LAKE | 22820 E. Appleway Ave | Liberty Lake | WA | 99019 | Liberty Lake, WA 99019 | 24 | 7 | 5 | 2020-01-20 | 2020-01-17 | 2020-01-06 | 703300 | 703301 | 5015 HH - LIBERTY LAKE KAH Win10 Upgrade Project Equipment Request | Please ship 24 UD3 Thin Client devices and 7 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/17/20. Ship to: ATTN: Kindred Implementation Services Tech 22820 E. Appleway Ave Liberty Lake, WA 99019 | 1990287 | No | Yes | 2020
7029201 | 7029 HH - COEUR D'ALENE ID (fka 2984) | 1230 N NORTHWOOD CENTER CT, Suite C | Coeur D Alene | ID | 83814 | Coeur D Alene, ID 83814 | 7 | 0 | 3 | 2020-01-20 | 2020-01-17 | 2020-01-06 | 703300 | 703301 | 7029 HH - COEUR D'ALENE ID (fka 2984) KAH Win10 Upgrade Project Equipment Request | Please ship 7 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/17/20. Ship to: ATTN: Kindred Implementation Services Tech 1230 N NORTHWOOD CENTER CT, Suite C Coeur D Alene, ID 83814 | 1990288 | No | Yes | 2020
5016201 | 5016 HH - PULLMAN | 1610 NE Eastgate Blvd STE 650 | Pullman | WA | 99163 | Pullman, WA 99163 | 6 | 2 | 1 | 2020-01-20 | 2020-01-17 | 2020-01-06 | 703300 | 703301 | 5016 HH - PULLMAN KAH Win10 Upgrade Project Equipment Request | Please ship 6 UD3 Thin Client devices and 2 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/17/20. Ship to: ATTN: Kindred Implementation Services Tech 1610 NE Eastgate Blvd STE 650 Pullman, WA 99163 | 1990289 | No | Yes | 2020
3776201 | 3776 HH - KOKOMO, IN (closed) | 2130 Sycamore St. STE 240 | Kokomo | IN | 46901 | Kokomo, IN 46901 | 0 | 0 | 0 | 0 | #NUM! | -14 | 703300 | 703301 | 3776 HH - KOKOMO, IN (closed) KAH Win10 Upgrade Project Equipment Request | #NUM! |  | No | 0 | 2020
2544201 | 2544 HH - COLUMBIA MO | 2404 Forum Boulevard STE 101 | Columbia | MO | 65203 | Columbia, MO 65203 | 5 | 3 | 5 | 2020-02-03 | 2020-01-31 | 2020-01-20 | 703300 | 703301 | 2544 HH - COLUMBIA MO KAH Win10 Upgrade Project Equipment Request | Please ship 5 UD3 Thin Client devices and 3 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/31/20. Ship to: ATTN: Kindred Implementation Services Tech 2404 Forum Boulevard STE 101 Columbia, MO 65203 | 1991994 | No | 0 | 2020
2546201 | 2546 HH - ROLLA | 1206 Homelife Plaza | Rolla | MO | 65401 | Rolla, MO 65401 | 11 | 8 | 3 | 2020-02-17 | 2020-02-14 | 2020-02-03 | 703300 | 703301 | 2546 HH - ROLLA KAH Win10 Upgrade Project Equipment Request | Please ship 11 UD3 Thin Client devices and 8 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/14/20. Ship to: ATTN: Kindred Implementation Services Tech 1206 Homelife Plaza Rolla, MO 65401 | 1991995 | No | 0 | 2020
2550201 | 2550 HH - FARMINGTON | 4783 Flat River Road STE 100A | Farmington | MO | 63640 | Farmington, MO 63640 | 9 | 2 | 5 | 2020-01-27 | 2020-01-24 | 2020-01-13 | 703300 | 703301 | 2550 HH - FARMINGTON KAH Win10 Upgrade Project Equipment Request | Please ship 9 UD3 Thin Client devices and 2 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/24/20. Ship to: ATTN: Kindred Implementation Services Tech 4783 Flat River Road STE 100A Farmington, MO 63640 | 1991996 | No | 0 | 2020
2551201 | 2551 HH - KANSAS CITY SOUTH | 11880 College Blvd. STE 4A | Overland Park | KS | 66210 | Overland Park, KS 66210 | 9 | 3 | 1 | 2020-01-27 | 2020-01-24 | 2020-01-13 | 703300 | 703301 | 2551 HH - KANSAS CITY SOUTH KAH Win10 Upgrade Project Equipment Request | Please ship 9 UD3 Thin Client devices and 3 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/24/20. Ship to: ATTN: Kindred Implementation Services Tech 11880 College Blvd. STE 4A Overland Park, KS 66210 | 1991997 | No | 0 | 2020
2552201 | 2552 HH - KANSAS CITY EAST | 20101 E. Jackson Drive STE D | Independence | MO | 64057 | Independence, MO 64057 | 11 | 3 | 11 | 2020-01-27 | 2020-01-24 | 2020-01-13 | 703300 | 703301 | 2552 HH - KANSAS CITY EAST KAH Win10 Upgrade Project Equipment Request | Please ship 11 UD3 Thin Client devices and 3 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/24/20. Ship to: ATTN: Kindred Implementation Services Tech 20101 E. Jackson Drive STE D Independence, MO 64057 | 1991998 | No | 0 | 2020
2574201 | 2574 HH - DALLAS | 4849 GREENVILLE AVE | DALLAS | TX | 75206 | DALLAS, TX 75206 | 7 | 0 | 3 | 2020-01-27 | 2020-01-24 | 2020-01-13 | 703300 | 703301 | 2574 HH - DALLAS KAH Win10 Upgrade Project Equipment Request | Please ship 7 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/24/20. Ship to: ATTN: Kindred Implementation Services Tech 4849 GREENVILLE AVE DALLAS, TX 75206 | 1992000 | No | 0 | 2020
2576201 | 2576 HH - Fort Worth | 6421 Camp Bowie Blvd, Ste 203 | Fort Worth | TX | 76116 | Fort Worth, TX 76116 | 6 | 0 | 4 | 2020-01-27 | 2020-01-24 | 2020-01-13 | 703300 | 703301 | 2576 HH - Fort Worth KAH Win10 Upgrade Project Equipment Request | Please ship 6 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/24/20. Ship to: ATTN: Kindred Implementation Services Tech 6421 Camp Bowie Blvd, Ste 203 Fort Worth, TX 76116 | 1992001 | No | 0 | 2020
2586201 | 2586 HH - BEAUMONT - HARDEN | 2615 Calder Street STE 202 | Beaumont | TX | 77702 | Beaumont, TX 77702 | 10 | 0 | 10 | 2020-01-27 | 2020-01-24 | 2020-01-13 | 703300 | 703301 | 2586 HH - BEAUMONT - HARDEN KAH Win10 Upgrade Project Equipment Request | Please ship 10 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/24/20. Ship to: ATTN: Kindred Implementation Services Tech 2615 Calder Street STE 202 Beaumont, TX 77702 | 1992002 | No | 0 | 2020
2653201 | 2653 HH - KENT | 20829 72nd Ave South STE 125 | Kent | WA | 98032 | Kent, WA 98032 | 17 | 3 | 9 | 2020-01-27 | 2020-01-24 | 2020-01-13 | 703300 | 703301 | 2653 HH - KENT KAH Win10 Upgrade Project Equipment Request | Please ship 17 UD3 Thin Client devices and 3 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/24/20. Ship to: ATTN: Kindred Implementation Services Tech 20829 72nd Ave South STE 125 Kent, WA 98032 | 1992003 | No |  | 2020
2686201 | 2686 HH - BREMERTON | 4660 Kitsap Way STE 101 | Bremerton | WA | 98312 | Bremerton, WA 98312 | 15 | 0 | 1 | 2020-01-27 | 2020-01-24 | 2020-01-13 | 703300 | 703301 | 2686 HH - BREMERTON KAH Win10 Upgrade Project Equipment Request | Please ship 15 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/24/20. Ship to: ATTN: Kindred Implementation Services Tech 4660 Kitsap Way STE 101 Bremerton, WA 98312 | 1992004 | No |  | 2020
7014201 | 7014 HH - ST LOUIS-WEST | 12125 Woodcrest Executive Dr. STE 340 | Creve Coeur | MO | 63141 | Creve Coeur, MO 63141 | 5 | 5 | 6 | 2020-02-03 | 2020-01-31 | 2020-01-20 | 703300 | 703301 | 7014 HH - ST LOUIS-WEST KAH Win10 Upgrade Project Equipment Request | Please ship 5 UD3 Thin Client devices and 5 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/31/20. Ship to: ATTN: Kindred Implementation Services Tech 12125 Woodcrest Executive Dr. STE 340 Creve Coeur, MO 63141 | 1992005 | No | 0 | 2020
7015201 | 7015 HH - KANSAS CITY NORTH | 7280 NW 87th Terrace, Building C STE 206 | Kansas City | MO | 64153 | Kansas City, MO 64153 | 5 | 3 | 3 | 2020-01-27 | 2020-01-24 | 2020-01-13 | 703300 | 703301 | 7015 HH - KANSAS CITY NORTH KAH Win10 Upgrade Project Equipment Request | Please ship 5 UD3 Thin Client devices and 3 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/24/20. Ship to: ATTN: Kindred Implementation Services Tech 7280 NW 87th Terrace, Building C STE 206 Kansas City, MO 64153 | 1992006 | No | 0 | 2020
2547201 | 2547 HH - WEST PLAINS | 707 Kentucky Avenue | West Plains | MO | 65775 | West Plains, MO 65775 | 6 | 0 | 4 | 2020-01-27 | 2020-01-24 | 2020-01-13 | 703300 | 703301 | 2547 HH - WEST PLAINS KAH Win10 Upgrade Project Equipment Request | Please ship 6 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/24/20. Ship to: ATTN: Kindred Implementation Services Tech 707 Kentucky Avenue West Plains, MO 65775 | 1992008 | No | 0 | 2020
2396201 | 2396 HH - CHICAGO | 2211 York Road STE 215 | Oak Brook | IL | 60523 | Oak Brook, IL 60523 | 8 | 0 | 4 | 2020-02-03 | 2020-01-31 | 2020-01-20 | 703300 | 703301 | 2396 HH - CHICAGO KAH Win10 Upgrade Project Equipment Request | Please ship 8 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/31/20. Ship to: ATTN: Kindred Implementation Services Tech 2211 York Road STE 215 Oak Brook, IL 60523 | 1992737 | No | 0 | 2020
2565201 | 2565 HH - FT SMITH | 2120 South Waldron STE Bldg C | Fort Smith | AR | 72903 | Fort Smith, AR 72903 | 16 | 8 | 1 | 2020-02-03 | 2020-01-31 | 2020-01-20 | 703300 | 703301 | 2565 HH - FT SMITH KAH Win10 Upgrade Project Equipment Request | Please ship 16 UD3 Thin Client devices and 8 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/31/20. Ship to: ATTN: Kindred Implementation Services Tech 2120 South Waldron STE Bldg C Fort Smith, AR 72903 | 1992738 | No | 0 | 2020
2573201 | 2573 HH - CORSICANA | 800 North Main Street STE Q | Corsicana | TX | 75110 | Corsicana, TX 75110 | 7 | 2 | 2 | 2020-02-03 | 2020-01-31 | 2020-01-20 | 703300 | 703301 | 2573 HH - CORSICANA KAH Win10 Upgrade Project Equipment Request | Please ship 7 UD3 Thin Client devices and 2 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/31/20. Ship to: ATTN: Kindred Implementation Services Tech 800 North Main Street STE Q Corsicana, TX 75110 | 1992740 | No | 0 | 2020
2575201 | 2575 HH - EASTLAND | 405 East Commerce Street | Eastland | TX | 76448 | Eastland, TX 76448 | 15 | 0 | 4 | 2020-02-03 | 2020-01-31 | 2020-01-20 | 703300 | 703301 | 2575 HH - EASTLAND KAH Win10 Upgrade Project Equipment Request | Please ship 15 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/31/20. Ship to: ATTN: Kindred Implementation Services Tech 405 East Commerce Street Eastland, TX 76448 | 1992741 | No | 0 | 2020
2578201 | 2578 HH - LONGVIEW | 434 East Loop 281 STE 100 | Longview | TX | 75605 | Longview, TX 75605 | 7 | 0 | 0 | 2020-02-03 | 2020-01-31 | 2020-01-20 | 703300 | 703301 | 2578 HH - LONGVIEW KAH Win10 Upgrade Project Equipment Request | Please ship 7 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/31/20. Ship to: ATTN: Kindred Implementation Services Tech 434 East Loop 281 STE 100 Longview, TX 75605 | 1992743 | No | 0 | 2020
2580201 | 2580 HH - SAN ANGELO - HARDEN | 1518 West Beauregard Avenue | San Angelo | TX | 76901 | San Angelo, TX 76901 | 8 | 1 | 2 | 2020-02-03 | 2020-01-31 | 2020-01-20 | 703300 | 703301 | 2580 HH - SAN ANGELO - HARDEN KAH Win10 Upgrade Project Equipment Request | Please ship 8 UD3 Thin Client devices and 1 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/31/20. Ship to: ATTN: Kindred Implementation Services Tech 1518 West Beauregard Avenue San Angelo, TX 76901 | 1992744 | No | 0 | 2020
2582201 | 2582 HH - TYLER - HARDEN | 1700 S Southeast Loop 323 STE 110 | Tyler | TX | 75701 | Tyler, TX 75701 | 0 | 0 | 0 | 0 | #NUM! | -14 | 703300 | 703301 | 2582 HH - TYLER - HARDEN KAH Win10 Upgrade Project Equipment Request | #NUM! | 1992745 | No | 0 | 2020
2585201 | 2585 HH - HUMBLE | 9810 FM 1960 Bypass Road West STE 215 | Humble | TX | 77338 | Humble, TX 77338 | 28 | 9 | 4 | 2020-02-03 | 2020-01-31 | 2020-01-20 | 703300 | 703301 | 2585 HH - HUMBLE KAH Win10 Upgrade Project Equipment Request | Please ship 28 UD3 Thin Client devices and 9 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/31/20. Ship to: ATTN: Kindred Implementation Services Tech 9810 FM 1960 Bypass Road West STE 215 Humble, TX 77338 | 1992747 | No | 0 | 2020
2587201 | 2587 HH - BELLAIRE | 6700 West Loop South STE 200 | Bellaire | TX | 77401 | Bellaire, TX 77401 | 3 | 1 | 2 | 2020-02-03 | 2020-01-31 | 2020-01-20 | 703300 | 703301 | 2587 HH - BELLAIRE KAH Win10 Upgrade Project Equipment Request | Please ship 3 UD3 Thin Client devices and 1 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/31/20. Ship to: ATTN: Kindred Implementation Services Tech 6700 West Loop South STE 200 Bellaire, TX 77401 | 1992748 | No | 0 | 2020
2591201 | 2591 HH - SAN ANTONIO - HARDEN | 4335 West Piedras Drive STE 100 | San Antonio | TX | 78228 | San Antonio, TX 78228 | 14 | 1 | 8 | 2020-02-03 | 2020-01-31 | 2020-01-20 | 703300 | 703301 | 2591 HH - SAN ANTONIO - HARDEN KAH Win10 Upgrade Project Equipment Request | Please ship 14 UD3 Thin Client devices and 1 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/31/20. Ship to: ATTN: Kindred Implementation Services Tech 4335 West Piedras Drive STE 100 San Antonio, TX 78228 | 1992750 | No | 0 | 2020
2592201 | 2592 HH - SCHULENBURG | 85 North Kessler Avenue | Schulenburg | TX | 78956 | Schulenburg, TX 78956 | 4 | 0 | 4 | 2020-02-03 | 2020-01-31 | 2020-01-20 | 703300 | 703301 | 2592 HH - SCHULENBURG KAH Win10 Upgrade Project Equipment Request | Please ship 4 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/31/20. Ship to: ATTN: Kindred Implementation Services Tech 85 North Kessler Avenue Schulenburg, TX 78956 | 1992757 | No | 0 | 2020
2593201 | 2593 HH - VICTORIA | 1501 East Mockingbird Lane STE 301 | Victoria | TX | 77904 | Victoria, TX 77904 | 11 | 1 | 1 | 2020-02-03 | 2020-01-31 | 2020-01-20 | 703300 | 703301 | 2593 HH - VICTORIA KAH Win10 Upgrade Project Equipment Request | Please ship 11 UD3 Thin Client devices and 1 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/31/20. Ship to: ATTN: Kindred Implementation Services Tech 1501 East Mockingbird Lane STE 301 Victoria, TX 77904 | 1992758 | No | 0 | 2020
3539201 | 3539 HH - BROWNWOOD | 118 South Park Drive STE D | Brownwood | TX | 76801 | Brownwood, TX 76801 | 9 | 0 | 3 | 2020-02-03 | 2020-01-31 | 2020-01-20 | 703300 | 703301 | 3539 HH - BROWNWOOD KAH Win10 Upgrade Project Equipment Request | Please ship 9 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 01/31/20. Ship to: ATTN: Kindred Implementation Services Tech 118 South Park Drive STE D Brownwood, TX 76801 | 1992759 | No | 0 | 2020
3282201 | RF3282 - Kindred at Home Billing | 2560 SW GRAPEVINE PKWY | GRAPEVINE | TX | 76051 | GRAPEVINE, TX 76051 | 0 | 0 | 0 | 0 | #NUM! | -14 | 703300 | 703301 | RF3282 - Kindred at Home Billing KAH Win10 Upgrade Project Equipment Request | #NUM! |  | No | 0 | 2020
2382201 | 2382 HH - RACINE | 6233 Bankers Road STE 1 | Racine | WI | 53403 | Racine, WI 53403 | 6 | 2 | 5 | 2020-02-10 | 2020-02-07 | 2020-01-27 | 703300 | 703301 | 2382 HH - RACINE KAH Win10 Upgrade Project Equipment Request | Please ship 6 UD3 Thin Client devices and 2 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/07/20. Ship to: ATTN: Kindred Implementation Services Tech 6233 Bankers Road STE 1 Racine, WI 53403 | 1993512 | No | 0 | 2020
2388201 | 2388 HH - OMAHA | 9140 West Dodge Road STE 401 | Omaha | NE | 68114 | Omaha, NE 68114 | 8 | 0 | 12 | 2020-02-10 | 2020-02-07 | 2020-01-27 | 703300 | 703301 | 2388 HH - OMAHA KAH Win10 Upgrade Project Equipment Request | Please ship 8 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/07/20. Ship to: ATTN: Kindred Implementation Services Tech 9140 West Dodge Road STE 401 Omaha, NE 68114 | 1993514 | No | 0 | 2020
2599201 | 2599 HH - MODESTO CA | 4216 Kiernan Avenue STE 100 | Modesto | CA | 95356 | Modesto, CA 95356 | 14 | 0 | 3 | 2020-02-10 | 2020-02-07 | 2020-01-27 | 703300 | 703301 | 2599 HH - MODESTO CA KAH Win10 Upgrade Project Equipment Request | Please ship 14 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/07/20. Ship to: ATTN: Kindred Implementation Services Tech 4216 Kiernan Avenue STE 100 Modesto, CA 95356 | 1993515 | No | 0 | 2020
2618201 | 2618 HH - STOCKTON | 10100 Trinity Parkway STE 425 | Stockton | CA | 95219 | Stockton, CA 95219 | 16 | 0 | 6 | 2020-02-10 | 2020-02-07 | 2020-01-27 | 703300 | 703301 | 2618 HH - STOCKTON KAH Win10 Upgrade Project Equipment Request | Please ship 16 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/07/20. Ship to: ATTN: Kindred Implementation Services Tech 10100 Trinity Parkway STE 425 Stockton, CA 95219 | 1993516 | No | 0 | 2020
2620201 | 2620 HH - SAN LUIS OBISPO HHA | 3220 S. Higuera St. STE 101 | San Luis Obispo | CA | 93401 | San Luis Obispo, CA 93401 | 11 | 2 | 0 | 2020-02-10 | 2020-02-07 | 2020-01-27 | 703300 | 703301 | 2620 HH - SAN LUIS OBISPO HHA KAH Win10 Upgrade Project Equipment Request | Please ship 11 UD3 Thin Client devices and 2 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/07/20. Ship to: ATTN: Kindred Implementation Services Tech 3220 S. Higuera St. STE 101 San Luis Obispo, CA 93401 | 1993517 | No | 0 | 2020
2629201 | 2629 HH - LAS CRUCES | 505 South Main STE 132B | Las Cruces | NM | 88001 | Las Cruces, NM 88001 | 4 | 0 | 3 | 2020-02-10 | 2020-02-07 | 2020-01-27 | 703300 | 703301 | 2629 HH - LAS CRUCES KAH Win10 Upgrade Project Equipment Request | Please ship 4 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/07/20. Ship to: ATTN: Kindred Implementation Services Tech 505 South Main STE 132B Las Cruces, NM 88001 | 1993519 | No | 0 | 2020
2631201 | 2631 HH - ALBUQUERQUE | 4401 Masthead Street NE STE 105 | Albuquerque | NM | 87109 | Albuquerque, NM 87109 | 8 | 2 | 6 | 2020-02-10 | 2020-02-07 | 2020-01-27 | 703300 | 703301 | 2631 HH - ALBUQUERQUE KAH Win10 Upgrade Project Equipment Request | Please ship 8 UD3 Thin Client devices and 2 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/07/20. Ship to: ATTN: Kindred Implementation Services Tech 4401 Masthead Street NE STE 105 Albuquerque, NM 87109 | 1993520 | No | 0 | 2020
5025201 | 5025 HH - VICEROY | 720 Park Centre Drive Suite 350-A | Kernersville | NC | 27284 | Kernersville, NC 27284 | 5 | 0 | 1 | 2020-02-10 | 2020-02-07 | 2020-01-27 | 703300 | 703301 | 5025 HH - VICEROY KAH Win10 Upgrade Project Equipment Request | Please ship 5 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/07/20. Ship to: ATTN: Kindred Implementation Services Tech 720 Park Centre Drive Suite 350-A Kernersville, NC 27284 | 1993521 | No | 0 | 2020
7016201 | 7016 HH - LINCOLN | 8055 O Street STE 111 | Lincoln | NE | 68510 | Lincoln, NE 68510 | 5 | 0 | 4 | 2020-02-10 | 2020-02-07 | 2020-01-27 | 703300 | 703301 | 7016 HH - LINCOLN KAH Win10 Upgrade Project Equipment Request | Please ship 5 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/07/20. Ship to: ATTN: Kindred Implementation Services Tech 8055 O Street STE 111 Lincoln, NE 68510 | 1993522 | No | 0 | 2020
7017201 | 7017 HH - WEST ALLIS (fka 2381) | 10150 W National Avenue, Ste 300 | West Allis | WI | 53227 | West Allis, WI 53227 | 5 | 5 | 4 | 2020-02-10 | 2020-02-07 | 2020-01-27 | 703300 | 703301 | 7017 HH - WEST ALLIS (fka 2381) KAH Win10 Upgrade Project Equipment Request | Please ship 5 UD3 Thin Client devices and 5 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/07/20. Ship to: ATTN: Kindred Implementation Services Tech 10150 W National Avenue, Ste 300 West Allis, WI 53227 | 1993523 | No | 0 | 2020
7018201 | 7018 HH - GERMANTOWN | W177 N9886 Rivercrest Drive STE 112 | Germantown | WI | 53022 | Germantown, WI 53022 | 2 | 2 | 4 | 2020-02-10 | 2020-02-07 | 2020-01-27 | 703300 | 703301 | 7018 HH - GERMANTOWN KAH Win10 Upgrade Project Equipment Request | Please ship 2 UD3 Thin Client devices and 2 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/07/20. Ship to: ATTN: Kindred Implementation Services Tech W177 N9886 Rivercrest Drive STE 112 Germantown, WI 53022 | 1993525 | No | 0 | 2020
7020201 | 7020 HH - HUGO (fka 2558) | 804 East Jackson Street | Hugo | OK | 74743 | Hugo, OK 74743 | 0 | 0 | 0 | 0 | #NUM! | -14 | 703300 | 703301 | 7020 HH - HUGO (fka 2558) KAH Win10 Upgrade Project Equipment Request | #NUM! |  | No | 0 | 2020
7022201 | 7022 HH - SAN DIEGO | 2525 Camino Del Rio South STE 220 | San Diego | CA | 92108 | San Diego, CA 92108 | 12 | 0 | 8 | 2020-02-10 | 2020-02-07 | 2020-01-27 | 703300 | 703301 | 7022 HH - SAN DIEGO KAH Win10 Upgrade Project Equipment Request | Please ship 12 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/07/20. Ship to: ATTN: Kindred Implementation Services Tech 2525 Camino Del Rio South STE 220 San Diego, CA 92108 | 1993526 | No | 0 | 2020
3875201 | 3875 HH - DELCO NC | 27385 Andrew Jackson Highway East STE C | Delco | NC | 28436 | Delco, NC 28436 | 0 | 0 | 0 | 2020-02-17 | 2020-02-14 | 2020-02-03 | 703300 | 703301 | 3875 HH - DELCO NC KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/14/20. Ship to: ATTN: Kindred Implementation Services Tech 27385 Andrew Jackson Highway East STE C Delco, NC 28436 |  | No | 0 | 2020
5022201 | 5022 HH - GREENSBORO | 3150 N Elm Street STE 102 | Greensboro | NC | 27408 | Greensboro, NC 27408 | 0 | 0 | 0 | 2020-02-17 | 2020-02-14 | 2020-02-03 | 703300 | 703301 | 5022 HH - GREENSBORO KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/14/20. Ship to: ATTN: Kindred Implementation Services Tech 3150 N Elm Street STE 102 Greensboro, NC 27408 |  | No | 0 | 2020
5035201 | 5035 HH - PINK HILL | 206 S. Turner Street | Pink Hill | NC | 28572 | Pink Hill, NC 28572 | 0 | 0 | 0 | 2020-02-17 | 2020-02-14 | 2020-02-03 | 703300 | 703301 | 5035 HH - PINK HILL KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/14/20. Ship to: ATTN: Kindred Implementation Services Tech 206 S. Turner Street Pink Hill, NC 28572 |  | No | 0 | 2020
5037201 | 5037 HH - ROCKY MOUNT | 4013 Capital Drive | Rocky Mount | NC | 27804 | Rocky Mount, NC 27804 | 0 | 0 | 0 | 2020-02-17 | 2020-02-14 | 2020-02-03 | 703300 | 703301 | 5037 HH - ROCKY MOUNT KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/14/20. Ship to: ATTN: Kindred Implementation Services Tech 4013 Capital Drive Rocky Mount, NC 27804 |  | No | 0 | 2020
5064201 | 5064 HH - BOONE | 579 Greenway Road STE 103 | Boone | NC | 28607 | Boone, NC 28607 | 0 | 0 | 0 | 2020-02-17 | 2020-02-14 | 2020-02-03 | 703300 | 703301 | 5064 HH - BOONE KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/14/20. Ship to: ATTN: Kindred Implementation Services Tech 579 Greenway Road STE 103 Boone, NC 28607 |  | No | 0 | 2020
5067201 | 5067 HH - ANNAPOLIS | 180 Admiral Cochrane Drive STE 310 | Annapolis | MD | 21401 | Annapolis, MD 21401 | 0 | 0 | 0 | 2020-02-17 | 2020-02-14 | 2020-02-03 | 703300 | 703301 | 5067 HH - ANNAPOLIS KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/14/20. Ship to: ATTN: Kindred Implementation Services Tech 180 Admiral Cochrane Drive STE 310 Annapolis, MD 21401 |  | No | 0 | 2020
5068201 | 5068 HH - TOWSON MD | 8600 LaSalle Road STE 315 | Towson | MD | 21286 | Towson, MD 21286 | 0 | 0 | 0 | 2020-02-17 | 2020-02-14 | 2020-02-03 | 703300 | 703301 | 5068 HH - TOWSON MD KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/14/20. Ship to: ATTN: Kindred Implementation Services Tech 8600 LaSalle Road STE 315 Towson, MD 21286 |  | No | 0 | 2020
5069201 | 5069 HH - COLUMBIA MD | 9250 Rumsey Road STE 200 | Columbia | MD | 21045 | Columbia, MD 21045 | 0 | 0 | 0 | 2020-02-17 | 2020-02-14 | 2020-02-03 | 703300 | 703301 | 5069 HH - COLUMBIA MD KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/14/20. Ship to: ATTN: Kindred Implementation Services Tech 9250 Rumsey Road STE 200 Columbia, MD 21045 |  | No | 0 | 2020
5070201 | 5070 HH - SILVER SPRINGS MD | 12501 Prosperity Drive STE 225 | Silver Spring | MD | 20904 | Silver Spring, MD 20904 | 0 | 0 | 0 | 2020-02-24 | 2020-02-21 | 2020-02-10 | 703300 | 703301 | 5070 HH - SILVER SPRINGS MD KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/21/20. Ship to: ATTN: Kindred Implementation Services Tech 12501 Prosperity Drive STE 225 Silver Spring, MD 20904 |  | No | 0 | 2020
7034201 | 7034 HH - ROANOKE (fka 5073) | 1302 Plantation Road NE | Roanoke | VA | 24012 | Roanoke, VA 24012 | 0 | 0 | 0 | 2020-02-17 | 2020-02-14 | 2020-02-03 | 703300 | 703301 | 7034 HH - ROANOKE (fka 5073) KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/14/20. Ship to: ATTN: Kindred Implementation Services Tech 1302 Plantation Road NE Roanoke, VA 24012 |  | No | 0 | 2020
7036201 | 7036 HH - LYNCHBURG (fka 5075) | 1928 Thomson Drive | Lynchburg | VA | 24501 | Lynchburg, VA 24501 | 0 | 0 | 0 | 2020-02-17 | 2020-02-14 | 2020-02-03 | 703300 | 703301 | 7036 HH - LYNCHBURG (fka 5075) KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/14/20. Ship to: ATTN: Kindred Implementation Services Tech 1928 Thomson Drive Lynchburg, VA 24501 |  | No | 0 | 2020
3207201 | 3207 HH - AIKEN | 80 Physician Drive | Aiken | SC | 29801 | Aiken, SC 29801 | 0 | 0 | 0 | 2020-02-24 | 2020-02-21 | 2020-02-10 | 703300 | 703301 | 3207 HH - AIKEN KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/21/20. Ship to: ATTN: Kindred Implementation Services Tech 80 Physician Drive Aiken, SC 29801 |  | No | 0 | 2020
5040201 | 5040 HH - MYRTLE BEACH | 1240 21st Avenue North STE 200 | Myrtle Beach | SC | 29577 | Myrtle Beach, SC 29577 | 0 | 0 | 0 | 2020-02-24 | 2020-02-21 | 2020-02-10 | 703300 | 703301 | 5040 HH - MYRTLE BEACH KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/21/20. Ship to: ATTN: Kindred Implementation Services Tech 1240 21st Avenue North STE 200 Myrtle Beach, SC 29577 |  | No | 0 | 2020
5048201 | 5048 HH - KANNAPOLIS | 201 Security Street | Kannapolis | NC | 28083 | Kannapolis, NC 28083 | 0 | 0 | 0 | 2020-02-17 | 2020-02-14 | 2020-02-03 | 703300 | 703301 | 5048 HH - KANNAPOLIS KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/14/20. Ship to: ATTN: Kindred Implementation Services Tech 201 Security Street Kannapolis, NC 28083 |  | No | 0 | 2020
5059201 | 5059 HH - GASTONIA | 934 Cox Road | Gastonia | NC | 28054 | Gastonia, NC 28054 | 0 | 0 | 0 | 2020-02-17 | 2020-02-14 | 2020-02-03 | 703300 | 703301 | 5059 HH - GASTONIA KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/14/20. Ship to: ATTN: Kindred Implementation Services Tech 934 Cox Road Gastonia, NC 28054 |  | No | 0 | 2020
5065201 | 5065 HH - NORTH WILKESBORO | 126 Executive Drive STE 120 | Wilkesboro | NC | 28697 | Wilkesboro, NC 28697 | 0 | 0 | 0 | 2020-02-17 | 2020-02-14 | 2020-02-03 | 703300 | 703301 | 5065 HH - NORTH WILKESBORO KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/14/20. Ship to: ATTN: Kindred Implementation Services Tech 126 Executive Drive STE 120 Wilkesboro, NC 28697 |  | No | 0 | 2020
5066201 | 5066 HH - WAKE FOREST - WILKES JV | 126 Executive Drive Suite 104 | Wilkesboro | NC | 28697 | Wilkesboro, NC 28697 | 0 | 0 | 0 | 2020-02-17 | 2020-02-14 | 2020-02-03 | 703300 | 703301 | 5066 HH - WAKE FOREST - WILKES JV KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/14/20. Ship to: ATTN: Kindred Implementation Services Tech 126 Executive Drive Suite 104 Wilkesboro, NC 28697 |  | No | 0 | 2020
5076201 | 5076 HH - CHRISTIANSBURG | 15 West Main Street STE 200 | Christiansburg | VA | 24073 | Christiansburg, VA 24073 | 0 | 0 | 0 | 2020-02-17 | 2020-02-14 | 2020-02-03 | 703300 | 703301 | 5076 HH - CHRISTIANSBURG KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/14/20. Ship to: ATTN: Kindred Implementation Services Tech 15 West Main Street STE 200 Christiansburg, VA 24073 |  | No | 0 | 2020
5886201 | 5886 HH - PRINCETON WV | 150 Courthouse Road STE 301A | Princeton | WV | 24740 | Princeton, WV 24740 | 0 | 0 | 0 | 2020-02-17 | 2020-02-14 | 2020-02-03 | 703300 | 703301 | 5886 HH - PRINCETON WV KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/14/20. Ship to: ATTN: Kindred Implementation Services Tech 150 Courthouse Road STE 301A Princeton, WV 24740 |  | No | 0 | 2020
6527201 | 6527 HH - STATESBORO | 1525 Fair Road STE 106 | Statesboro | GA | 30458 | Statesboro, GA 30458 | 0 | 0 | 0 | 2020-02-24 | 2020-02-21 | 2020-02-10 | 703300 | 703301 | 6527 HH - STATESBORO KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/21/20. Ship to: ATTN: Kindred Implementation Services Tech 1525 Fair Road STE 106 Statesboro, GA 30458 |  | No | 0 | 2020
6528201 | 6528 HH - AUGUSTA GA | 1225 West Wheeler Parkway Bldg C | Augusta | GA | 30909 | Augusta, GA 30909 | 0 | 0 | 0 | 2020-02-24 | 2020-02-21 | 2020-02-10 | 703300 | 703301 | 6528 HH - AUGUSTA GA KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/21/20. Ship to: ATTN: Kindred Implementation Services Tech 1225 West Wheeler Parkway Bldg C Augusta, GA 30909 |  | No | 0 | 2020
6529201 | 6529 HH - GREENVILLE SC | 15 Brendan Way STE 250 | Greenville | SC | 29615 | Greenville, SC 29615 | 0 | 0 | 0 | 2020-02-24 | 2020-02-21 | 2020-02-10 | 703300 | 703301 | 6529 HH - GREENVILLE SC KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/21/20. Ship to: ATTN: Kindred Implementation Services Tech 15 Brendan Way STE 250 Greenville, SC 29615 |  | No | 0 | 2020
6532201 | 6532 HH - SPARTANBURG | 905 East Main Street STE 1 | Spartanburg | SC | 29302 | Spartanburg, SC 29302 | 0 | 0 | 0 | 2020-02-24 | 2020-02-21 | 2020-02-10 | 703300 | 703301 | 6532 HH - SPARTANBURG KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/21/20. Ship to: ATTN: Kindred Implementation Services Tech 905 East Main Street STE 1 Spartanburg, SC 29302 |  | No | 0 | 2020
6533201 | 6533 HH - GAFFNEY | 206 Chesnee Highway STE G & H | Gaffney | SC | 29341 | Gaffney, SC 29341 | 0 | 0 | 0 | 2020-02-24 | 2020-02-21 | 2020-02-10 | 703300 | 703301 | 6533 HH - GAFFNEY KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/21/20. Ship to: ATTN: Kindred Implementation Services Tech 206 Chesnee Highway STE G & H Gaffney, SC 29341 |  | No | 0 | 2020
7030201 | 7030 HH - SAVANNAH | 2280 East Victory Drive STE B | Savannah | GA | 31404 | Savannah, GA 31404 | 0 | 0 | 0 | 2020-02-24 | 2020-02-21 | 2020-02-10 | 703300 | 703301 | 7030 HH - SAVANNAH KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/21/20. Ship to: ATTN: Kindred Implementation Services Tech 2280 East Victory Drive STE B Savannah, GA 31404 |  | No | 0 | 2020
3182201 | 3182 HH - ANDERSON DHEC | 1704 E. Greenville Street STE 2D | Anderson | SC | 29621 | Anderson, SC 29621 | 0 | 0 | 0 | 2020-03-02 | 2020-02-28 | 2020-02-17 | 703300 | 703301 | 3182 HH - ANDERSON DHEC KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/28/20. Ship to: ATTN: Kindred Implementation Services Tech 1704 E. Greenville Street STE 2D Anderson, SC 29621 |  | No | 0 | 2020
3183201 | 3183 HH - NEWBERRY | 2521 Evans Street | Newberry | SC | 29108 | Newberry, SC 29108 | 0 | 0 | 0 | 2020-02-24 | 2020-02-21 | 2020-02-10 | 703300 | 703301 | 3183 HH - NEWBERRY KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/21/20. Ship to: ATTN: Kindred Implementation Services Tech 2521 Evans Street Newberry, SC 29108 |  | No | 0 | 2020
3185201 | 3185 HH - FLORENCE | 702 Pamplico Highway STE B | Florence | SC | 29505 | Florence, SC 29505 | 0 | 0 | 0 | 2020-03-02 | 2020-02-28 | 2020-02-17 | 703300 | 703301 | 3185 HH - FLORENCE KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/28/20. Ship to: ATTN: Kindred Implementation Services Tech 702 Pamplico Highway STE B Florence, SC 29505 |  | No | 0 | 2020
3186201 | 3186 HH - CHESTERFIELD | 515 Market Street | Cheraw | SC | 29520 | Cheraw, SC 29520 | 0 | 0 | 0 | 2020-03-02 | 2020-02-28 | 2020-02-17 | 703300 | 703301 | 3186 HH - CHESTERFIELD KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/28/20. Ship to: ATTN: Kindred Implementation Services Tech 515 Market Street Cheraw, SC 29520 |  | No | 0 | 2020
3187201 | 3187 HH - DILLON | 1311 N Main Street STE 102 | Marion | SC | 29571 | Marion, SC 29571 | 0 | 0 | 0 | 2020-03-02 | 2020-02-28 | 2020-02-17 | 703300 | 703301 | 3187 HH - DILLON KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/28/20. Ship to: ATTN: Kindred Implementation Services Tech 1311 N Main Street STE 102 Marion, SC 29571 |  | No | 0 | 2020
3188201 | 3188 HH - MANNING | 122 N. Brooks Street | Manning | SC | 29102 | Manning, SC 29102 | 0 | 0 | 0 | 2020-03-02 | 2020-02-28 | 2020-02-17 | 703300 | 703301 | 3188 HH - MANNING KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/28/20. Ship to: ATTN: Kindred Implementation Services Tech 122 N. Brooks Street Manning, SC 29102 |  | No | 0 | 2020
3209201 | 3209 HH - ORANGEBURG | 1739 Village Park Drive | Orangeburg | SC | 29118 | Orangeburg, SC 29118 | 0 | 0 | 0 | 2020-03-02 | 2020-02-28 | 2020-02-17 | 703300 | 703301 | 3209 HH - ORANGEBURG KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/28/20. Ship to: ATTN: Kindred Implementation Services Tech 1739 Village Park Drive Orangeburg, SC 29118 |  | No | 0 | 2020
5039201 | 5039 HH - COLUMBIA SC | 2000 Center Point Road STE 2300 | Columbia | SC | 29210 | Columbia, SC 29210 | 0 | 0 | 0 | 2020-02-24 | 2020-02-21 | 2020-02-10 | 703300 | 703301 | 5039 HH - COLUMBIA SC KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/21/20. Ship to: ATTN: Kindred Implementation Services Tech 2000 Center Point Road STE 2300 Columbia, SC 29210 |  | No | 0 | 2020
5041201 | 5041 HH - ROCK HILL 2 | 250 Piedmont Blvd | Rock Hill | SC | 29732 | Rock Hill, SC 29732 | 0 | 0 | 0 | 2020-03-02 | 2020-02-28 | 2020-02-17 | 703300 | 703301 | 5041 HH - ROCK HILL 2 KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/28/20. Ship to: ATTN: Kindred Implementation Services Tech 250 Piedmont Blvd Rock Hill, SC 29732 |  | No | 0 | 2020
5044201 | 5044 HH - NORTH CHARLOTTE | 9009-C Perimeter Woods Drive | Charlotte | NC | 28216 | Charlotte, NC 28216 | 0 | 0 | 0 | 2020-03-02 | 2020-02-28 | 2020-02-17 | 703300 | 703301 | 5044 HH - NORTH CHARLOTTE KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/28/20. Ship to: ATTN: Kindred Implementation Services Tech 9009-C Perimeter Woods Drive Charlotte, NC 28216 |  | No | 0 | 2020
5045201 | 5045 HH - SOUTH CHARLOTTE | 11111 Carmel Commons Blvd. STE 350 | Charlotte | NC | 28226 | Charlotte, NC 28226 | 0 | 0 | 0 | 2020-03-02 | 2020-02-28 | 2020-02-17 | 703300 | 703301 | 5045 HH - SOUTH CHARLOTTE KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/28/20. Ship to: ATTN: Kindred Implementation Services Tech 11111 Carmel Commons Blvd. STE 350 Charlotte, NC 28226 |  | No | 0 | 2020
5062201 | 5062 HH - MONROE, NC | 1995 Wellness Boulevard STE 220 | Monroe | NC | 28110 | Monroe, NC 28110 | 0 | 0 | 0 | 2020-03-02 | 2020-02-28 | 2020-02-17 | 703300 | 703301 | 5062 HH - MONROE, NC KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/28/20. Ship to: ATTN: Kindred Implementation Services Tech 1995 Wellness Boulevard STE 220 Monroe, NC 28110 |  | No | 0 | 2020
6531201 | 6531 HH - SENECA | 977 Tiger Boulevard | Clemson | SC | 29631 | Clemson, SC 29631 | 0 | 0 | 0 | 2020-03-02 | 2020-02-28 | 2020-02-17 | 703300 | 703301 | 6531 HH - SENECA KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/28/20. Ship to: ATTN: Kindred Implementation Services Tech 977 Tiger Boulevard Clemson, SC 29631 |  | No | 0 | 2020
6534201 | 6534 HH - UNION 2 | 1261 South Duncan Bypass | Union | SC | 29379 | Union, SC 29379 | 0 | 0 | 0 | 2020-03-02 | 2020-02-28 | 2020-02-17 | 703300 | 703301 | 6534 HH - UNION 2 KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/28/20. Ship to: ATTN: Kindred Implementation Services Tech 1261 South Duncan Bypass Union, SC 29379 |  | No | 0 | 2020
7032201 | 7032 HH Charlotte University | 11111 Carmel Commons Blvd. Suite 350-B | Charlotte | NC | 28226 | Charlotte, NC 28226 | 0 | 0 | 0 | 2020-03-02 | 2020-02-28 | 2020-02-17 | 703300 | 703301 | 7032 HH Charlotte University KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 02/28/20. Ship to: ATTN: Kindred Implementation Services Tech 11111 Carmel Commons Blvd. Suite 350-B Charlotte, NC 28226 |  | No | 0 | 2020
3190201 | 3190 HH - WALTERBORO | 415-E Robertson Boulevard | Walterboro | SC | 29488 | Walterboro, SC 29488 | 0 | 0 | 0 | 2020-03-09 | 2020-03-06 | 2020-02-24 | 703300 | 703301 | 3190 HH - WALTERBORO KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/06/20. Ship to: ATTN: Kindred Implementation Services Tech 415-E Robertson Boulevard Walterboro, SC 29488 |  | No | 0 | 2020
5078201 | 5078 HH - HOPKINSVILLE HHA | 540 Noel Avenue | Hopkinsville | KY | 42240 | Hopkinsville, KY 42240 | 0 | 0 | 0 | 2020-03-09 | 2020-03-06 | 2020-02-24 | 703300 | 703301 | 5078 HH - HOPKINSVILLE HHA KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/06/20. Ship to: ATTN: Kindred Implementation Services Tech 540 Noel Avenue Hopkinsville, KY 42240 |  | No | 0 | 2020
5079201 | 5079 HH - NASHVILLE | 624 Grassmere Park Drive STE 8 | Nashville | TN | 37211 | Nashville, TN 37211 | 0 | 0 | 0 | 2020-03-09 | 2020-03-06 | 2020-02-24 | 703300 | 703301 | 5079 HH - NASHVILLE KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/06/20. Ship to: ATTN: Kindred Implementation Services Tech 624 Grassmere Park Drive STE 8 Nashville, TN 37211 |  | No | 0 | 2020
5089201 | 5089 HH - PARKERSBURG WV | 39 12th Street | Parkersburg | WV | 26101 | Parkersburg, WV 26101 | 0 | 0 | 0 | 2020-03-09 | 2020-03-06 | 2020-02-24 | 703300 | 703301 | 5089 HH - PARKERSBURG WV KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/06/20. Ship to: ATTN: Kindred Implementation Services Tech 39 12th Street Parkersburg, WV 26101 |  | No | 0 | 2020
5764201 | 5764 HH - CHARLESTON WV | 100 Kanawha Blvd West | Charleston | WV | 25302 | Charleston, WV 25302 | 0 | 0 | 0 | 2020-03-09 | 2020-03-06 | 2020-02-24 | 703300 | 703301 | 5764 HH - CHARLESTON WV KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/06/20. Ship to: ATTN: Kindred Implementation Services Tech 100 Kanawha Blvd West Charleston, WV 25302 |  | No | 0 | 2020
5883201 | 5883 HH - CHAPMANVILLE | 46 Friendly Neighbor Drive | Chapmanville | WV | 25508 | Chapmanville, WV 25508 | 0 | 0 | 0 | 2020-03-09 | 2020-03-06 | 2020-02-24 | 703300 | 703301 | 5883 HH - CHAPMANVILLE KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/06/20. Ship to: ATTN: Kindred Implementation Services Tech 46 Friendly Neighbor Drive Chapmanville, WV 25508 |  | No | 0 | 2020
5884201 | 5884 HH - BECKLEY WV | 112 Mellon Street | Beckley | WV | 25801 | Beckley, WV 25801 | 0 | 0 | 0 | 2020-03-09 | 2020-03-06 | 2020-02-24 | 703300 | 703301 | 5884 HH - BECKLEY WV KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/06/20. Ship to: ATTN: Kindred Implementation Services Tech 112 Mellon Street Beckley, WV 25801 |  | No | 0 | 2020
5885201 | 5885 HH - HUNTINGTON WV | 5187 US Route 60 STE 28 | Huntington | WV | 25705 | Huntington, WV 25705 | 0 | 0 | 0 | 2020-03-09 | 2020-03-06 | 2020-02-24 | 703300 | 703301 | 5885 HH - HUNTINGTON WV KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/06/20. Ship to: ATTN: Kindred Implementation Services Tech 5187 US Route 60 STE 28 Huntington, WV 25705 |  | No | 0 | 2020
5887201 | 5887 HH - SUMMERSVILLE WV | 800 Broad Street | Summersville | WV | 26651 | Summersville, WV 26651 | 0 | 0 | 0 | 2020-03-09 | 2020-03-06 | 2020-02-24 | 703300 | 703301 | 5887 HH - SUMMERSVILLE WV KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/06/20. Ship to: ATTN: Kindred Implementation Services Tech 800 Broad Street Summersville, WV 26651 |  | No | 0 | 2020
6227201 | 6227 HH - LOUISVILLE | 710 Executive Park | Louisville | KY | 40207 | Louisville, KY 40207 | 0 | 0 | 0 | 2020-03-09 | 2020-03-06 | 2020-02-24 | 703300 | 703301 | 6227 HH - LOUISVILLE KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/06/20. Ship to: ATTN: Kindred Implementation Services Tech 710 Executive Park Louisville, KY 40207 |  | No | 0 | 2020
6238201 | 6238 HH - N KENTUCKY | 2114 Chamber Center Drive | Fort Mitchell | KY | 41017 | Fort Mitchell, KY 41017 | 0 | 0 | 0 | 2020-03-09 | 2020-03-06 | 2020-02-24 | 703300 | 703301 | 6238 HH - N KENTUCKY KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/06/20. Ship to: ATTN: Kindred Implementation Services Tech 2114 Chamber Center Drive Fort Mitchell, KY 41017 |  | No | 0 | 2020
6248201 | 6248 HH - LEXINGTON | 1300 E New Circle Road STE 180 | Lexington | KY | 40505 | Lexington, KY 40505 | 0 | 0 | 0 | 2020-03-09 | 2020-03-06 | 2020-02-24 | 703300 | 703301 | 6248 HH - LEXINGTON KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/06/20. Ship to: ATTN: Kindred Implementation Services Tech 1300 E New Circle Road STE 180 Lexington, KY 40505 |  | No | 0 | 2020
6522201 | 6522 HH - SHELBYVILLE | 140 Stonecrest Road STE 203 | Shelbyville | KY | 40065 | Shelbyville, KY 40065 | 0 | 0 | 0 | 2020-03-09 | 2020-03-06 | 2020-02-24 | 703300 | 703301 | 6522 HH - SHELBYVILLE KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/06/20. Ship to: ATTN: Kindred Implementation Services Tech 140 Stonecrest Road STE 203 Shelbyville, KY 40065 |  | No | 0 | 2020
6524201 | 6524 HH - DANVILLE - NEW | 105 Citation Dr STE B | Danville | KY | 40422 | Danville, KY 40422 | 0 | 0 | 0 | 2020-03-09 | 2020-03-06 | 2020-02-24 | 703300 | 703301 | 6524 HH - DANVILLE - NEW KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/06/20. Ship to: ATTN: Kindred Implementation Services Tech 105 Citation Dr STE B Danville, KY 40422 |  | No | 0 | 2020
7031201 | 7031 HH - CHARLESTON SC | 4975 Lacross Road STE 354 | North Charleston | SC | 29406 | North Charleston, SC 29406 | 0 | 0 | 0 | 2020-03-09 | 2020-03-06 | 2020-02-24 | 703300 | 703301 | 7031 HH - CHARLESTON SC KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/06/20. Ship to: ATTN: Kindred Implementation Services Tech 4975 Lacross Road STE 354 North Charleston, SC 29406 |  | No | 0 | 2020
2361201 | 2361 HH - BANGOR | 175 Exchange Street STE 100 | Bangor | ME | 4401 | Bangor, ME 4401 | 0 | 0 | 0 | 2020-03-16 | 2020-03-13 | 2020-03-02 | 703300 | 703301 | 2361 HH - BANGOR KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/13/20. Ship to: ATTN: Kindred Implementation Services Tech 175 Exchange Street STE 100 Bangor, ME 4401 |  | No | 0 | 2020
2435201 | 2435 HH - LANCASTER | 1860 Charter Lane STE 106 | Lancaster | PA | 17601 | Lancaster, PA 17601 | 0 | 0 | 0 | 2020-03-16 | 2020-03-13 | 2020-03-02 | 703300 | 703301 | 2435 HH - LANCASTER KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/13/20. Ship to: ATTN: Kindred Implementation Services Tech 1860 Charter Lane STE 106 Lancaster, PA 17601 |  | No | 0 | 2020
2460201 | 2460 HH - GWINNETT | 1075 Old Norcross Road STE S | Lawrenceville | GA | 30046 | Lawrenceville, GA 30046 | 0 | 0 | 0 | 2020-03-16 | 2020-03-13 | 2020-03-02 | 703300 | 703301 | 2460 HH - GWINNETT KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/13/20. Ship to: ATTN: Kindred Implementation Services Tech 1075 Old Norcross Road STE S Lawrenceville, GA 30046 |  | No | 0 | 2020
2461201 | 2461 HH - STOCKBRIDGE | 200 Business Center Drive STE 218 | Stockbridge | GA | 30281 | Stockbridge, GA 30281 | 0 | 0 | 0 | 2020-03-16 | 2020-03-13 | 2020-03-02 | 703300 | 703301 | 2461 HH - STOCKBRIDGE KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/13/20. Ship to: ATTN: Kindred Implementation Services Tech 200 Business Center Drive STE 218 Stockbridge, GA 30281 |  | No | 0 | 2020
2463201 | 2463 HH - GRIFFIN | 246 O'Dell Road STE Unit 3 | Griffin | GA | 30224 | Griffin, GA 30224 | 0 | 0 | 0 | 2020-03-16 | 2020-03-13 | 2020-03-02 | 703300 | 703301 | 2463 HH - GRIFFIN KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/13/20. Ship to: ATTN: Kindred Implementation Services Tech 246 O'Dell Road STE Unit 3 Griffin, GA 30224 |  | No | 0 | 2020
2464201 | 2464 HH - VILLA RICA GA | 845 South Carroll Road STE C | Villa Rica | GA | 30180 | Villa Rica, GA 30180 | 0 | 0 | 0 | 2020-03-16 | 2020-03-13 | 2020-03-02 | 703300 | 703301 | 2464 HH - VILLA RICA GA KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/13/20. Ship to: ATTN: Kindred Implementation Services Tech 845 South Carroll Road STE C Villa Rica, GA 30180 |  | No | 0 | 2020
2465201 | 2465 HH - PEACHTREE CITY | 277 Hwy 74 North STE 307 | Peachtree City | GA | 30269 | Peachtree City, GA 30269 | 0 | 0 | 0 | 2020-03-16 | 2020-03-13 | 2020-03-02 | 703300 | 703301 | 2465 HH - PEACHTREE CITY KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/13/20. Ship to: ATTN: Kindred Implementation Services Tech 277 Hwy 74 North STE 307 Peachtree City, GA 30269 |  | No | 0 | 2020
2466201 | 2466 HH - SANDY SPRINGS | 1303 Hightower Trail STE 105 | Atlanta | GA | 30350 | Atlanta, GA 30350 | 0 | 0 | 0 | 2020-03-16 | 2020-03-13 | 2020-03-02 | 703300 | 703301 | 2466 HH - SANDY SPRINGS KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/13/20. Ship to: ATTN: Kindred Implementation Services Tech 1303 Hightower Trail STE 105 Atlanta, GA 30350 |  | No | 0 | 2020
2466201 | 2466 HH - SANDY SPRINGS | 1303 Hightower Trail STE 105 | Atlanta | GA | 30350 | Atlanta, GA 30350 | 0 | 0 | 0 | 2020-03-16 | 2020-03-13 | 2020-03-02 | 703300 | 703301 | 2466 HH - SANDY SPRINGS KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/13/20. Ship to: ATTN: Kindred Implementation Services Tech 1303 Hightower Trail STE 105 Atlanta, GA 30350 |  | No | 0 | 2020
2467201 | 2467 HH - CUMMING | 2080 Ronald Reagan Blvd STE 500 | Cumming | GA | 30041 | Cumming, GA 30041 | 0 | 0 | 0 | 2020-03-16 | 2020-03-13 | 2020-03-02 | 703300 | 703301 | 2467 HH - CUMMING KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/13/20. Ship to: ATTN: Kindred Implementation Services Tech 2080 Ronald Reagan Blvd STE 500 Cumming, GA 30041 |  | No | 0 | 2020
2469201 | 2469 HH - MARIETTA | 1395 South Marietta Pkwy. STE 902 | Marietta | GA | 30067 | Marietta, GA 30067 | 0 | 0 | 0 | 2020-03-16 | 2020-03-13 | 2020-03-02 | 703300 | 703301 | 2469 HH - MARIETTA KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/13/20. Ship to: ATTN: Kindred Implementation Services Tech 1395 South Marietta Pkwy. STE 902 Marietta, GA 30067 |  | No | 0 | 2020
3714201 | 3714 - Norfolk (confirmed open with Larry) | 410 N. Center Drive, Bldg. 9, Suite 102 | Norfolk | VA | 23502 | Norfolk , VA 23502 | 0 | 0 | 0 | 2020-03-16 | 2020-03-13 | 2020-03-02 | 703300 | 703301 | 3714 - Norfolk (confirmed open with Larry) KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/13/20. Ship to: ATTN: Kindred Implementation Services Tech 410 N. Center Drive, Bldg. 9, Suite 102 Norfolk , VA 23502 |  | No | 0 | 2020
6964201 | 6964 HH - Charlotte Cntrl Intk - Shrd Svcs | 2221 EDGE LAKE DRIVE | CHARLOTTE | NC | 28217 | CHARLOTTE, NC 28217 | 0 | 0 | 0 | 2020-03-16 | 2020-03-13 | 2020-03-02 | 703300 | 703301 | 6964 HH - Charlotte Cntrl Intk - Shrd Svcs KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/13/20. Ship to: ATTN: Kindred Implementation Services Tech 2221 EDGE LAKE DRIVE CHARLOTTE, NC 28217 |  | No | 0 | 2020
7013201 | 7013 HH - SANFORD ME | 2 Livewell Drive STE 101 | Kennebunk | ME | 4043 | Kennebunk, ME 4043 | 0 | 0 | 0 | 2020-03-16 | 2020-03-13 | 2020-03-02 | 703300 | 703301 | 7013 HH - SANFORD ME KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/13/20. Ship to: ATTN: Kindred Implementation Services Tech 2 Livewell Drive STE 101 Kennebunk, ME 4043 |  | No | 0 | 2020
7033201 | 7033 HH - RICHMOND | 7113 Three Chopt Road STE 201 | Richmond | VA | 23226 | Richmond, VA 23226 | 0 | 0 | 0 | 2020-03-16 | 2020-03-13 | 2020-03-02 | 703300 | 703301 | 7033 HH - RICHMOND KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/13/20. Ship to: ATTN: Kindred Implementation Services Tech 7113 Three Chopt Road STE 201 Richmond, VA 23226 |  | No | 0 | 2020
2355201 | 2355 HH - SPRINGFIELD BEHAV HEALTH | 2069 Roosevelt Avenue | Springfield | MA | 1104 | Springfield, MA 1104 | 0 | 0 | 0 | 2020-03-23 | 2020-03-20 | 2020-03-09 | 703300 | 703301 | 2355 HH - SPRINGFIELD BEHAV HEALTH KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/20/20. Ship to: ATTN: Kindred Implementation Services Tech 2069 Roosevelt Avenue Springfield, MA 1104 |  |  | 0 | 2020
2363201 | 2363 HH - PITTSFIELD | 279 Dalton Ave. STE B | Pittsfield | MA | 1201 | Pittsfield, MA 1201 | 0 | 0 | 0 | 2020-03-23 | 2020-03-20 | 2020-03-09 | 703300 | 703301 | 2363 HH - PITTSFIELD KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/20/20. Ship to: ATTN: Kindred Implementation Services Tech 279 Dalton Ave. STE B Pittsfield, MA 1201 |  | No | 0 | 2020
2366201 | 2366 HH - PORTLAND ME | 51 Baxter Boulevard | Portland | ME | 4101 | Portland, ME 4101 | 0 | 0 | 0 | 2020-03-23 | 2020-03-20 | 2020-03-09 | 703300 | 703301 | 2366 HH - PORTLAND ME KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/20/20. Ship to: ATTN: Kindred Implementation Services Tech 51 Baxter Boulevard Portland, ME 4101 |  | No | 0 | 2020
2372201 | 2372 HH - AUBURN NY | 425 Grant Ave. | Auburn | NY | 13021 | Auburn, NY 13021 | 0 | 0 | 0 | 2020-03-23 | 2020-03-20 | 2020-03-09 | 703300 | 703301 | 2372 HH - AUBURN NY KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/20/20. Ship to: ATTN: Kindred Implementation Services Tech 425 Grant Ave. Auburn, NY 13021 |  | No | 0 | 2020
2373201 | 2373 HH - OSWEGO | 19 Fourth Avenue | Oswego | NY | 13126 | Oswego, NY 13126 | 0 | 0 | 0 | 2020-03-23 | 2020-03-20 | 2020-03-09 | 703300 | 703301 | 2373 HH - OSWEGO KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/20/20. Ship to: ATTN: Kindred Implementation Services Tech 19 Fourth Avenue Oswego, NY 13126 |  | No | 0 | 2020
2374201 | 2374 HH - LIVERPOOL | 200 Elwood Davis Rd | Liverpool | NY | 13088 | Liverpool, NY 13088 | 0 | 0 | 0 | 2020-03-23 | 2020-03-20 | 2020-03-09 | 703300 | 703301 | 2374 HH - LIVERPOOL KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/20/20. Ship to: ATTN: Kindred Implementation Services Tech 200 Elwood Davis Rd Liverpool, NY 13088 |  | No | 0 | 2020
2376201 | 2376 HH - STRATFORD | 99 Hawley Lane STE 1101 | Stratford | CT | 6614 | Stratford, CT 6614 | 0 | 0 | 0 | 2020-03-23 | 2020-03-20 | 2020-03-09 | 703300 | 703301 | 2376 HH - STRATFORD KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/20/20. Ship to: ATTN: Kindred Implementation Services Tech 99 Hawley Lane STE 1101 Stratford, CT 6614 |  | No | 0 | 2020
2377201 | 2377 HH - HAMDEN | 1952 Whitney Avenue, 1st Floor | Hamden | CT | 6517 | Hamden, CT 6517 | 0 | 0 | 0 | 2020-03-23 | 2020-03-20 | 2020-03-09 | 703300 | 703301 | 2377 HH - HAMDEN KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/20/20. Ship to: ATTN: Kindred Implementation Services Tech 1952 Whitney Avenue, 1st Floor Hamden, CT 6517 |  | No | 0 | 2020
2378201 | 2378 HH - OLD SAYBROOK | 210 Main Street STE 1A & 2 | Old Saybrook | CT | 6475 | Old Saybrook, CT 6475 | 0 | 0 | 0 | 2020-03-23 | 2020-03-20 | 2020-03-09 | 703300 | 703301 | 2378 HH - OLD SAYBROOK KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/20/20. Ship to: ATTN: Kindred Implementation Services Tech 210 Main Street STE 1A & 2 Old Saybrook, CT 6475 |  | No | 0 | 2020
2379201 | 2379 HH - MALTA NY | Clifton Park Center, 320 Ushers Road | Ballston Lake | NY | 12065 | Ballston Lake, NY 12065 | 0 | 0 | 0 | 2020-03-23 | 2020-03-20 | 2020-03-09 | 703300 | 703301 | 2379 HH - MALTA NY KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/20/20. Ship to: ATTN: Kindred Implementation Services Tech Clifton Park Center, 320 Ushers Road Ballston Lake, NY 12065 |  | No | 0 | 2020
2434201 | 2434 HH - CORNING | 11849 East Corning Road STE 108 | Corning | NY | 14830 | Corning, NY 14830 | 0 | 0 | 0 | 2020-03-23 | 2020-03-20 | 2020-03-09 | 703300 | 703301 | 2434 HH - CORNING KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/20/20. Ship to: ATTN: Kindred Implementation Services Tech 11849 East Corning Road STE 108 Corning, NY 14830 |  | No | 0 | 2020
7012201 | 7012 HH - SANDWICH (fka 2364) | 88 Route 6A STE 101 | Sandwich | MA | 2563 | Sandwich, MA 2563 | 0 | 0 | 0 | 2020-03-23 | 2020-03-20 | 2020-03-09 | 703300 | 703301 | 7012 HH - SANDWICH (fka 2364) KAH Win10 Upgrade Project Equipment Request | Please ship 0 UD3 Thin Client devices and 0 laptops with the Gentiva Win10 Image with docking stations. Please send the equipment on PO703300 and PO703301 to be at facility by 03/20/20. Ship to: ATTN: Kindred Implementation Services Tech 88 Route 6A STE 101 Sandwich, MA 2563 |  | No | 0 | 2020
A 123 | A 123 East Carolina/R140 South Region | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 703300 | 703301 | A 123 East Carolina/R140 South Region KAH Win10 Upgrade Project Equipment Request | #N/A | 1960807 | No | #N/A | 2019
3122201 | 3122 HH-Catawba Co | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 703300 | 703301 | 3122 HH-Catawba Co KAH Win10 Upgrade Project Equipment Request | #N/A |  | No | #N/A | 2020
Totals | [6 empty] | 1769 | 281 | 929
Remaining Stock
Formulas:
Migration Date = VLOOKUP(ServiceTickets[Facility ID],'T-Schedule'!B$2:C286,2,FALSE)
Onsite By = ServiceTickets[[#This Row],[Migration Date]] - WEEKDAY(ServiceTickets[[#This Row],[Migration Date]]-6)
Order By = ServiceTickets[[#This Row],[Migration Date]] - 14

## Asset to Location Tracking All
Original Device Information |  |  |  |  | Replacement Device Information |  |  |  | Project/Technician Information
Pre-PCN | Device Type | Device SN | UserName | Action | Post-PCN | Device Type2 | Device SN2 | UserNameme2 | Project | Project Phase | Date Start | Date Finish | Technician | Facility ID | Facility Name | Facility Street 1 | Facility City | Facility State | Facility Zip | Facility Phone
Note on N57: Young, Hunter: Cawthorn, Joshua Dawson, Michael
Note on N58: Young, Hunter: Cawthorn, Joshua Dawson, Michael
Note on N59: Young, Hunter: Cawthorn, Joshua Dawson, Michael
Note on N60: Young, Hunter: Cawthorn, Joshua Dawson, Michael
Note on N61: Young, Hunter: Cawthorn, Joshua Dawson, Michael
Note on N62: Young, Hunter: Cawthorn, Joshua Dawson, Michael
Note on N63: Young, Hunter: Cawthorn, Joshua Dawson, Michael
Note on N64: Young, Hunter: Cawthorn, Joshua Dawson, Michael
Note on N65: Young, Hunter: Cawthorn, Joshua Dawson, Michael
Note on N66: Young, Hunter: Cawthorn, Joshua Dawson, Michael
Note on N67: Young, Hunter: Cawthorn, Joshua Dawson, Michael
Note on N68: Young, Hunter: Cawthorn, Joshua Dawson, Michael
Note on N69: Young, Hunter: Cawthorn, Joshua Dawson, Michael
Note on N70: Young, Hunter: Cawthorn, Joshua Dawson, Michael
Note on N71: Young, Hunter: Cawthorn, Joshua Dawson, Michael
Note on N72: Young, Hunter: Cawthorn, Joshua Dawson, Michael
Note on N73: Young, Hunter: Cawthorn, Joshua Dawson, Michael
Note on N74: Young, Hunter: Cawthorn, Joshua Dawson, Michael
Note on N75: Young, Hunter: Cawthorn, Joshua Dawson, Michael
Note on N76: Young, Hunter: Cawthorn, Joshua Dawson, Michael
Note on N77: Young, Hunter: Cawthorn, Joshua Dawson, Michael
Note on N78: Young, Hunter: Cawthorn, Joshua Dawson, Michael
Note on N79: Young, Hunter: Cawthorn, Joshua Dawson, Michael
Note on N80: Young, Hunter: Cawthorn, Joshua Dawson, Michael
Note on N81: Young, Hunter: Cawthorn, Joshua Dawson, Michael
Note on N82: Young, Hunter: Cawthorn, Joshua Dawson, Michael
Note on N83: Young, Hunter: Cawthorn, Joshua Dawson, Michael
Note on N84: Young, Hunter: Cawthorn, Joshua Dawson, Michael
Note on N85: Young, Hunter: Cawthorn, Joshua Dawson, Michael
Note on N86: Young, Hunter: Cawthorn, Joshua Dawson, Michael
Note on N87: Young, Hunter: Cawthorn, Joshua Dawson, Michael
Note on N88: Young, Hunter: Cawthorn, Joshua Dawson, Michael
Note on N89: Young, Hunter: Cawthorn, Joshua Dawson, Michael
Note on N90: Young, Hunter: Cawthorn, Joshua Dawson, Michael
Note on N91: Young, Hunter: Cawthorn, Joshua Dawson, Michael
Note on N134: Young, Hunter: Freeman, Jamil McMurry, Barry
Note on N135: Young, Hunter: Freeman, Jamil McMurry, Barry
Note on N136: Young, Hunter: Freeman, Jamil McMurry, Barry
Note on N137: Young, Hunter: Freeman, Jamil McMurry, Barry
Note on N138: Young, Hunter: Freeman, Jamil McMurry, Barry
Note on N139: Young, Hunter: Freeman, Jamil McMurry, Barry
Note on N140: Young, Hunter: Freeman, Jamil McMurry, Barry
Note on N141: Young, Hunter: Freeman, Jamil McMurry, Barry
Note on N142: Young, Hunter: Freeman, Jamil McMurry, Barry
Note on N143: Young, Hunter: Freeman, Jamil McMurry, Barry
Note on N144: Young, Hunter: Freeman, Jamil McMurry, Barry
Note on N145: Young, Hunter: Freeman, Jamil McMurry, Barry
Note on N146: Young, Hunter: Freeman, Jamil McMurry, Barry
Note on N147: Young, Hunter: Freeman, Jamil McMurry, Barry
Note on N148: Young, Hunter: Freeman, Jamil McMurry, Barry
Note on N149: Young, Hunter: Freeman, Jamil McMurry, Barry
Note on N150: Young, Hunter: Freeman, Jamil McMurry, Barry
Note on N151: Young, Hunter: Freeman, Jamil McMurry, Barry
Note on N152: Young, Hunter: Freeman, Jamil McMurry, Barry
Note on N153: Young, Hunter: Freeman, Jamil McMurry, Barry
Note on N154: Young, Hunter: Freeman, Jamil McMurry, Barry
Note on N155: Young, Hunter: Freeman, Jamil McMurry, Barry
Note on N156: Young, Hunter: Freeman, Jamil McMurry, Barry
Note on N157: Young, Hunter: Freeman, Jamil McMurry, Barry
Note on N158: Young, Hunter: Freeman, Jamil McMurry, Barry
Note on N159: Young, Hunter: Freeman, Jamil McMurry, Barry
Note on N160: Young, Hunter: Freeman, Jamil McMurry, Barry
Note on N161: Young, Hunter: Freeman, Jamil McMurry, Barry
Note on N162: Young, Hunter: Freeman, Jamil McMurry, Barry
Note on N163: Young, Hunter: Freeman, Jamil McMurry, Barry
Note on N164: Young, Hunter: Freeman, Jamil McMurry, Barry
Note on N165: Young, Hunter: Freeman, Jamil McMurry, Barry
Note on N166: Young, Hunter: Freeman, Jamil McMurry, Barry
Note on N167: Young, Hunter: Freeman, Jamil McMurry, Barry
Note on N168: Young, Hunter: Freeman, Jamil McMurry, Barry
Note on N169: Young, Hunter: Freeman, Jamil McMurry, Barry
Note on N170: Young, Hunter: Sanchez, George
Note on N171: Young, Hunter: Sanchez, George
Note on N172: Young, Hunter: Sanchez, George
Note on N173: Young, Hunter: Sanchez, George
Note on N174: Young, Hunter: Sanchez, George
Note on N175: Young, Hunter: Sanchez, George
Note on N176: Young, Hunter: Sanchez, George
Note on N177: Young, Hunter: Sanchez, George
Note on N178: Young, Hunter: Sanchez, George
Note on N179: Young, Hunter: Sanchez, George
Note on N180: Young, Hunter: Sanchez, George
Note on N181: Young, Hunter: Sanchez, George
Note on N182: Young, Hunter: Sanchez, George
Note on N183: Young, Hunter: Sanchez, George
Note on N184: Young, Hunter: Sanchez, George
Note on N185: Young, Hunter: Sanchez, George
Note on N186: Young, Hunter: Sanchez, George
Note on N187: Young, Hunter: Sanchez, George
Note on N188: Young, Hunter: Sanchez, George
Note on N189: Young, Hunter: Sanchez, George
Note on N190: Young, Hunter: Sanchez, George
Note on N191: Young, Hunter: Sanchez, George
Note on N192: Young, Hunter: Sanchez, George
Note on N193: Young, Hunter: Sanchez, George
Note on N194: Young, Hunter: Sanchez, George
Note on N195: Young, Hunter: Sanchez, George
Note on N196: Young, Hunter: Sanchez, George
Note on N197: Young, Hunter: Sanchez, George
Note on N198: Young, Hunter: Sanchez, George
Note on N199: Young, Hunter: Sanchez, George
Note on N200: Young, Hunter: Sanchez, George
Note on N201: Young, Hunter: Sanchez, George
Note on N202: Young, Hunter: Sanchez, George
Note on N203: Young, Hunter: Sanchez, George
Note on N204: Young, Hunter: Sanchez, George
Note on N205: Young, Hunter: Sanchez, George
Note on N206: Young, Hunter: Sanchez, George
Note on N207: Young, Hunter: Sanchez, George
Note on N208: Young, Hunter: Sanchez, George
Note on N209: Young, Hunter: Sanchez, George
Note on N210: Young, Hunter: Sanchez, George
Note on N211: Young, Hunter: Sanchez, George
Note on N212: Young, Hunter: Sanchez, George
Note on N213: Young, Hunter: Sanchez, George
Note on N353: Young, Hunter: Alegbeley, Ladi
Note on N354: Young, Hunter: Alegbeley, Ladi
Note on N355: Young, Hunter: Alegbeley, Ladi
Note on N356: Young, Hunter: Alegbeley, Ladi
Note on N357: Young, Hunter: Alegbeley, Ladi
Note on N358: Young, Hunter: Alegbeley, Ladi
Note on N359: Young, Hunter: Alegbeley, Ladi
Note on N360: Young, Hunter: Alegbeley, Ladi
Note on N361: Young, Hunter: Alegbeley, Ladi
Note on N362: Young, Hunter: Alegbeley, Ladi
Note on N363: Young, Hunter: Alegbeley, Ladi
Note on N364: Young, Hunter: Alegbeley, Ladi
Note on N365: Young, Hunter: Alegbeley, Ladi
Note on N366: Young, Hunter: Alegbeley, Ladi
Note on N367: Young, Hunter: Alegbeley, Ladi
Note on N368: Young, Hunter: Alegbeley, Ladi
Note on N369: Young, Hunter: Alegbeley, Ladi
Note on N370: Young, Hunter: Gamboa, Andrew
Note on N371: Young, Hunter: Gamboa, Andrew
Note on N372: Young, Hunter: Gamboa, Andrew
Note on N373: Young, Hunter: Gamboa, Andrew
Note on N374: Young, Hunter: Gamboa, Andrew
Note on N375: Young, Hunter: Gamboa, Andrew
Note on N376: Young, Hunter: Gamboa, Andrew
Note on N377: Young, Hunter: Gamboa, Andrew
Note on N378: Young, Hunter: Gamboa, Andrew
Note on N379: Young, Hunter: Gamboa, Andrew
Note on N380: Young, Hunter: Gamboa, Andrew
Note on N381: Young, Hunter: Gamboa, Andrew
Note on N382: Young, Hunter: Gamboa, Andrew
Note on N383: Young, Hunter: Gamboa, Andrew
Note on N384: Young, Hunter: Gamboa, Andrew
Note on N385: Young, Hunter: Gamboa, Andrew
Note on N386: Young, Hunter: Gamboa, Andrew
Note on N387: Young, Hunter: Gamboa, Andrew
Note on N388: Young, Hunter: Gamboa, Andrew
Note on N389: Young, Hunter: Gamboa, Andrew
Note on N390: Young, Hunter: Gamboa, Andrew
Note on N391: Young, Hunter: Gamboa, Andrew
Note on N392: Young, Hunter: Gamboa, Andrew
Note on N393: Young, Hunter: Gamboa, Andrew
Note on N394: Young, Hunter: Gamboa, Andrew
Note on N395: Young, Hunter: Gamboa, Andrew
Note on N396: Young, Hunter: Gamboa, Andrew
Note on N766: Young, Hunter: Gamboa, Andrew
Note on N767: Young, Hunter: Gamboa, Andrew
Note on N768: Young, Hunter: Gamboa, Andrew
Note on N769: Young, Hunter: Gamboa, Andrew
Note on N770: Young, Hunter: Gamboa, Andrew
Note on N771: Young, Hunter: Gamboa, Andrew
Note on N772: Young, Hunter: Gamboa, Andrew
Note on N773: Young, Hunter: Gamboa, Andrew
Note on N774: Young, Hunter: Gamboa, Andrew
Note on N775: Young, Hunter: Gamboa, Andrew
Note on N776: Young, Hunter: Gamboa, Andrew
Note on N777: Young, Hunter: Gamboa, Andrew
Note on N778: Young, Hunter: Gamboa, Andrew
Note on N779: Young, Hunter: Gamboa, Andrew
Note on N780: Young, Hunter: Gamboa, Andrew
Note on N781: Young, Hunter: Gamboa, Andrew
Note on N782: Young, Hunter: Gamboa, Andrew
Note on N783: Young, Hunter: Gamboa, Andrew
Note on N784: Young, Hunter: Gamboa, Andrew
Note on N785: Young, Hunter: Gamboa, Andrew
Note on N786: Young, Hunter: Gamboa, Andrew
Note on N787: Young, Hunter: Gamboa, Andrew
Note on N788: Young, Hunter: Gamboa, Andrew
Note on N789: Young, Hunter: Gamboa, Andrew
Note on N790: Young, Hunter: Gamboa, Andrew
Note on N791: Young, Hunter: Gamboa, Andrew
Note on N792: Young, Hunter: Gamboa, Andrew
Note on N793: Young, Hunter: Gamboa, Andrew
Note on N794: Young, Hunter: Gamboa, Andrew
Note on N795: Young, Hunter: Gamboa, Andrew
Note on N796: Young, Hunter: Gamboa, Andrew
Note on N797: Young, Hunter: Gamboa, Andrew
Note on N798: Young, Hunter: Gamboa, Andrew
Note on N799: Young, Hunter: Gamboa, Andrew
Note on N800: Young, Hunter: Gamboa, Andrew
Note on N801: Young, Hunter: Gamboa, Andrew
Note on N802: Young, Hunter: Gamboa, Andrew
Note on N803: Young, Hunter: Gamboa, Andrew
Note on N804: Young, Hunter: Gamboa, Andrew
Note on N805: Young, Hunter: Gamboa, Andrew
Note on N806: Young, Hunter: Gamboa, Andrew
Note on N807: Young, Hunter: Gamboa, Andrew
Note on N808: Young, Hunter: Gamboa, Andrew
Note on N809: Young, Hunter: Gamboa, Andrew
Note on N810: Young, Hunter: Gamboa, Andrew
Note on N811: Young, Hunter: Gamboa, Andrew
Note on N812: Young, Hunter: Gamboa, Andrew
Note on N813: Young, Hunter: Gamboa, Andrew
Note on N814: Young, Hunter: Gamboa, Andrew
Note on N815: Young, Hunter: Gamboa, Andrew
Note on N816: Young, Hunter: Gamboa, Andrew
Note on N817: Young, Hunter: Gamboa, Andrew
Note on N818: Young, Hunter: Gamboa, Andrew